## SLW NOA
SLW NOA | [5 empty] | 2027-05-24 | 2027-06-29 |  | 36
Phase | Trade | Parent | Task | Task Owner | Consultant | Baseline Finish | Actual / Forecast Finish | Status | Slippage (days) | Overdue? | Days to Finish/Delay | RAG | Notes | CurKey | OvdRank | ShowFlag | DesignRank
Masterplan | Masterplan |  |  |  |  | 2026-08-31 | 2026-10-06 |  | 36 |  | 114 | Green |  | #REF! |  | 0
Masterplan | Masterplan | NOA Masterplan | Final NOA MP Direction From Development | Osama / Ahmed Ramadan | Shaker & (MY&A) | 2026-03-30 | 2026-03-30 | Completed | 0 | - | 0 | Red |  |  |  | 0
Masterplan | Masterplan | NOA Masterplan | VO With Shaker | Nour / Ali | Shaker & (MY&A) | 2026-04-13 | 2026-06-29 | Inprogress | 77 | Yes | 15 | Amber |  |  | 1 | 1 | 1
Masterplan | Masterplan | NOA Masterplan | 100% Schematic Design (Icluding Grading Levels) | Osama / Ahmed Ramadan | Shaker & (MY&A) | 2026-05-11 | 2026-06-11 | Completed | 31 | - | 0 | Red |  |  |  | 0
Masterplan | Masterplan | NOA Masterplan | Ministerial Decree Package (For NOA) | Osama / Ahmed Ramadan | Shaker & (MY&A) | 2026-05-11 | 2026-05-11 | Completed | 0 | - | 0 | Red |  |  |  | 0
Masterplan | Masterplan | NOA Masterplan | HAP Review - 100% SD | Osama / Ahmed Ramadan | HAP | 2026-05-25 | 2026-06-30 | Inprogress | 36 | Yes | 16 | Amber |  |  | 2 | 1 | 2
Masterplan | Masterplan | NOA Masterplan | 100% Detailed Design | Osama / Ahmed Ramadan | Shaker & (MY&A) | 2026-07-20 | 2026-08-18 | Not Started | 29 | No | 65 | Green |  |  |  | 0
Masterplan | Masterplan | NOA Masterplan | HAP Review - 100% DD | Osama / Ahmed Ramadan | HAP | 2026-08-03 | 2026-08-25 | Not Started | 22 | No | 72 | Green |  |  |  | 0
Masterplan | Masterplan | NOA Masterplan | Tender Package | Osama / Ahmed Ramadan | Shaker & (MY&A) | 2026-08-17 | 2026-09-27 | Not Started | 41 | No | 105 | Green |  |  |  | 0
Masterplan | Masterplan | NOA Masterplan | HAP Review - TD | Osama / Ahmed Ramadan | HAP | 2026-08-31 | 2026-10-06 | Not Started | 36 | No | 114 | Green |  |  |  | 0
Infrastructure | Infrastructure |  |  |  |  | 2026-08-31 | 2026-10-02 |  | 32 |  | 110 | Green |  | Infrastructure¦Infrastructure |  | 0
Infrastructure | Infrastructure | NOA Infra & Roads | Final NOA MP Direction From Development | Osama / Ahmed Ramadan |  | 2026-03-30 | 2026-03-30 | Completed | 0 | - | 0 | Red |  |  |  | 0
Infrastructure | Infrastructure | NOA Infra & Roads | VO With Shaker | Nour / Ali | Shaker | 2026-04-13 | 2026-06-29 | Inprogress | 77 | Yes | 15 | Amber |  |  | 3 | 1 | 3
Infrastructure | Infrastructure | NOA Infra & Roads | Kick-off - NOA Infra & Roads | Osama / Ahmed Ramadan | Shaker |  | 2026-05-10 | Completed |  | - | 0 | Red |  |  |  | 0
Infrastructure | Infrastructure | NOA Infra & Roads | 100% Schematic Design | Osama / Ahmed Ramadan | Shaker | 2026-05-11 | 2026-06-11 | Completed | 31 | - | 0 | Red |  |  |  | 0
Infrastructure | Infrastructure | NOA Infra & Roads | HAP Review - 100% SD | Osama / Ahmed Ramadan | HAP | 2026-05-25 | 2026-06-30 | Inprogress | 36 | Yes | 16 | Amber |  |  | 4 | 1 | 4
Infrastructure | Infrastructure | NOA Infra & Roads | 100% Detailed Design | Osama / Ahmed Ramadan | Shaker | 2026-07-20 | 2026-08-18 | Not Started | 29 | No | 65 | Green |  |  |  | 0
Infrastructure | Infrastructure | NOA Infra & Roads | HAP Review - 100% DD | Osama / Ahmed Ramadan | HAP | 2026-08-03 | 2026-08-25 | Not Started | 22 | No | 72 | Green |  |  |  | 0
Infrastructure | Infrastructure | NOA Infra & Roads | Tender Package | Osama / Ahmed Ramadan | Shaker | 2026-08-17 | 2026-09-25 | Not Started | 39 | No | 103 | Green |  |  |  | 0
Infrastructure | Infrastructure | NOA Infra & Roads | HAP Review - TD | Osama / Ahmed Ramadan | HAP | 2026-08-31 | 2026-10-02 | Not Started | 32 | No | 110 | Green |  |  |  | 0
Retaining walls | Retaining walls |  |  |  |  | 2026-06-29 | 2026-08-04 |  | 36 |  | 51 | Green |  | Retaining walls¦Retaining walls |  | 0
Retaining walls | Retaining walls | NOA RWs | NOA RWs Early Package | Hoda / Roshdy | Crancnell | 2026-06-22 | 2026-07-28 | Not Started | 36 | No | 44 | Green |  |  |  | 0
Retaining walls | Retaining walls | NOA RWs | HAP Review - EP | Hoda / Roshdy | HAP | 2026-06-29 | 2026-08-04 | Not Started | 36 | No | 51 | Green |  |  |  | 0
Landscape | Landscape |  |  |  |  | 2027-01-11 | 2027-01-11 |  | 0 |  | 211 | Green |  | Landscape¦Landscape |  | 0
Landscape | Landscape | NOA Landscape | 50% Concept Design (Including NOA RWs) | Hoda / Roshdy | Crancnell | 2026-07-20 | 2026-08-25 | Not Started | 36 | No | 72 | Green |  |  |  | 0
Landscape | Landscape | NOA Landscape | HAP Review - 50% CD | Hoda / Roshdy | HAP | 2026-08-03 | 2026-09-08 | Not Started | 36 | No | 86 | Green |  |  |  | 0
Landscape | Landscape | NOA Landscape | 100% Concept Design | Hoda / Roshdy | Crancnell | 2026-09-28 | 2026-11-03 | Not Started | 36 | No | 142 | Green |  |  |  | 0
Landscape | Landscape | NOA Landscape | HAP Review - 100% CD | Hoda / Roshdy | HAP | 2026-10-12 | 2026-11-17 | Not Started | 36 | No | 156 | Green |  |  |  | 0
Landscape | Landscape | NOA Landscape | Cost Plan - 100% CD | Nour / Ali | Survtec | 2026-10-19 | 2026-11-24 | Not Started | 36 | No | 163 | Green |  |  |  | 0
Landscape | Landscape | NOA Landscape | 50% Schematic Design | Hoda / Roshdy | Crancnell | 2026-11-09 | 2026-11-09 | Not Started | 0 | No | 148 | Green |  |  |  | 0
Landscape | Landscape | NOA Landscape | HAP Review - 50% SD | Hoda / Roshdy | HAP | 2026-11-23 | 2026-11-23 | Not Started | 0 | No | 162 | Green |  |  |  | 0
Landscape | Landscape | NOA Landscape | 100% Schematic Design | Hoda / Roshdy | Crancnell | 2026-12-21 | 2026-12-21 | Not Started | 0 | No | 190 | Green |  |  |  | 0
Landscape | Landscape | NOA Landscape | HAP Review - 100% SD | Hoda / Roshdy | HAP | 2027-01-04 | 2027-01-04 | Not Started | 0 | No | 204 | Green |  |  |  | 0
Landscape | Landscape | NOA Landscape | Cost Plan - 100% SD | Nour / Ali | Survtec | 2027-01-11 | 2027-01-11 | Not Started | 0 | No | 211 | Green |  |  |  | 0
Twain Apartments-Phase 5 | Buildings |  |  |  |  | 2025-05-19 | 2026-07-20 |  | 427 |  | 36 | Green |  | Twain Apartments-Phase 5¦Buildings |  | 0
Twain Apartments-Phase 5 | Buildings | Twain Apartments-Phase 5 | 100% Concept Design |  | Archimid | 2023-08-20 | 2023-08-20 | Completed | 0 | - | 0 | Red |  |  |  | 0
Twain Apartments-Phase 5 | Buildings | Twain Apartments-Phase 5 | HAP Review - 100% CD |  | HAP | 2023-09-03 | 2023-09-03 | Completed | 0 | - | 0 | Red |  |  |  | 0
Twain Apartments-Phase 5 | Buildings | Twain Apartments-Phase 5 | Delay in Commencing Schematic Design |  | Archimid |  |  | Inprogress |  |  |  | Amber |  |  |  | 0
Twain Apartments-Phase 5 | Buildings | Twain Apartments-Phase 5 | 100% Schematic Design |  | Archimid | 2024-06-26 | 2024-06-26 | Completed | 0 | - | 0 | Red |  |  |  | 0
Twain Apartments-Phase 5 | Buildings | Twain Apartments-Phase 5 | HAP Review - 100% SD |  | HAP | 2024-07-10 | 2024-07-10 | Completed | 0 | - | 0 | Red |  |  |  | 0
Twain Apartments-Phase 5 | Buildings | Twain Apartments-Phase 5 | Cost Plan - 100% SD | Nour / Ali | Survtec | 2024-07-10 | 2024-07-10 | Completed | 0 | - | 0 | Red |  |  |  | 0
Twain Apartments-Phase 5 | Buildings | Twain Apartments-Phase 5 | 50% Detailed Design (Incl. Permits PKG) |  | Archimid | 2024-09-14 | 2024-09-14 | Completed | 0 | - | 0 | Red |  |  |  | 0
Twain Apartments-Phase 5 | Buildings | Twain Apartments-Phase 5 | 100% Detailed Design |  | Archimid | 2024-11-12 | 2024-11-17 | Completed | 5 | - | 0 | Red |  |  |  | 0
Twain Apartments-Phase 5 | Buildings | Twain Apartments-Phase 5 | HAP Review - 100% DD |  | HAP | 2024-12-04 | 2024-12-30 | Completed | 26 | - | 0 | Red |  |  |  | 0
Twain Apartments-Phase 5 | Buildings | Twain Apartments-Phase 5 | Structure Peer Review |  | Archimid | 2024-12-04 | 2024-12-30 | Completed | 26 | - | 0 | Red |  |  |  | 0
Twain Apartments-Phase 5 | Buildings | Twain Apartments-Phase 5 | Cost Plan - 100% DD | Nour / Ali | Survtec | 2024-12-04 | 2024-12-30 | Completed | 26 | - | 0 | Red |  |  |  | 0
Twain Apartments-Phase 5 | Buildings | Twain Apartments-Phase 5 | Tender Package (Flexi Finish) |  | Archimid | 2025-04-28 | 2025-04-28 | Completed | 0 | - | 0 | Red |  |  |  | 0
Twain Apartments-Phase 5 | Buildings | Twain Apartments-Phase 5 | HAP Review - TD (Flexi Finish) |  | HAP | 2025-05-19 | 2025-05-19 | Completed | 0 | - | 0 | Red |  |  |  | 0
Twain Apartments-Phase 5 | Buildings | Twain Apartments-Phase 5 | Tender Package ( Fully Finished) | Osama / Ahmed Ramadan | Archimid |  | 2026-07-06 | Inprogress |  | No | 22 | Green |  |  |  | 0
Twain Apartments-Phase 5 | Buildings | Twain Apartments-Phase 5 | HAP Review - TD | Osama / Ahmed Ramadan | HAP |  | 2026-07-20 | Not Started |  | No | 36 | Green |  |  |  | 0
Authorities Twain Apartments-Phase 5 | Authorities |  |  |  |  | 2026-01-05 | 2026-10-12 |  | 280 |  | 120 | Green |  | Authorities Twain Apartments-Phase 5¦Authorities |  | 0
Authorities Twain Apartments-Phase 5 | Authorities | Authorities Twain Apartments-Phase 5 | MD Approval 2 [Phases 5A, 5B, 5C-1, 6A] | Afifi |  | 2025-10-13 | 2026-04-01 | Completed | 170 | - | 0 | Red |  |  |  | 0
Authorities Twain Apartments-Phase 5 | Authorities | Authorities Twain Apartments-Phase 5 | Civil Defense / Decenial Liability [Phases 5A, 5B, 5C-1, 6A] | Afifi |  | 2025-11-24 | 2026-07-20 | Inprogress | 238 | No | 36 | Green |  |  |  | 0
Authorities Twain Apartments-Phase 5 | Authorities | Authorities Twain Apartments-Phase 5 | Permits Approval [Phases 5A, 5B, 5C-1, 6A] | Afifi |  | 2026-01-05 | 2026-08-31 | Not Started | 238 | No | 78 | Green |  |  |  | 0
Authorities Twain Apartments-Phase 5 | Authorities | Authorities Twain Apartments-Phase 5 | Mineral License | Afifi |  | 2026-02-16 | 2026-10-12 | Not Started | 238 | No | 120 | Green |  |  |  | 0
One Story Villas-Ph5 | Buildings |  |  |  |  | 2025-06-22 | 2026-06-01 |  | 344 |  | -13 | Red |  | One Story Villas-Ph5¦Buildings |  | 0
One Story Villas-Ph5 | Buildings | One Story Villas-Ph5 | 100% Concept Design (Arch.) |  | Archimid |  | 2023-12-26 | Completed |  | - | 0 | Red |  |  |  | 0
One Story Villas-Ph5 | Buildings | One Story Villas-Ph5 | HAP Review - 100% CD (Arch) |  | HAP |  | 2024-01-16 | Completed |  | - | 0 | Red |  |  |  | 0
One Story Villas-Ph5 | Buildings | One Story Villas-Ph5 | Cost Plan - 100% CD | Nour / Ali | Survtec |  | 2024-01-30 | Completed |  | - | 0 | Red |  |  |  | 0
One Story Villas-Ph5 | Buildings | One Story Villas-Ph5 | 100% Concept Design (Str. & MEP) |  | Archimid | 2023-12-26 | 2024-06-15 | Completed | 172 | - | 0 | Red |  |  |  | 0
One Story Villas-Ph5 | Buildings | One Story Villas-Ph5 | HAP Review - 100% CD (Str. & MEP) |  | HAP | 2024-01-16 | 2024-06-29 | Completed | 165 | - | 0 | Red |  |  |  | 0
One Story Villas-Ph5 | Buildings | One Story Villas-Ph5 | Postponing Design for Workload Purpose |  | Archimid |  |  | Completed |  |  | 0 | Amber |  |  |  | 0
One Story Villas-Ph5 | Buildings | One Story Villas-Ph5 | 100% Schematic Design |  | Archimid | 2024-09-09 | 2024-09-09 | Completed | 0 | - | 0 | Red |  |  |  | 0
One Story Villas-Ph5 | Buildings | One Story Villas-Ph5 | HAP Review - 100% SD |  | HAP | 2024-10-20 | 2024-10-20 | Completed | 0 | - | 0 | Red |  |  |  | 0
One Story Villas-Ph5 | Buildings | One Story Villas-Ph5 | Cost Plan - 100% SD | Nour / Ali | Survtec | 2024-10-27 | 2024-10-27 | Completed | 0 | - | 0 | Red |  |  |  | 0
One Story Villas-Ph5 | Buildings | One Story Villas-Ph5 | 50% Detailed Design (Incl. Permits PKG) |  | Archimid | 2024-11-17 | 2024-11-10 | Completed | -7 | - | 0 | Red |  |  |  | 0
One Story Villas-Ph5 | Buildings | One Story Villas-Ph5 | 100% Detailed Design |  | Archimid | 2024-12-29 | 2024-11-17 | Completed | -42 | - | 0 | Red |  |  |  | 0
One Story Villas-Ph5 | Buildings | One Story Villas-Ph5 | HAP Review - 100% DD |  | HAP | 2025-01-19 | 2025-01-12 | Completed | -7 | - | 0 | Red |  |  |  | 0
One Story Villas-Ph5 | Buildings | One Story Villas-Ph5 | Structure Peer Review |  | Archimid | 2025-01-19 | 2025-01-12 | Completed | -7 | - | 0 | Red |  |  |  | 0
One Story Villas-Ph5 | Buildings | One Story Villas-Ph5 | Cost Plan - 100% DD | Nour / Ali | Survtec | 2025-01-19 | 2025-01-12 | Completed | -7 | - | 0 | Red |  |  |  | 0
One Story Villas-Ph5 | Buildings | One Story Villas-Ph5 | Tender Package |  | Archimid | 2025-04-20 | 2025-04-20 | Completed | 0 | - | 0 | Red |  |  |  | 0
One Story Villas-Ph5 | Buildings | One Story Villas-Ph5 | HAP Review - TD |  | HAP | 2025-06-22 | 2025-06-22 | Completed | 0 | - | 0 | Red |  |  |  | 0
One Story Villas-Ph5 | Buildings | One Story Villas-Ph5 | Revised Tender Package (Regarding BOQs Splitting) |  | Archimid |  | 2026-05-17 | Completed |  | - | 0 | Red |  |  |  | 0
One Story Villas-Ph5 | Buildings | One Story Villas-Ph5 | HAP Review - TD |  | HAP |  | 2026-06-01 | Completed |  | - | 0 | Red |  |  |  | 0
Authorities One Story Villas-Ph5 | Authorities |  |  |  |  | 2026-02-16 | 2026-08-31 |  | 196 |  | 78 | Green |  | Authorities One Story Villas-Ph5¦Authorities |  | 0
Authorities One Story Villas-Ph5 | Authorities | Authorities One Story Villas-Ph5 | MD Approval 2 [Phases 5A, 5B, 5C-1, 6A] | Afifi |  | 2025-10-13 | 2026-04-01 | Completed | 170 | - | 0 | Red |  |  |  | 0
Authorities One Story Villas-Ph5 | Authorities | Authorities One Story Villas-Ph5 | Civil Defense / Decenial Liability [Phases 5A, 5B, 5C-1, 6A] | Afifi |  | 2025-11-24 | 2026-04-01 | Completed | 128 | - | 0 | Red |  |  |  | 0
Authorities One Story Villas-Ph5 | Authorities | Authorities One Story Villas-Ph5 | Permits Approval [Phases 5A, 5B, 5C-1, 6A] | Afifi |  | 2026-01-05 | 2026-06-30 | Inprogress | 176 | Yes | 16 | Amber |  |  | 5 | 1 | 5
Authorities One Story Villas-Ph5 | Authorities | Authorities One Story Villas-Ph5 | Mineral License | Afifi |  | 2026-02-16 | 2026-08-31 | Not Started | 196 | No | 78 | Green |  |  |  | 0
Single Story Villas (E & D) -Ph6 | Buildings |  |  |  |  | 2025-11-12 | 2026-06-17 |  | 217 |  | 3 | Amber |  | Single Story Villas (E & D) -Ph6¦Buildings |  | 0
Single Story Villas (E & D) -Ph6 | Buildings | Single Story Villas (E & D) -Ph6 | 100% Concept Design (Arch.) |  | GDG | 2025-01-09 | 2025-03-04 | Completed | 54 | - | 0 | Red |  |  |  | 0
Single Story Villas (E & D) -Ph6 | Buildings | Single Story Villas (E & D) -Ph6 | HAP Review - 100% CD (Arch) |  | HAP | 2025-01-30 | 2025-03-26 | Completed | 55 | - | 0 | Red |  |  |  | 0
Single Story Villas (E & D) -Ph6 | Buildings | Single Story Villas (E & D) -Ph6 | Cost Plan - 100% CD | Nour / Ali | Survtec | 2025-02-13 | 2025-04-09 | Completed | 55 | - | 0 | Red |  |  |  | 0
Single Story Villas (E & D) -Ph6 | Buildings | Single Story Villas (E & D) -Ph6 | 100% Concept Design (Str. & MEP) |  | GDG | 2025-02-06 | 2025-05-15 | Completed | 98 | - | 0 | Red |  |  |  | 0
Single Story Villas (E & D) -Ph6 | Buildings | Single Story Villas (E & D) -Ph6 | HAP Review - 100% CD (Str. & MEP) |  | HAP | 2025-02-20 | 2025-05-29 | Completed | 98 | - | 0 | Red |  |  |  | 0
Single Story Villas (E & D) -Ph6 | Buildings | Single Story Villas (E & D) -Ph6 | 100% Schematic Design |  | GDG | 2025-03-20 | 2025-07-10 | Completed | 112 | - | 0 | Red |  |  |  | 0
Single Story Villas (E & D) -Ph6 | Buildings | Single Story Villas (E & D) -Ph6 | HAP Review - 100% SD |  | HAP | 2025-04-03 | 2025-07-24 | Completed | 112 | - | 0 | Red |  |  |  | 0
Single Story Villas (E & D) -Ph6 | Buildings | Single Story Villas (E & D) -Ph6 | Cost Plan - 100% SD | Nour / Ali | Survtec | 2025-04-03 | 2025-07-24 | Completed | 112 | - | 0 | Red |  |  |  | 0
Single Story Villas (E & D) -Ph6 | Buildings | Single Story Villas (E & D) -Ph6 | 50% Detailed Design (Incl. Permits PKG) |  | GDG | 2025-05-01 | 2025-08-21 | Completed | 112 | - | 0 | Red |  |  |  | 0
Single Story Villas (E & D) -Ph6 | Buildings | Single Story Villas (E & D) -Ph6 | 100% Detailed Design |  | GDG | 2025-09-24 | 2025-09-24 | Completed | 0 | - | 0 | Red |  |  |  | 0
Single Story Villas (E & D) -Ph6 | Buildings | Single Story Villas (E & D) -Ph6 | HAP Review - 100% DD |  | HAP | 2025-10-15 | 2025-10-15 | Completed | 0 | - | 0 | Red |  |  |  | 0
Single Story Villas (E & D) -Ph6 | Buildings | Single Story Villas (E & D) -Ph6 | Structure Peer Review (ABCG) |  | GDG | 2025-10-15 | 2025-10-22 | Completed | 7 | - | 0 | Red |  |  |  | 0
Single Story Villas (E & D) -Ph6 | Buildings | Single Story Villas (E & D) -Ph6 | Cost Plan - 100% DD | Nour / Ali | Survtec | 2025-10-15 | 2025-12-08 | Completed | 54 | - | 0 | Red |  |  |  | 0
Single Story Villas (E & D) -Ph6 | Buildings | Single Story Villas (E & D) -Ph6 | Tender Package (+Permits DWGs) |  | GDG | 2025-10-29 | 2026-04-29 | Completed | 182 | - | 0 | Red |  |  |  | 0
Single Story Villas (E & D) -Ph6 | Buildings | Single Story Villas (E & D) -Ph6 | HAP Review - TD |  | HAP | 2025-11-12 | 2026-06-17 | Completed | 217 | - | 0 | Amber |  |  |  | 0
Authorities - Single Story Villas (E & D) -Ph6 | Authorities |  |  |  |  | 2026-06-08 | 2027-02-23 |  | 260 |  | 254 | Green |  | Authorities - Single Story Villas (E & D) -Ph6¦Authorities |  | 0
Authorities - Single Story Villas (E & D) -Ph6 | Authorities | Authorities - Single Story Villas (E & D) -Ph6 | MD Approval 3 [Phases 05-C, 06] | Afifi |  | 2026-02-02 | 2026-10-20 | Not Started | 260 | No | 128 | Green |  |  |  | 0
Authorities - Single Story Villas (E & D) -Ph6 | Authorities | Authorities - Single Story Villas (E & D) -Ph6 | Civil Defense / Decenial Liability [Phases 05-C, 06] | Afifi |  | 2026-03-16 | 2026-12-01 | Not Started | 260 | No | 170 | Green |  |  |  | 0
Authorities - Single Story Villas (E & D) -Ph6 | Authorities | Authorities - Single Story Villas (E & D) -Ph6 | Permits Approval [Phases 05-C, 06] | Afifi |  | 2026-04-27 | 2027-01-12 | Not Started | 260 | No | 212 | Green |  |  |  | 0
Authorities - Single Story Villas (E & D) -Ph6 | Authorities | Authorities - Single Story Villas (E & D) -Ph6 | Mineral License | Afifi |  | 2026-06-08 | 2027-02-23 | Not Started | 260 | No | 254 | Green |  |  |  | 0
Type A Shimmers | Buildings |  |  |  |  | 2025-11-09 | 2026-07-05 |  | 238 |  | 21 | Amber |  | Type A Shimmers¦Buildings |  | 0
Type A Shimmers | Buildings | Type A Shimmers | 100% Concept Design (Arch.) |  | GDG | 2024-01-10 15:00 | 2024-01-14 | Completed | 3.375 | - | 0 | Red |  |  |  | 0
Type A Shimmers | Buildings | Type A Shimmers | HAP Review - 100% CD (Arch) |  | HAP | 2024-01-24 15:00 | 2024-02-05 | Completed | 11.375 | - | 0 | Red |  |  |  | 0
Type A Shimmers | Buildings | Type A Shimmers | Cost Plan - 100% CD | Nour / Ali | Survtec | 2024-01-24 15:00 | 2024-01-28 | Completed | 3.375 | - | 0 | Red |  |  |  | 0
Type A Shimmers | Buildings | Type A Shimmers | 100% Concept Design (Arch.) VNour / Alidation |  | GDG |  | 2024-02-19 | Completed |  | - | 0 | Red |  |  |  | 0
Type A Shimmers | Buildings | Type A Shimmers | Delay in Commencing Remaining Design |  | GDG |  |  | Completed |  |  | 0 | Amber |  |  |  | 0
Type A Shimmers | Buildings | Type A Shimmers | 100% Schematic Design |  | GDG | 2024-11-24 | 2024-11-20 | Completed | -4 | - | 0 | Red |  |  |  | 0
Type A Shimmers | Buildings | Type A Shimmers | HAP Review - 100% SD |  | HAP | 2024-12-19 | 2024-12-19 | Completed | 0 | - | 0 | Red |  |  |  | 0
Type A Shimmers | Buildings | Type A Shimmers | Cost Plan - 100% SD | Nour / Ali | Survtec | 2025-01-26 | 2025-01-26 | Completed | 0 | - | 0 | Red |  |  |  | 0
Type A Shimmers | Buildings | Type A Shimmers | 50% Detailed Design (Incl. Permits PKG) |  | GDG | 2025-02-02 | 2025-02-02 | Completed | 0 | - | 0 | Red |  |  |  | 0
Type A Shimmers | Buildings | Type A Shimmers | HAP Review - 50% DD |  | HAP | 2025-02-16 | 2025-02-16 | Completed | 0 | - | 0 | Red |  |  |  | 0
Type A Shimmers | Buildings | Type A Shimmers | 100% Detailed Design |  | GDG | 2025-03-17 | 2025-03-17 | Completed | 0 | - | 0 | Red |  |  |  | 0
Type A Shimmers | Buildings | Type A Shimmers | HAP Review - 100% DD |  | HAP | 2025-04-30 | 2025-04-30 | Completed | 0 | - | 0 | Red |  |  |  | 0
Type A Shimmers | Buildings | Type A Shimmers | Structure Peer Review |  | GDG | 2025-06-10 | 2025-06-10 | Completed | 0 | - | 0 | Red |  |  |  | 0
Type A Shimmers | Buildings | Type A Shimmers | Cost Plan - 100% DD | Nour / Ali | Survtec | 2025-05-05 | 2025-05-05 | Completed | 0 | - | 0 | Red |  |  |  | 0
Type A Shimmers | Buildings | Type A Shimmers | Tender Package (Incl. Permits PKG) - For Flexi Finish | Osama / Ahmed Ramadan | GDG | 2025-10-19 | 2026-06-21 | Completed | 245 | - | 0 | Amber |  |  |  | 0
Type A Shimmers | Buildings | Type A Shimmers | Tender Package (Incl. Permits PKG) For Fully Finished | Osama / Ahmed Ramadan | GDG |  | 2026-06-21 | Completed |  | - | 0 | Amber |  |  |  | 0
Type A Shimmers | Buildings | Type A Shimmers | HAP Review - TD | Osama / Ahmed Ramadan | HAP | 2025-11-09 | 2026-07-05 | Inprogress | 238 | No | 21 | Amber |  |  |  | 0
Type D Shimmers | Buildings |  |  |  |  | 2026-02-13 | 2026-08-20 |  | 188 |  | 67 | Green |  | Type D Shimmers¦Buildings |  | 0
Type D Shimmers | Buildings | Type D Shimmers | 100% Schematic Design |  | GDG | 2025-09-28 | 2025-12-22 | Completed | 85 | - | 0 | Red |  |  |  | 0
Type D Shimmers | Buildings | Type D Shimmers | HAP Review - 100% SD |  | HAP | 2025-10-09 | 2025-12-31 | Completed | 83 | - | 0 | Red |  |  |  | 0
Type D Shimmers | Buildings | Type D Shimmers | Cost Plan - 100% SD | Nour / Ali | Survtec | 2025-10-13 | 2026-06-22 | Inprogress | 252 | Yes | 8 | Amber |  |  | 6 | 1 | 6
Type D Shimmers | Buildings | Type D Shimmers | 50% Detailed Design |  | GDG | 2025-11-09 | 2026-02-08 | Completed | 91 | - | 0 | Red |  |  |  | 0
Type D Shimmers | Buildings | Type D Shimmers | HAP Review - 50% DD |  | HAP | 2025-11-24 | 2026-02-18 | Completed | 86 | - | 0 | Red |  |  |  | 0
Type D Shimmers | Buildings | Type D Shimmers | 100% Detailed Design (Incl. Permits PKG) | Osama / Ahmed Ramadan | GDG | 2025-12-23 | 2026-07-02 | Inprogress | 191 | No | 18 | Amber |  |  |  | 0
Type D Shimmers | Buildings | Type D Shimmers | HAP Review - 100% DD | Osama / Ahmed Ramadan | HAP | 2026-01-07 | 2026-07-16 | Not Started | 190 | No | 32 | Green |  |  |  | 0
Type D Shimmers | Buildings | Type D Shimmers | Cost Plan - 100% DD | Nour / Ali | Survtec | 2026-01-07 | 2026-06-22 | Not Started | 166 | Yes | 8 | Amber |  |  | 7 | 1 | 7
Type D Shimmers | Buildings | Type D Shimmers | Tender Package | Osama / Ahmed Ramadan | GDG | 2026-01-29 | 2026-08-06 | Not Started | 189 | No | 53 | Green |  |  |  | 0
Type D Shimmers | Buildings | Type D Shimmers | HAP Review - TD | Osama / Ahmed Ramadan | HAP | 2026-02-13 | 2026-08-20 | Not Started | 188 | No | 67 | Green |  |  |  | 0
Authorities - Shimmers | Authorities |  |  |  |  | 2026-06-08 | 2027-02-23 |  | 260 |  | 254 | Green |  | Authorities - Shimmers¦Authorities |  | 0
Authorities - Shimmers | Authorities | Authorities - Shimmers | MD Approval 3 [Phases 05-C, 06] | Afifi |  | 2026-02-02 | 2026-10-20 | Not Started | 260 | No | 128 | Green |  |  |  | 0
Authorities - Shimmers | Authorities | Authorities - Shimmers | Civil Defense / Decenial Liability [Phases 05-C, 06] | Afifi |  | 2026-03-16 | 2026-12-01 | Not Started | 260 | No | 170 | Green |  |  |  | 0
Authorities - Shimmers | Authorities | Authorities - Shimmers | Permits Approval [Phases 05-C, 06] | Afifi |  | 2026-04-27 | 2027-01-12 | Not Started | 260 | No | 212 | Green |  |  |  | 0
Authorities - Shimmers | Authorities | Authorities - Shimmers | Mineral License | Afifi |  | 2026-06-08 | 2027-02-23 | Not Started | 260 | No | 254 | Green |  |  |  | 0
Solos | Buildings |  |  |  |  | 2025-11-24 | 2026-06-17 |  | 205 |  | 3 | Amber |  | Solos¦Buildings |  | 0
Solos | Buildings | Solos | 100% Concept Design (Arch.) |  | GDG |  | 2025-03-04 | Completed |  | - | 0 | Red |  |  |  | 0
Solos | Buildings | Solos | HAP Review - 100% CD (Arch) |  | HAP |  | 2025-04-03 | Completed |  | - | 0 | Red |  |  |  | 0
Solos | Buildings | Solos | Delay in Commencing Concept Design |  |  |  |  | Completed |  |  | 0 | Amber |  |  |  | 0
Solos | Buildings | Solos | 100% Concept Design (Plans and Renders) |  |  | 2025-01-15 | 2025-05-04 | Completed | 109 | - | 0 | Red |  |  |  | 0
Solos | Buildings | Solos | HAP Review - 100% CD |  | HAP | 2025-01-29 | 2025-05-18 | Completed | 109 | - | 0 | Red |  |  |  | 0
Solos | Buildings | Solos | Cost Plan - 100% CD | Nour / Ali | Survtec | 2025-01-29 | 2025-05-18 | Completed | 109 | - | 0 | Red |  |  |  | 0
Solos | Buildings | Solos | 100% Concept Design - BODR |  | GDG | 2025-02-26 | 2025-06-15 | Completed | 109 | - | 0 | Red |  |  |  | 0
Solos | Buildings | Solos | HAP Review - 100% CD BODR |  | HAP | 2025-03-12 | 2025-06-29 | Completed | 109 | - | 0 | Red |  |  |  | 0
Solos | Buildings | Solos | 100% Schematic Design |  | GDG | 2025-02-26 | 2025-07-06 | Completed | 130 | - | 0 | Red |  |  |  | 0
Solos | Buildings | Solos | HAP Review - 100% SD |  | HAP | 2025-03-12 | 2025-07-20 | Completed | 130 | - | 0 | Red |  |  |  | 0
Solos | Buildings | Solos | Cost Plan - 100% SD | Nour / Ali | Survtec | 2025-03-12 | 2025-07-20 | Completed | 130 | - | 0 | Red |  |  |  | 0
Solos | Buildings | Solos | 50% Detailed Design (Incl. Permits PKG) |  | GDG | 2025-04-09 | 2025-08-17 | Completed | 130 | - | 0 | Red |  |  |  | 0
Solos | Buildings | Solos | 100% Detailed Design |  | GDG | 2025-09-24 | 2025-09-24 | Completed | 0 | - | 0 | Red |  |  |  | 0
Solos | Buildings | Solos | HAP Review - 100% DD |  | HAP | 2025-10-15 | 2025-10-15 | Completed | 0 | - | 0 | Red |  |  |  | 0
Solos | Buildings | Solos | Structure Peer Review |  | GDG | 2025-10-15 | 2025-10-22 | Completed | 7 | - | 0 | Red |  |  |  | 0
Solos | Buildings | Solos | Cost Plan - 100% DD | Nour / Ali | Survtec | 2025-10-15 | 2025-12-08 | Completed | 54 | - | 0 | Red |  |  |  | 0
Solos | Buildings | Solos | Tender Package |  | GDG | 2025-11-02 | 2026-05-29 | Completed | 208 | - | 0 | Red |  |  |  | 0
Solos | Buildings | Solos | HAP Review - TD | Osama / Ahmed Ramadan | HAP | 2025-11-24 | 2026-06-17 | Completed | 205 | - | 0 | Amber |  |  |  | 0
Authorities Solos | Authorities |  |  |  |  | 2026-06-08 | 2027-02-23 |  | 260 |  | 254 | Green |  | Authorities Solos¦Authorities |  | 0
Authorities Solos | Authorities | Authorities Solos | MD Approval 3 [Phases 05-C, 06] | Afifi |  | 2026-02-02 | 2026-10-20 | Not Started | 260 | No | 128 | Green |  |  |  | 0
Authorities Solos | Authorities | Authorities Solos | Civil Defense / Decenial Liability [Phases 05-C, 06] | Afifi |  | 2026-03-16 | 2026-12-01 | Not Started | 260 | No | 170 | Green |  |  |  | 0
Authorities Solos | Authorities | Authorities Solos | Permits Approval [Phases 05-C, 06] | Afifi |  | 2026-04-27 | 2027-01-12 | Not Started | 260 | No | 212 | Green |  |  |  | 0
Authorities Solos | Authorities | Authorities Solos | Mineral License | Afifi |  | 2026-06-08 | 2027-02-23 | Not Started | 260 | No | 254 | Green |  |  |  | 0
Cabannas | Buildings |  |  |  |  | 2026-11-24 | 2027-01-04 |  | 41 |  | 204 | Green |  | Cabannas¦Buildings |  | 0
Cabannas | Buildings | Cabannas | Development Brief |  |  | 2025-08-17 | 2025-08-17 | Completed | 0 | - | 0 | Red |  |  |  | 0
Cabannas | Buildings | Cabannas | Brief Approval |  |  | 2025-09-11 | 2025-09-11 | Completed | 0 | - | 0 | Red |  |  |  | 0
Cabannas | Buildings | Cabannas | RFP - Cabannas |  |  | 2025-09-25 | 2025-09-25 | Completed | 0 | - | 0 | Red |  |  |  | 0
Cabannas | Buildings | Cabannas | Tender to assign consultant - Cabannas |  |  | 2025-11-03 | 2025-11-03 | Completed | 0 | - | 0 | Red |  |  |  | 0
Cabannas | Buildings | Cabannas | Kick-off - Cabannas |  |  | 2025-11-10 | 2025-11-10 | Completed | 0 | - | 0 | Red |  |  |  | 0
Cabannas | Buildings | Cabannas | Preconcept Design |  |  | 2025-12-11 | 2025-12-17 | Completed | 6 | - | 0 | Red |  |  |  | 0
Cabannas | Buildings | Cabannas | HAP Review - PC |  |  | 2025-12-18 | 2025-12-24 | Completed | 6 | - | 0 | Red |  |  |  | 0
Cabannas | Buildings | Cabannas | Cost Plan - PC | Nour / Ali | Survtec | 2025-12-25 | 2026-02-05 | Completed | 42 | - | 0 | Red |  |  |  | 0
Cabannas | Buildings | Cabannas | 50% Concept Design |  |  | 2026-01-25 | 2026-01-28 | Completed | 3 | - | 0 | Red |  |  |  | 0
Cabannas | Buildings | Cabannas | HAP Review - 50% CD |  |  | 2026-02-01 | 2026-02-04 | Completed | 3 | - | 0 | Red |  |  |  | 0
Cabannas | Buildings | Cabannas | 100% Concept Design |  |  | 2026-03-09 | 2026-03-11 | Completed | 2 | - | 0 | Red |  |  |  | 0
Cabannas | Buildings | Cabannas | HAP Review - 100% CD |  |  | 2026-03-16 | 2026-03-18 | Completed | 2 | - | 0 | Red |  |  |  | 0
Cabannas | Buildings | Cabannas | 100% Schematic Design | Mariam |  | 2026-06-15 | 2026-06-30 | Inprogress | 15 | Yes | 16 | Amber |  |  | 8 | 1 | 8
Cabannas | Buildings | Cabannas | HAP Review - 100% SD | Mariam | HAP | 2026-06-29 | 2026-07-14 | Not Started | 15 | No | 30 | Green |  |  |  | 0
Cabannas | Buildings | Cabannas | Cost Plan - 100% SD | Nour / Ali | Survtec | 2026-07-06 | 2026-07-21 | Not Started | 15 | No | 37 | Green |  |  |  | 0
Cabannas | Buildings | Cabannas | Tender to assign consultant - Cabannas | Ahmed Ragheb | HAP | 2026-06-16 | 2026-07-02 | Inprogress | 16 | No | 18 | Amber |  |  |  | 0
Cabannas | Buildings | Cabannas | BODR & Design validation | Osama / Ahmed Ramadan |  | 2026-06-23 | 2026-07-13 | Not Started | 20 | No | 29 | Green |  |  |  | 0
Cabannas | Buildings | Cabannas | HAP Review - BODR | Osama / Ahmed Ramadan |  | 2026-06-30 | 2026-07-20 | Not Started | 20 | No | 36 | Green |  |  |  | 0
Cabannas | Buildings | Cabannas | 100% Schematic Design | Osama / Ahmed Ramadan |  | 2026-07-21 | 2026-08-17 | Not Started | 27 | No | 64 | Green |  |  |  | 0
Cabannas | Buildings | Cabannas | HAP Review - 100% SD | Osama / Ahmed Ramadan |  | 2026-08-04 | 2026-08-31 | Not Started | 27 | No | 78 | Green |  |  |  | 0
Cabannas | Buildings | Cabannas | 50% Detailed Design - Inprogress PKG | Osama / Ahmed Ramadan |  | 2026-08-11 | 2026-09-14 | Not Started | 34 | No | 92 | Green |  |  |  | 0
Cabannas | Buildings | Cabannas | HAP Review - 50% DD inprogress | Osama / Ahmed Ramadan |  | 2026-08-18 | 2026-09-21 | Not Started | 34 | No | 99 | Green |  |  |  | 0
Cabannas | Buildings | Cabannas | 50% Detailed Design - Final PKG | Osama / Ahmed Ramadan |  | 2026-08-25 | 2026-10-05 | Not Started | 41 | No | 113 | Green |  |  |  | 0
Cabannas | Buildings | Cabannas | HAP Review - 50% DD Final | Osama / Ahmed Ramadan |  | 2026-09-08 | 2026-10-19 | Not Started | 41 | No | 127 | Green |  |  |  | 0
Cabannas | Buildings | Cabannas | 100% Detailed Design - Inprogress PKG | Osama / Ahmed Ramadan |  | 2026-09-22 | 2026-11-02 | Not Started | 41 | No | 141 | Green |  |  |  | 0
Cabannas | Buildings | Cabannas | HAP Review - 100% DD Inprogress | Osama / Ahmed Ramadan |  | 2026-09-29 | 2026-11-09 | Not Started | 41 | No | 148 | Green |  |  |  | 0
Cabannas | Buildings | Cabannas | 100% Detailed Design - Final PKG | Osama / Ahmed Ramadan |  | 2026-10-13 | 2026-11-23 | Not Started | 41 | No | 162 | Green |  |  |  | 0
Cabannas | Buildings | Cabannas | HAP Review - 100% DD Final | Osama / Ahmed Ramadan |  | 2026-10-27 | 2026-12-07 | Not Started | 41 | No | 176 | Green |  |  |  | 0
Cabannas | Buildings | Cabannas | Cost Plan - 100% DD | Nour / Ali | Survtec | 2026-11-03 | 2026-12-14 | Not Started | 41 | No | 183 | Green |  |  |  | 0
Cabannas | Buildings | Cabannas | Permits Drawings | Osama / Ahmed Ramadan |  | 2026-11-10 | 2026-12-21 | Not Started | 41 | No | 190 | Green |  |  |  | 0
Cabannas | Buildings | Cabannas | Tender Package | Osama / Ahmed Ramadan |  | 2026-11-10 | 2026-12-21 | Not Started | 41 | No | 190 | Green |  |  |  | 0
Cabannas | Buildings | Cabannas | HAP Review - TD | Osama / Ahmed Ramadan |  | 2026-11-24 | 2027-01-04 | Not Started | 41 | No | 204 | Green |  |  |  | 0
Authorities -Cabannas | Authorities |  |  |  |  | 2027-03-16 | 2027-02-23 |  | -21 |  | 254 | Green |  | Authorities -Cabannas¦Authorities |  | 0
Authorities -Cabannas | Authorities | Authorities -Cabannas | MD Approval 3 | Afifi |  | 2026-10-11 | 2026-10-20 | Not Started | 9 | No | 128 | Green |  |  |  | 0
Authorities -Cabannas | Authorities | Authorities -Cabannas | Civil Defense / Decenial Liability | Afifi |  | 2027-01-05 | 2026-12-15 | Not Started | -21 | No | 184 | Green |  |  |  | 0
Authorities -Cabannas | Authorities | Authorities -Cabannas | Permits Approval | Afifi |  | 2027-02-02 | 2027-01-12 | Not Started | -21 | No | 212 | Green |  |  |  | 0
Authorities -Cabannas | Authorities | Authorities -Cabannas | Mineral License | Afifi |  | 2027-03-16 | 2027-02-23 | Not Started | -21 | No | 254 | Green |  |  |  | 0
Lagoon | Lagoon |  |  |  |  | 2027-05-24 | 2027-05-24 |  | 0 |  | 344 | Green |  | Lagoon¦Lagoon |  | 0
|  | Lagoon | Tender to assign Water wells Cunslutent |  |  |  |  | Not Started |  |  |  | Amber |  | ¦ |  | 0
|  | Lagoon | Concept Verification |  |  |  |  | Not Started |  |  |  | Amber |  | ¦ |  | 0
Lagoon | Lagoon | Lagoon | Tender to assign Cunslutent - Lagoon | Hoda / Roshdy |  | 2026-12-21 | 2026-12-21 | Not Started | 0 | No | 190 | Green |  |  |  | 0
Lagoon | Lagoon | Lagoon | 100% Schematic Design Verification | Hoda / Roshdy |  | 2027-01-18 | 2027-01-18 | Not Started | 0 | No | 218 | Green |  |  |  | 0
Lagoon | Lagoon | Lagoon | HAP Review - 100% SD | Hoda / Roshdy |  | 2027-01-25 | 2027-01-25 | Not Started | 0 | No | 225 | Green |  |  |  | 0
Lagoon | Lagoon | Lagoon | 50% Detailed Design | Hoda / Roshdy |  | 2027-02-22 | 2027-02-22 | Not Started | 0 | No | 253 | Green |  |  |  | 0
Lagoon | Lagoon | Lagoon | HAP Review - 50% DD | Hoda / Roshdy |  | 2027-03-08 | 2027-03-08 | Not Started | 0 | No | 267 | Green |  |  |  | 0
Lagoon | Lagoon | Lagoon | 100% Detailed Design | Hoda / Roshdy |  | 2027-04-05 | 2027-04-05 | Not Started | 0 | No | 295 | Green |  |  |  | 0
Lagoon | Lagoon | Lagoon | HAP Review - 100% DD | Hoda / Roshdy |  | 2027-04-19 | 2027-04-19 | Not Started | 0 | No | 309 | Green |  |  |  | 0
Lagoon | Lagoon | Lagoon | Cost Plan - 100% DD | Nour / Ali | Survtec | 2027-04-26 | 2027-04-26 | Not Started | 0 | No | 316 | Green |  |  |  | 0
Lagoon | Lagoon | Lagoon | Tender Package | Hoda / Roshdy |  | 2027-05-10 | 2027-05-10 | Not Started | 0 | No | 330 | Green |  |  |  | 0
Lagoon | Lagoon | Lagoon | HAP Review - TD | Hoda / Roshdy |  | 2027-05-24 | 2027-05-24 | Not Started | 0 | No | 344 | Green |  |  |  | 0
Hotel | Buildings |  |  |  |  | 2027-02-15 | 2027-04-20 |  | 64 |  | 310 | Green |  | Hotel¦Buildings |  | 0
Hotel | Buildings | Hotel | RFP And Contract Signing | Eyad | Local Consultant | 2026-03-15 | 2026-03-15 | Completed | 0 | - | -91 | Red |  |  |  | 0
Hotel | Buildings | Hotel | Commencement date | Eyad | Local Consultant | 2026-03-15 | 2026-03-15 | Completed | 0 | - | -91 | Red |  |  |  | 0
Hotel | Buildings | Hotel | 50% Schematic Design |  | Ghoneimi | 2026-04-13 | 2026-06-03 | Completed | 51 | - | -11 | Red |  |  |  | 0
Hotel | Buildings | Hotel | Operator Review | Eyad / Osama | HAP | 2026-04-27 | 2026-06-30 | Inprogress | 64 | Yes | 16 | Amber |  |  | 9 | 1 | 9
Hotel | Buildings | Hotel | HAP Review - 50% SD | Eyad / Osama | HAP | 2026-04-27 | 2026-06-17 | Completed | 51 | - | 3 | Amber |  |  |  | 0
Hotel | Buildings | Hotel | Conslidated Comments | Eyad / Osama | HAP | 2026-05-04 | 2026-07-07 | Inprogress | 64 | No | 23 | Green |  |  |  | 0
Hotel | Buildings | Hotel | Cost Plan - 50% SD | Nour / Ali | Survtec | 2026-05-04 | 2026-06-24 | Not Started | 51 | Yes | 10 | Amber |  |  | 10 | 1 | 10
Hotel | Buildings | Hotel | 100% Schematic Design | Eyad / Osama | Ghoneimi | 2026-06-01 | 2026-08-04 | Not Started | 64 | No | 51 | Green |  |  |  | 0
Hotel | Buildings | Hotel | Operator Review | Eyad / Osama | HAP | 2026-06-15 | 2026-08-18 | Not Started | 64 | No | 65 | Green |  |  |  | 0
Hotel | Buildings | Hotel | HAP Review - 100% SD | Eyad / Osama | HAP | 2026-06-15 | 2026-08-18 | Not Started | 64 | No | 65 | Green |  |  |  | 0
Hotel | Buildings | Hotel | Conslidated Comments | Eyad / Osama | HAP | 2026-06-22 | 2026-08-25 | Not Started | 64 | No | 72 | Green |  |  |  | 0
Hotel | Buildings | Hotel | Cost Plan - 100% SD | Nour / Ali | Survtec | 2026-06-29 | 2026-09-01 | Not Started | 64 | No | 79 | Green |  |  |  | 0
Hotel | Buildings | Hotel | Ministerial Decree | Eyad / Osama | HAP | 2026-05-18 | 2026-07-21 | Not Started | 64 | No | 37 | Green |  |  |  | 0
Hotel | Buildings | Hotel | HAP Review - MD | Eyad / Osama | HAP | 2026-06-01 | 2026-08-04 | Not Started | 64 | No | 51 | Green |  |  |  | 0
Hotel | Buildings | Hotel | Mockup Package | Eyad / Osama | HAP | 2026-07-20 | 2026-09-22 | Not Started | 64 | No | 100 | Green |  |  |  | 0
Hotel | Buildings | Hotel | HAP Review - MP | Eyad / Osama | HAP | 2026-08-03 | 2026-10-06 | Not Started | 64 | No | 114 | Green |  |  |  | 0
Hotel | Buildings | Hotel | 50% Detailed Design | Eyad / Osama | Ghoneimi | 2026-09-07 | 2026-11-10 | Not Started | 64 | No | 149 | Green |  |  |  | 0
Hotel | Buildings | Hotel | Operator Review | Eyad / Osama | HAP | 2026-09-21 | 2026-11-24 | Not Started | 64 | No | 163 | Green |  |  |  | 0
Hotel | Buildings | Hotel | HAP Review - 50% DD | Eyad / Osama | HAP | 2026-09-21 | 2026-11-24 | Not Started | 64 | No | 163 | Green |  |  |  | 0
Hotel | Buildings | Hotel | Conslidated Comments | Eyad / Osama | HAP | 2026-09-28 | 2026-12-01 | Not Started | 64 | No | 170 | Green |  |  |  | 0
Hotel | Buildings | Hotel | 100% Detailed Design (Including BOQs) | Eyad / Osama | Ghoneimi | 2026-11-30 | 2027-02-02 | Not Started | 64 | No | 233 | Green |  |  |  | 0
Hotel | Buildings | Hotel | Permits Drawings | Eyad / Osama | HAP | 2026-12-28 | 2027-03-02 | Not Started | 64 | No | 261 | Green |  |  |  | 0
Hotel | Buildings | Hotel | Operator Review | Eyad / Osama | HAP | 2026-12-14 | 2027-02-16 | Not Started | 64 | No | 247 | Green |  |  |  | 0
Hotel | Buildings | Hotel | HAP Review - 100% DD | Eyad / Osama | HAP | 2026-12-14 | 2027-02-16 | Not Started | 64 | No | 247 | Green |  |  |  | 0
Hotel | Buildings | Hotel | Conslidated Comments | Eyad / Osama | HAP | 2026-12-21 | 2027-02-23 | Not Started | 64 | No | 254 | Green |  |  |  | 0
Hotel | Buildings | Hotel | Enabling Package (Skeleton Package) | Eyad / Osama | HAP | 2026-12-21 | 2027-02-23 | Not Started | 64 | No | 254 | Green |  |  |  | 0
Hotel | Buildings | Hotel | HAP Review - EP |  | HAP | 2026-12-21 | 2027-02-23 | Not Started | 64 | No | 254 | Green |  |  |  | 0
Hotel | Buildings | Hotel | Cost Verification |  | HAP | 2026-12-28 | 2027-03-02 | Not Started | 64 | No | 261 | Green |  |  |  | 0
Hotel | Buildings | Hotel | Tender Package |  | Ghoneimi | 2027-02-01 | 2027-04-06 | Not Started | 64 | No | 296 | Green |  |  |  | 0
Hotel | Buildings | Hotel | HAP Review - TD |  | HAP | 2027-02-15 | 2027-04-20 | Not Started | 64 | No | 310 | Green |  |  |  | 0
Masterplan - Hotel | Masterplan |  |  |  |  | 2026-07-27 | 2026-09-29 |  | 64 | No | 107 | Green |  | Masterplan - Hotel¦Masterplan |  | 0
Masterplan - Hotel | Masterplan | Masterplan - Hotel | 100% Detailed Design |  |  | 2026-06-15 | 2026-08-18 | Not Started | 64 | No | 65 | Green |  |  |  | 0
Masterplan - Hotel | Masterplan | Masterplan - Hotel | Ministerial Decree |  |  | 2026-07-13 | 2026-09-15 | Not Started | 64 | No | 93 | Green |  |  |  | 0
Masterplan - Hotel | Masterplan | Masterplan - Hotel | HAP Review - 100% DD |  |  | 2026-07-27 | 2026-09-29 | Not Started | 64 | No | 107 | Green |  |  |  | 0
Landscape - Hotel | Landscape |  |  |  |  | 2026-10-25 | 2027-01-20 |  | 87 | No | 220 | Green |  | Landscape - Hotel¦Landscape |  | 0
Landscape - Hotel | Landscape | Landscape - Hotel | VO With Cracknell | Roshdy | Cracknell | 2026-04-05 | 2026-07-01 | Inprogress | 87 | Yes | 17 | Amber |  |  | 11 | 1 | 11
Landscape - Hotel | Landscape | Landscape - Hotel | Preconcept Design | Roshdy | Cracknell | 2026-04-26 | 2026-07-22 | Not Started | 87 | No | 38 | Green |  |  |  | 0
Landscape - Hotel | Landscape | Landscape - Hotel | HAP Review - PC | Roshdy | HAP | 2026-05-03 | 2026-07-29 | Not Started | 87 | No | 45 | Green |  |  |  | 0
Landscape - Hotel | Landscape | Landscape - Hotel | 100% Concept Design | Roshdy | Cracknell | 2026-05-24 | 2026-08-19 | Not Started | 87 | No | 66 | Green |  |  |  | 0
Landscape - Hotel | Landscape | Landscape - Hotel | HAP Review - 100% CD | Roshdy | HAP | 2026-06-07 | 2026-09-02 | Not Started | 87 | No | 80 | Green |  |  |  | 0
Landscape - Hotel | Landscape | Landscape - Hotel | 50% Schematic Design | Roshdy | Cracknell | 2026-07-05 | 2026-09-30 | Not Started | 87 | No | 108 | Green |  |  |  | 0
Landscape - Hotel | Landscape | Landscape - Hotel | HAP Review - 50% SD | Roshdy | HAP | 2026-07-19 | 2026-10-14 | Not Started | 87 | No | 122 | Green |  |  |  | 0
Landscape - Hotel | Landscape | Landscape - Hotel | 100% Schematic Design | Roshdy | Cracknell | 2026-08-16 | 2026-11-11 | Not Started | 87 | No | 150 | Green |  |  |  | 0
Landscape - Hotel | Landscape | Landscape - Hotel | HAP Review - 100% SD | Roshdy | HAP | 2026-08-30 | 2026-11-25 | Not Started | 87 | No | 164 | Green |  |  |  | 0
Landscape - Hotel | Landscape | Landscape - Hotel | 100% Detailed Design | Roshdy | Cracknell | 2026-10-11 | 2027-01-06 | Not Started | 87 | No | 206 | Green |  |  |  | 0
Landscape - Hotel | Landscape | Landscape - Hotel | HAP Review - 100% DD | Roshdy | HAP | 2026-10-25 | 2027-01-20 | Not Started | 87 | No | 220 | Green |  |  |  | 0
Interior - Hotel | Fit-out |  |  |  |  | 2026-10-05 | 2026-12-08 |  | 64 | No | 177 | Green |  | Interior - Hotel¦Fit-out |  | 0
Interior - Hotel | Fit-out | Interior - Hotel | 100% Concept Design |  | Ghoneimi | 2026-06-29 | 2026-09-01 | Not Started | 64 | No | 79 | Green |  |  |  | 0
Interior - Hotel | Fit-out | Interior - Hotel | 100% Schematic Design |  | Ghoneimi | 2026-08-10 | 2026-10-13 | Not Started | 64 | No | 121 | Green |  |  |  | 0
Interior - Hotel | Fit-out | Interior - Hotel | 100% Detailed Design |  | Ghoneimi | 2026-10-05 | 2026-12-08 | Not Started | 64 | No | 177 | Green |  |  |  | 0
Authorities Issuance - Hotel | Authorities |  |  |  |  | 2027-04-26 | 2027-06-29 |  | 64 | No | 380 | Green |  | Authorities Issuance - Hotel¦Authorities |  | 0
Authorities Issuance - Hotel | Authorities | Authorities Issuance - Hotel | Ministerial decree NUCA | Afifi |  | 2026-11-16 | 2027-01-19 | Not Started | 64 | Yes | 219 | Green |  |  | 12 | 1 | 12
Authorities Issuance - Hotel | Authorities | Authorities Issuance - Hotel | Touristic Licenses | Afifi |  | 2027-02-15 | 2027-04-20 | Not Started | 64 | Yes | 310 | Green |  |  | 13 | 1 | 13
Authorities Issuance - Hotel | Authorities | Authorities Issuance - Hotel | Egyptian Institution for Construction Civil Liability Insurance & Civil Defense | Afifi |  | 2027-03-15 | 2027-05-18 | Not Started | 64 | Yes | 338 | Green |  |  | 14 | 1 | 14
Authorities Issuance - Hotel | Authorities | Authorities Issuance - Hotel | Mineral licenses | Afifi |  | 2027-04-26 | 2027-06-29 | Not Started | 64 | Yes | 380 | Green |  |  | 15 | 1 | 15
Master Plan - Boomerang | Masterplan |  |  |  |  | 2026-04-20 | 2026-12-16 |  | 240 | Yes | 185 | Green |  | Master Plan - Boomerang¦Masterplan | 16 | 1 | 16
Master Plan - Boomerang | Masterplan | Master Plan - Boomerang | Development Brief |  |  | 2025-12-07 | 2025-12-07 | Completed | 0 | No | -189 | Red |  |  |  | 0
Master Plan - Boomerang | Masterplan | Master Plan - Boomerang | Brief Approval |  | Internation Consultant | 2025-12-22 | 2025-12-21 | Completed | -1 | No | -175 | Red |  |  |  | 0
Master Plan - Boomerang | Masterplan | Master Plan - Boomerang | RFP |  | Local Consultant | 2026-01-05 | 2026-01-04 | Completed | -1 | No | -161 | Red |  |  |  | 0
Master Plan - Boomerang | Masterplan | Master Plan - Boomerang | Tender to assign Consultant |  | Local Consultant | 2026-02-02 | 2026-03-24 | Completed | 50 | No | -82 | Red |  |  |  | 0
Master Plan - Boomerang | Masterplan | Master Plan - Boomerang | Kick off |  | HAP | 2026-02-09 | 2026-04-01 | Completed | 51 | No | -74 | Red |  |  |  | 0
Master Plan - Boomerang | Masterplan | Master Plan - Boomerang | Pre-Concept |  | YBA | 2026-02-23 | 2026-04-29 | Completed | 65 | No | -46 | Red |  |  |  | 0
Master Plan - Boomerang | Masterplan | Master Plan - Boomerang | HAP Review |  | HAP | 2026-03-02 | 2026-05-06 | Completed | 65 | No | -39 | Red |  |  |  | 0
Master Plan - Boomerang | Masterplan | Master Plan - Boomerang | 50% Concept |  | YBA | 2026-03-16 | 2026-05-26 | Completed | 71 | No | -19 | Red |  |  |  | 0
Master Plan - Boomerang | Masterplan | Master Plan - Boomerang | HAP Review |  | Local Consultant | 2026-03-23 | 2026-06-24 | Inprogress | 93 | No | 10 | Amber |  |  |  | 0
Master Plan - Boomerang | Masterplan | Master Plan - Boomerang | 100% Conceptt |  | YBA | 2026-04-13 | 2026-08-05 | Not Started | 114 | Yes | 52 | Green |  |  | 17 | 1 | 17
Master Plan - Boomerang | Masterplan | Master Plan - Boomerang | HAP Review |  | Local Consultant | 2026-04-20 | 2026-08-19 | Not Started | 121 | Yes | 66 | Green |  |  | 18 | 1 | 18
Master Plan - Boomerang | Masterplan | Master Plan - Boomerang | 50% Schematic Design |  | YBA | 2026-05-18 | 2026-10-14 | Not Started | 149 | Yes | 122 | Green |  |  | 19 | 1 | 19
Master Plan - Boomerang | Masterplan | Master Plan - Boomerang | HAP Review |  |  | 2026-06-01 | 2026-10-28 | Not Started | 149 | Yes | 136 | Green |  |  | 20 | 1 | 20
Master Plan - Boomerang | Masterplan | Master Plan - Boomerang | Launch Material |  | YBA | 2026-06-29 | 2026-08-19 | Not Started | 51 | Yes | 66 | Green |  |  | 21 | 1 | 21
Master Plan - Boomerang | Masterplan | Master Plan - Boomerang | HAP Review |  |  | 2026-07-13 | 2026-08-19 | Not Started | 37 | Yes | 66 | Green |  |  | 22 | 1 | 22
|  | Master Plan - Boomerang | Ministerial Decree |  | YBA | 2026-07-06 | 2026-12-02 | Not Started | 149 | Yes | 171 | Green |  | ¦ | 23 | 1 | 23
|  | Master Plan - Boomerang | HAP Review |  |  | 2026-07-20 | 2026-12-16 | Not Started | 149 | Yes | 185 | Green |  | ¦ | 24 | 1 | 24
Landscape - Boomerang | Landscape |  |  |  |  | 2026-09-07 | 2026-12-23 |  | 107 | Yes | 192 | Green |  | Landscape - Boomerang¦Landscape | 25 | 1 | 25
Landscape - Boomerang | Landscape | Landscape - Boomerang | Kickoff |  | Internation Consultant | 2026-03-23 | 2026-06-24 | Not Started | 93 | No | 10 | Amber |  |  |  | 0
Landscape - Boomerang | Landscape | Landscape - Boomerang | 50% Concept |  | Cracnell | 2026-04-13 | 2026-07-15 | Not Started | 93 | Yes | 31 | Green |  |  | 26 | 1 | 26
Landscape - Boomerang | Landscape | Landscape - Boomerang | HAP Review |  | Local Consultant | 2026-04-20 | 2026-07-29 | Not Started | 100 | Yes | 45 | Green |  |  | 27 | 1 | 27
Landscape - Boomerang | Landscape | Landscape - Boomerang | 100% Concept Design |  | Cracnell | 2026-05-18 | 2026-08-26 | Not Started | 100 | Yes | 73 | Green |  |  | 28 | 1 | 28
Landscape - Boomerang | Landscape | Landscape - Boomerang | HAP Review |  | HAP | 2026-05-25 | 2026-09-09 | Not Started | 107 | Yes | 87 | Green |  |  | 29 | 1 | 29
Landscape - Boomerang | Landscape | Landscape - Boomerang | 50% Schematic Deisgn |  | Cracnell | 2026-07-20 | 2026-11-04 | Not Started | 107 | Yes | 143 | Green |  |  | 30 | 1 | 30
Landscape - Boomerang | Landscape | Landscape - Boomerang | HAP Review |  | HAP | 2026-08-03 | 2026-11-18 | Not Started | 107 | Yes | 157 | Green |  |  | 31 | 1 | 31
Landscape - Boomerang | Landscape | Landscape - Boomerang | 100% Schematic Design |  | Cracnell | 2026-08-31 | 2026-12-16 | Not Started | 107 | Yes | 185 | Green |  |  | 32 | 1 | 32
Landscape - Boomerang | Landscape | Landscape - Boomerang | HAP REVIEW / Cost Verification |  |  | 2026-09-07 | 2026-12-23 | Not Started | 107 | Yes | 192 | Green |  |  | 33 | 1 | 33
Buildings - Boomerang | Buildings |  |  |  |  | 2026-07-20 | 2026-10-21 |  | 93 | Yes | 129 | Green |  | Buildings - Boomerang¦Buildings | 34 | 1 | 34
Buildings - Boomerang | Buildings | Buildings - Boomerang | Kick off |  | HAP | 2026-02-09 | 2026-04-01 | Completed | 51 | No | -74 | Red |  |  |  | 0
Buildings - Boomerang | Buildings | Buildings - Boomerang | Pre-Concept |  | YBA | 2026-03-02 | 2026-06-24 | Inprogress | 114 | No | 10 | Amber |  |  |  | 0
Buildings - Boomerang | Buildings | Buildings - Boomerang | HAP Review |  | Local Consultant | 2026-03-09 | 2026-07-01 | Not Started | 114 | Yes | 17 | Amber |  |  | 35 | 1 | 35
Buildings - Boomerang | Buildings | Buildings - Boomerang | 50% Concept |  | YBA | 2026-03-23 | 2026-07-15 | Not Started | 114 | Yes | 31 | Green |  |  | 36 | 1 | 36
Buildings - Boomerang | Buildings | Buildings - Boomerang | HAP Review |  | Local Consultant | 2026-04-06 | 2026-07-22 | Not Started | 107 | Yes | 38 | Green |  |  | 37 | 1 | 37
Buildings - Boomerang | Buildings | Buildings - Boomerang | 100% Concept |  | YBA | 2026-05-04 | 2026-08-05 | Not Started | 93 | Yes | 52 | Green |  |  | 38 | 1 | 38
Buildings - Boomerang | Buildings | Buildings - Boomerang | HAP Review |  | Local Consultant | 2026-05-11 | 2026-08-12 | Not Started | 93 | Yes | 59 | Green |  |  | 39 | 1 | 39
Buildings - Boomerang | Buildings | Buildings - Boomerang | Launch Materials |  | YBA | 2026-06-08 | 2026-08-12 | Not Started | 65 | Yes | 59 | Green |  |  | 40 | 1 | 40
Buildings - Boomerang | Buildings | Buildings - Boomerang | HAP Review |  |  | 2026-06-22 | 2026-08-12 | Not Started | 51 | Yes | 59 | Green |  |  | 41 | 1 | 41
Buildings - Boomerang | Buildings | Buildings - Boomerang | 50% Schemtic Design (Arch) |  | YBA | 2026-06-01 | 2026-09-02 | Not Started | 93 | Yes | 80 | Green |  |  | 42 | 1 | 42
Buildings - Boomerang | Buildings | Buildings - Boomerang | HAP Review |  |  | 2026-06-15 | 2026-09-16 | Not Started | 93 | Yes | 94 | Green |  |  | 43 | 1 | 43
Buildings - Boomerang | Buildings | Buildings - Boomerang | 50% Schemtic Design (STR & MEP) |  | YBA | 2026-07-06 | 2026-10-07 | Not Started | 93 | Yes | 115 | Green |  |  | 44 | 1 | 44
Buildings - Boomerang | Buildings | Buildings - Boomerang | HAP Review |  |  | 2026-07-20 | 2026-10-21 | Not Started | 93 | Yes | 129 | Green |  |  | 45 | 1 | 45
Buildings - Boomerang | Fit-out |  |  |  |  | 2026-08-17 | 2026-11-25 |  | 100 | Yes | 164 | Green |  | Buildings - Boomerang¦Fit-out | 46 | 1 | 46
Buildings - Boomerang | Fit-out | Interior - Boomerang | RFP |  |  | 2026-04-26 | 2026-06-18 | Inprogress | 53 | No | 4 | Amber |  |  |  | 0
Buildings - Boomerang | Fit-out | Interior - Boomerang | Signle Source to KH Studio |  |  | 2026-05-03 | 2026-06-25 | Not Started
Buildings - Boomerang | Fit-out | Interior - Boomerang | Kick off |  |  | 2026-05-10 | 2026-07-02 | Not Started
Buildings - Boomerang | Fit-out | Interior - Boomerang | 50% Concept |  | KH Studio | 2026-05-24 | 2026-08-05 | Not Started
Buildings - Boomerang | Fit-out | Interior - Boomerang | HAP Review |  |  | 2026-05-31 | 2026-08-12 | Not Started
Buildings - Boomerang | Fit-out | Interior - Boomerang | 100% Concept |  | KH Studio | 2026-06-14 | 2026-09-02 | Not Started
Buildings - Boomerang | Fit-out | Interior - Boomerang | HAP Review |  |  | 2026-06-28 | 2026-09-09 | Not Started
Buildings - Boomerang | Fit-out | Interior - Boomerang | 100% Schematic |  | KH Studio | 2026-07-12 | 2026-11-11 | Not Started
Buildings - Boomerang | Fit-out | Interior - Boomerang | HAP Review |  |  | 2026-07-26 | 2026-11-25 | Not Started
Formulas:
Overdue? = IF([Parent]="","",IF([Actual / Forecast Finish]="","",IF([Status]="completed","-",IF([Actual / Forecast Finish]>TODAY(),"No","Yes"))))
Overdue? = IF([Actual / Forecast Finish]="","",IF([Actual / Forecast Finish]>TODAY(),"No","Yes"))

## DRJ
DRJ | [5 empty] | 2027-09-22 | 2027-10-12 | 20
Phase | Trade | Parent | Task | Task Owner | Consultant | Baseline Finish | Actual / Forecast Finish | Status | Slippage (days) | Overdue? | Days to Finish/Delay | RAG | Notes | CurKey | OvdRank | ShowFlag | DesignRank
DRJ | Authorities | [5 empty] | 2026-09-13 |  |  |  | 91 | Green |  | #REF! |  | 0
DRJ | Authorities | Ministerial Decrees | Phase-01 (1A, 2B, 2A, 2E & 2D right) | Afifi |  |  | 2026-03-25 | Completed |  | - | 0 | Red |  |  |  | 0
DRJ | Authorities | Ministerial Decrees | Phase-02 (Villas + Towers) | Afifi |  |  | 2026-09-13 | Inprogress |  | No | 91 | Green |  |  |  | 0
DRJ | Authorities | Ministerial Decrees | Phase-03 (Commercial) | Afifi |  |  |  | Completed |  |  | 0 | Amber |  |  |  | 0
DRJ | Landscape |  |  |  |  | 2025-12-10 | 2026-06-26 |  | 198 |  | 12 | Amber |  | DRJ¦Landscape |  | 0
DRJ | Landscape | General Landscape ( Concept To Schematic) | 50% Concept Design Review (International Consultant) | Hoda / Roshdy | Cracnell | 2025-06-29 | 2025-06-29 | Completed | 0 | - | 0 | Red |  |  |  | 0
DRJ | Landscape | General Landscape ( Concept To Schematic) | HAP Review | Hoda / Roshdy | Cracnell | 2025-07-13 | 2025-07-13 | Completed | 0 | - | 0 | Red |  |  |  | 0
DRJ | Landscape | General Landscape ( Concept To Schematic) | 100% Concept Design Review (International Consultant) | Hoda / Roshdy | Cracnell | 2025-08-10 | 2025-08-10 | Completed | 0 | - | 0 | Red |  |  |  | 0
DRJ | Landscape | General Landscape ( Concept To Schematic) | HAP Review | Hoda / Roshdy | Cracnell | 2025-08-24 | 2025-08-24 | Completed | 0 | - | 0 | Red |  |  |  | 0
DRJ | Landscape | General Landscape ( Concept To Schematic) | 50% Schematic Design For Central Park (International Consultant) | Hoda / Roshdy | Cracnell |  | 2026-02-13 | Completed |  | - | 0 | Red |  |  |  | 0
DRJ | Landscape | General Landscape ( Concept To Schematic) | HAP Review For Centeral Park | Hoda / Roshdy | Cracnell |  | 2026-03-09 | Completed |  | - | 0 | Red |  |  |  | 0
DRJ | Landscape | General Landscape ( Concept To Schematic) | 50% Schematic Design For Remaining Project (International Consultant) | Hoda / Roshdy | Cracnell | 2025-10-15 | 2026-02-13 | Completed | 121 | - | 0 | Red |  |  |  | 0
DRJ | Landscape | General Landscape ( Concept To Schematic) | HAP Review For Remaining Project | Hoda / Roshdy | Cracnell | 2025-11-05 | 2026-03-09 | Completed | 124 | - | 0 | Red |  |  |  | 0
DRJ | Landscape | General Landscape ( Concept To Schematic) | 100% Schematic Design For Central Park (International Consultant) | Hoda / Roshdy | Cracnell |  | 2026-04-10 | Completed |  | - | 0 | Red |  |  |  | 0
DRJ | Landscape | General Landscape ( Concept To Schematic) | HAP Review For Central Park | Hoda / Roshdy | Cracnell |  | 2026-06-26 | Inprogress |  | Yes | 12 | Amber |  |  | 1 | 1 | 1
DRJ | Landscape | General Landscape ( Concept To Schematic) | 100% Schematic Design for Remaining Project (International Consultant) | Hoda / Roshdy | Cracnell | 2025-11-26 | 2026-04-10 | Completed | 135 | - | 0 | Red |  |  |  | 0
DRJ | Landscape | General Landscape ( Concept To Schematic) | HAP Review For Remaining Project | Hoda / Roshdy | Cracnell | 2025-12-10 | 2026-06-26 | Inprogress | 198 | Yes | 12 | Amber |  |  | 2 | 1 | 2
DRJ | Landscape |  |  |  |  | 2026-05-06 | 2026-05-11 |  | 5 |  | -34 | Red |  |  |  | 0
DRJ | Landscape | Landscape Park Central (1B, 2C) & Teracces (1A) & Great Lawn (2A, 2B) & (2E, 2D) | Concept Validation | Hoda / Roshdy | ECG | 2026-02-04 | 2026-02-04 | Completed | 0 | - | 0 | Red |  |  |  | 0
DRJ | Landscape | Landscape Park Central (1B, 2C) & Teracces (1A) & Great Lawn (2A, 2B) & (2E, 2D) | HAP Review - CV | Hoda / Roshdy | ECG | 2026-02-11 | 2026-02-11 | Completed | 0 | - | 0 | Red |  |  |  | 0
DRJ | Landscape | Landscape Park Central (1B, 2C) & Teracces (1A) & Great Lawn (2A, 2B) & (2E, 2D) | 50% Schematic Validation For Central Park | Hoda / Roshdy | ECG | 2026-05-03 | 2026-05-06 | Completed | 3 | - | 0 | Red |  |  |  | 0
DRJ | Landscape | Landscape Park Central (1B, 2C) & Teracces (1A) & Great Lawn (2A, 2B) & (2E, 2D) | HAP Review For Central Park | Hoda / Roshdy | ECG | 2026-05-06 | 2026-05-11 | Completed | 5 | - | 0 | Red |  |  |  | 0
DRJ | Landscape | Landscape Park Central (1B, 2C) & Teracces (1A) & Great Lawn (2A, 2B) & (2E, 2D) | 50% Schematic Validation For Remaining Project | Hoda / Roshdy | ECG | 2026-05-03 | 2026-05-06 | Completed | 3 | - | 0 | Red |  |  |  | 0
DRJ | Landscape | Landscape Park Central (1B, 2C) & Teracces (1A) & Great Lawn (2A, 2B) & (2E, 2D) | HAP Review For Remaining Project | Hoda / Roshdy | ECG | 2026-05-06 | 2026-05-11 | Completed | 5 | - | 0 | Red |  |  |  | 0
DRJ | Landscape | Landscape Park Central (1B, 2C) & Teracces (1A) & Great Lawn (2A, 2B) & (2E, 2D) | 100% Schematic Validation For Central Park | Hoda / Roshdy | ECG | 2026-05-03 | 2026-05-06 | Completed | 3 | - | 0 | Red |  |  |  | 0
DRJ | Landscape | Landscape Park Central (1B, 2C) & Teracces (1A) & Great Lawn (2A, 2B) & (2E, 2D) | HAP Review For Central Park | Hoda / Roshdy | ECG | 2026-05-06 | 2026-05-11 | Completed | 5 | - | 0 | Red |  |  |  | 0
DRJ | Landscape | Landscape Park Central (1B, 2C) & Teracces (1A) & Great Lawn (2A, 2B) & (2E, 2D) | 100% Schematic Validation For Remaining Project | Hoda / Roshdy | ECG | 2026-05-03 | 2026-05-06 | Completed | 3 | - | 0 | Red |  |  |  | 0
DRJ | Landscape | Landscape Park Central (1B, 2C) & Teracces (1A) & Great Lawn (2A, 2B) & (2E, 2D) | HAP Review For Remaining Project | Hoda / Roshdy | ECG | 2026-05-06 | 2026-05-11 | Completed | 5 | - | 0 | Red |  |  |  | 0
Centeral Park | Landscape |  |  |  |  | 2026-07-07 | 2026-07-22 |  | 15 |  | 38 | Green |  | Centeral Park¦Landscape |  | 0
Centeral Park | Landscape | Landscape Centeral Park Including Courts | 100% Detailed Design | Hoda / Roshdy | ECG | 2026-06-14 | 2026-06-29 | Inprogress | 15 | Yes | 15 | Amber |  |  | 3 | 1 | 3
Centeral Park | Landscape | Landscape Centeral Park Including Courts | HAP Review - 100% DD | Hoda / Roshdy |  | 2026-06-16 | 2026-07-01 | Not Started | 15 | Yes | 17 | Amber |  |  | 4 | 1 | 4
Centeral Park | Landscape | Landscape Centeral Park Including Courts | Cost Plan - 100% DD | Nour / Noha |  | 2026-06-28 | 2026-07-13 | Not Started | 15 | No | 29 | Green |  |  |  | 0
Centeral Park | Landscape | Landscape Centeral Park Including Courts | Tender Package For Central Park | Hoda / Roshdy | ECG | 2026-06-30 | 2026-07-15 | Not Started | 15 | No | 31 | Green |  |  |  | 0
RW - Centeral Park | Landscape | Landscape Centeral Park Including Courts | HAP Review - TD | Hoda / Roshdy |  | 2026-07-07 | 2026-07-22 | Not Started | 15 | No | 38 | Green |  | RW - Centeral Park¦Landscape |  | 0
RW - Centeral Park | Landscape |  |  |  |  | 2026-09-23 | 2026-10-25 |  | 32 |  | 133 | Green |  |  |  | 0
RW - Centeral Park | Landscape | Retaining Walls | 100% Schematic Verification | Hoda / Roshdy | ECG | 2026-05-20 | 2026-05-06 | Completed | -14 | - | 0 | Red |  |  |  | 0
RW - Centeral Park | Landscape | Retaining Walls | HAP Review - 100% SD | Hoda / Roshdy |  | 2026-05-27 | 2026-05-11 | Completed | -16 | - | 0 | Red |  |  |  | 0
RW - Centeral Park | Landscape | Retaining Walls | 50% Detailed Design | Hoda / Roshdy | ECG | 2026-06-24 | 2026-07-26 | Not Started | 32 | No | 42 | Green |  |  |  | 0
RW - Centeral Park | Landscape | Retaining Walls | HAP Review - 50% DD | Hoda / Roshdy |  | 2026-07-08 | 2026-08-09 | Not Started | 32 | No | 56 | Green |  |  |  | 0
RW - Centeral Park | Landscape | Retaining Walls | 100% Detailed Design | Hoda / Roshdy | ECG | 2026-08-05 | 2026-09-06 | Not Started | 32 | No | 84 | Green |  |  |  | 0
RW - Centeral Park | Landscape | Retaining Walls | HAP Review - 100% DD | Hoda / Roshdy |  | 2026-08-19 | 2026-09-20 | Not Started | 32 | No | 98 | Green |  |  |  | 0
RW - Centeral Park | Landscape | Retaining Walls | Tender Package | Hoda / Roshdy | ECG | 2026-09-09 | 2026-10-11 | Not Started | 32 | No | 119 | Green |  |  |  | 0
RW - Centeral Park | Landscape | Retaining Walls | HAP Review - TD | Hoda / Roshdy |  | 2026-09-23 | 2026-10-25 | Not Started | 32 | No | 133 | Green |  |  |  | 0
CH - Centeral Park | Landscape |  |  |  |  | 2027-02-21 | 2027-03-25 |  | 32 |  | 284 | Green |  | CH - Centeral Park¦Landscape |  | 0
CH - Centeral Park | Landscape | Club House Park Central | Schematic Verification | Hoda / Roshdy | ECG | 2026-10-18 | 2026-11-19 | Not Started | 32 | No | 158 | Green |  |  |  | 0
CH - Centeral Park | Landscape | Club House Park Central | HAP Review - 100% SD | Hoda / Roshdy |  | 2026-10-25 | 2026-11-26 | Not Started | 32 | No | 165 | Green |  |  |  | 0
CH - Centeral Park | Landscape | Club House Park Central | 50% Detailed Design | Hoda / Roshdy | ECG | 2026-11-22 | 2026-12-24 | Not Started | 32 | No | 193 | Green |  |  |  | 0
CH - Centeral Park | Landscape | Club House Park Central | HAP Review - 50% DD | Hoda / Roshdy |  | 2026-12-06 | 2027-01-07 | Not Started | 32 | No | 207 | Green |  |  |  | 0
CH - Centeral Park | Landscape | Club House Park Central | 100% Detailed Design | Hoda / Roshdy | ECG | 2027-01-03 | 2027-02-04 | Not Started | 32 | No | 235 | Green |  |  |  | 0
CH - Centeral Park | Landscape | Club House Park Central | HAP Review - 100% DD | Hoda / Roshdy |  | 2027-01-17 | 2027-02-18 | Not Started | 32 | No | 249 | Green |  |  |  | 0
CH - Centeral Park | Landscape | Club House Park Central | Cost Plan - 100% DD | Hoda / Roshdy |  | 2027-01-17 | 2027-02-18 | Not Started | 32 | No | 249 | Green |  |  |  | 0
CH - Centeral Park | Landscape | Club House Park Central | Tender Package | Hoda / Roshdy | ECG | 2027-02-07 | 2027-03-11 | Not Started | 32 | No | 270 | Green |  |  |  | 0
CH - Centeral Park | Landscape | Club House Park Central | HAP Review - TD | Hoda / Roshdy |  | 2027-02-21 | 2027-03-25 | Not Started | 32 | No | 284 | Green |  |  |  | 0
Kiosks - Centeral Park | Landscape |  |  |  |  | 2026-10-20 | 2026-11-04 |  | 15 |  | 143 | Green |  | Kiosks - Centeral Park¦Landscape |  | 0
Kiosks - Centeral Park | Landscape | F&B Kiosks | Schematic Verification | Hoda / Roshdy | ECG | 2026-06-30 | 2026-07-15 | Not Started | 15 | No | 31 | Green |  |  |  | 0
Kiosks - Centeral Park | Landscape | F&B Kiosks | HAP Review - 100% SD | Hoda / Roshdy |  | 2026-07-07 | 2026-07-22 | Not Started | 15 | No | 38 | Green |  |  |  | 0
Kiosks - Centeral Park | Landscape | F&B Kiosks | 50% Detailed Design | Hoda / Roshdy | ECG | 2026-08-04 | 2026-08-19 | Not Started | 15 | No | 66 | Green |  |  |  | 0
Kiosks - Centeral Park | Landscape | F&B Kiosks | HAP Review - 50% DD | Hoda / Roshdy |  | 2026-08-18 | 2026-09-02 | Not Started | 15 | No | 80 | Green |  |  |  | 0
Kiosks - Centeral Park | Landscape | F&B Kiosks | 100% Detailed Design | Hoda / Roshdy | ECG | 2026-09-01 | 2026-09-16 | Not Started | 15 | No | 94 | Green |  |  |  | 0
Kiosks - Centeral Park | Landscape | F&B Kiosks | HAP Review - 100% DD | Hoda / Roshdy |  | 2026-09-15 | 2026-09-30 | Not Started | 15 | No | 108 | Green |  |  |  | 0
Kiosks - Centeral Park | Landscape | F&B Kiosks | Tender Package | Hoda / Roshdy | ECG | 2026-10-06 | 2026-10-21 | Not Started | 15 | No | 129 | Green |  |  |  | 0
Kiosks - Centeral Park | Landscape | F&B Kiosks | HAP Review - TD | Hoda / Roshdy |  | 2026-10-20 | 2026-11-04 | Not Started | 15 | No | 143 | Green |  |  |  | 0
Ph - 1A | Buildings |  |  |  |  | 2026-04-27 | 2026-09-27 |  | 153 |  | 105 | Green |  | Ph - 1A¦Buildings |  | 0
Ph - 1A | Buildings | Apartment Buildings Terraces ( 3 Prototypes ) PHASE 1-A ( Core&shell Scope ) | 100% Concept Design | Ashraf / Qadry | ECG | 2024-11-13 | 2024-11-13 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph - 1A | Buildings | Apartment Buildings Terraces ( 3 Prototypes ) PHASE 1-A ( Core&shell Scope ) | HAP Review - 100% CD | Ashraf / Qadry |  | 2024-12-02 | 2024-12-02 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph - 1A | Buildings | Apartment Buildings Terraces ( 3 Prototypes ) PHASE 1-A ( Core&shell Scope ) | 100% Schematic Design | Ashraf / Qadry | ECG | 2024-12-26 | 2024-12-26 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph - 1A | Buildings | Apartment Buildings Terraces ( 3 Prototypes ) PHASE 1-A ( Core&shell Scope ) | HAP Review - 100% SD | Ashraf / Qadry |  | 2025-01-12 | 2025-01-12 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph - 1A | Buildings | Apartment Buildings Terraces ( 3 Prototypes ) PHASE 1-A ( Core&shell Scope ) | Cost Plan - 100% SD | Nour / Noha |  | 2025-01-26 | 2025-01-26 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph - 1A | Buildings | Apartment Buildings Terraces ( 3 Prototypes ) PHASE 1-A ( Core&shell Scope ) | 50% Detailed Design | Ashraf / Qadry | ECG | 2025-03-03 | 2025-03-03 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph - 1A | Buildings | Apartment Buildings Terraces ( 3 Prototypes ) PHASE 1-A ( Core&shell Scope ) | HAP Review - 50% DD | Ashraf / Qadry |  | 2025-05-27 | 2025-05-27 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph - 1A | Buildings | Apartment Buildings Terraces ( 3 Prototypes ) PHASE 1-A ( Core&shell Scope ) | 100% Detailed Design | Ashraf / Qadry | ECG | 2025-08-18 | 2025-08-18 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph - 1A | Buildings | Apartment Buildings Terraces ( 3 Prototypes ) PHASE 1-A ( Core&shell Scope ) | HAP Review - 100% DD | Ashraf / Qadry |  | 2025-09-01 | 2025-09-01 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph - 1A | Buildings | Apartment Buildings Terraces ( 3 Prototypes ) PHASE 1-A ( Core&shell Scope ) | Cost Plan - 100% DD | Nour / Noha |  | 2025-09-01 | 2025-09-01 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph - 1A | Buildings | Apartment Buildings Terraces ( 3 Prototypes ) PHASE 1-A ( Core&shell Scope ) | Permit Drawings | Ashraf / Qadry | ECG | 2025-09-30 | 2025-09-30 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph - 1A | Buildings | Apartment Buildings Terraces ( 3 Prototypes ) PHASE 1-A ( Core&shell Scope ) | Tender Package | Ashraf / Qadry | ECG | 2025-10-02 | 2026-03-18 | Completed | 167 | - | 0 | Red |  |  |  | 0
Ph - 1A | Buildings | Apartment Buildings Terraces ( 3 Prototypes ) PHASE 1-A ( Core&shell Scope ) | HAP Review - TD | Ashraf / Qadry |  | 2025-10-16 | 2026-04-05 | Completed | 171 | - | 0 | Red |  |  |  | 0
Ph - 1A | Authorities |  |  |  |  | 2026-04-27 | 2026-09-27 |  | 153 |  | 105 | Green |  | Ph - 1A¦Authorities |  | 0
Ph - 1A | Authorities | Authorities Issuance 1-A | Ministerial decree-Midar | Afifi |  | 2025-08-18 | 2025-08-18 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph - 1A | Authorities | Authorities Issuance 1-A | Ministerial decree-NUCA | Afifi |  | 2025-12-08 | 2026-03-25 | Completed | 107 | - | 0 | Red |  |  |  | 0
Ph - 1A | Authorities | Authorities Issuance 1-A | Egyptian Institution for Construction Civil Liability Insurance & Civil Defense | Afifi |  | 2026-01-19 | 2026-07-05 | Inprogress | 167 | No | 21 | Amber |  |  |  | 0
Ph - 1A | Authorities | Authorities Issuance 1-A | Construction licenses-Permits | Afifi |  | 2026-03-02 | 2026-08-02 | Not Started | 153 | No | 49 | Green |  |  |  | 0
Ph - 1A | Authorities | Authorities Issuance 1-A | Mineral licenses-Excavation | Afifi |  | 2026-04-27 | 2026-09-27 | Not Started | 153 | No | 105 | Green |  |  |  | 0
Ph - 1A | Plot Fences |  |  |  |  | 2026-06-28 | 2026-07-29 |  | 31 |  | 45 | Green |  | Ph - 1A¦Plot Fences |  | 0
Ph - 1A | Plot Fences | Plot Fences 1-A | 100% Detailed Design | Ashraf / Qadry | ECG | 2026-05-17 | 2026-06-17 | Completed | 31 | - | 0 | Amber |  |  |  | 0
Ph - 1A | Plot Fences | Plot Fences 1-A | HAP Review - 100% DD | Ashraf / Qadry |  | 2026-05-31 | 2026-07-01 | Inprogress | 31 | Yes | 17 | Amber |  |  | 5 | 1 | 5
Ph - 1A | Plot Fences | Plot Fences 1-A | Tender Package | Ashraf / Qadry | ECG | 2026-06-14 | 2026-07-15 | Not Started | 31 | No | 31 | Green |  |  |  | 0
Ph - 1A | Plot Fences | Plot Fences 1-A | HAP Review - TD | Ashraf / Qadry |  | 2026-06-28 | 2026-07-29 | Not Started | 31 | No | 45 | Green |  |  |  | 0
Ph - 1A | Fit-out |  |  |  |  | 2026-07-12 | 2026-11-26 |  | 137 |  | 165 | Green |  | Ph - 1A¦Fit-out |  | 0
Ph - 1A | Fit-out | Fit-Out ( 3 Prototypes ) PHASE 1-A | Mood Board has been considered from SLR Concept | Ashraf / Qadry |  | 2025-11-12 | 2025-12-18 | Completed | 36 | - | 0 | Red |  |  |  | 0
Ph - 1A | Fit-out | Fit-Out ( 3 Prototypes ) PHASE 1-A | 100% Schematic Design | Ashraf / Qadry | ECG | 2025-12-24 | 2026-01-29 | Completed | 36 | - | 0 | Red |  |  |  | 0
Ph - 1A | Fit-out | Fit-Out ( 3 Prototypes ) PHASE 1-A | HAP Review - 100% SD | Ashraf / Qadry |  | 2026-01-07 | 2026-02-08 | Completed | 32 | - | 0 | Red |  |  |  | 0
Ph - 1A | Fit-out | Fit-Out ( 3 Prototypes ) PHASE 1-A | 50% Detailed Design | Ashraf / Qadry | ECG | 2026-02-04 | 2026-05-04 | Completed | 89 | - | 0 | Red |  |  |  | 0
Ph - 1A | Fit-out | Fit-Out ( 3 Prototypes ) PHASE 1-A | HAP Review - 50% DD | Ashraf / Qadry |  | 2026-02-18 | 2026-05-25 | Completed | 96 | - | 0 | Red |  |  |  | 0
Ph - 1A | Fit-out | Fit-Out ( 3 Prototypes ) PHASE 1-A | 100% Detailed Design | Ashraf / Qadry | ECG |  | 2026-06-29 | Inprogress |  | Yes | 15 | Amber |  |  | 6 | 1 | 6
Ph - 1A | Fit-out | Fit-Out ( 3 Prototypes ) PHASE 1-A | HAP Review - 100% DD | Ashraf / Qadry |  |  | 2026-07-06 | Not Started |  | No | 22 | Green |  |  |  | 0
Ph - 1A | Fit-out | Fit-Out ( 3 Prototypes ) PHASE 1-A | Cost Plan - 100% DD | Nour / Noha |  | 2026-02-18 | 2026-07-13 | Not Started | 145 | No | 29 | Green |  |  |  | 0
Ph - 1A | Fit-out | Fit-Out ( 3 Prototypes ) PHASE 1-A | Tender Package | Ashraf / Qadry | ECG | 2026-03-08 | 2026-07-23 | Not Started | 137 | No | 39 | Green |  |  |  | 0
Ph - 1A | Fit-out | Fit-Out ( 3 Prototypes ) PHASE 1-A | HAP Review - TD | Ashraf / Qadry |  | 2026-03-22 | 2026-08-06 | Not Started | 137 | No | 53 | Green |  |  |  | 0
|  | Fit-Out ( 3 Prototypes ) PHASE 1-A | BOQ Preperation |  | ECG | 2026-04-19 | 2026-09-03 | Not Started | 137 | No | 81 | Green |  | ¦ |  | 0
|  | Fit-Out ( 3 Prototypes ) PHASE 1-A | Tender Process |  |  | 2026-07-12 | 2026-11-26 | Not Started | 137 | No | 165 | Green |  | ¦ |  | 0
Ph - 1A | Masterplan |  |  |  |  | 2025-11-03 | 2026-04-06 |  | 154 |  | -69 | Red |  | Ph - 1A¦Masterplan |  | 0
Ph - 1A | Masterplan | Master Planning (PHASE - 1A) Apartment Buildings Terraces | 50% Concept Design | Ashraf / Qadry | ECG | 2024-11-10 | 2024-11-10 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph - 1A | Masterplan | Master Planning (PHASE - 1A) Apartment Buildings Terraces | HAP Review - 50% CD | Ashraf / Qadry |  | 2024-12-01 | 2024-12-01 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph - 1A | Masterplan | Master Planning (PHASE - 1A) Apartment Buildings Terraces | 100% Concept Design Review | Ashraf / Qadry | ECG | 2024-12-15 | 2024-12-15 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph - 1A | Masterplan | Master Planning (PHASE - 1A) Apartment Buildings Terraces | HAP Review - 100% CD | Ashraf / Qadry |  | 2024-12-29 | 2024-12-29 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph - 1A | Masterplan | Master Planning (PHASE - 1A) Apartment Buildings Terraces | 100% Schematic Design & BODR | Ashraf / Qadry | ECG | 2025-01-12 | 2025-01-12 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph - 1A | Masterplan | Master Planning (PHASE - 1A) Apartment Buildings Terraces | HAP Review - 100% SD | Ashraf / Qadry |  | 2025-01-26 | 2025-01-26 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph - 1A | Masterplan | Master Planning (PHASE - 1A) Apartment Buildings Terraces | 50% Detailed Design | Ashraf / Qadry | ECG | 2025-03-16 | 2025-03-16 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph - 1A | Masterplan | Master Planning (PHASE - 1A) Apartment Buildings Terraces | HAP Review - 50% DD | Ashraf / Qadry |  | 2025-03-30 | 2025-03-30 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph - 1A | Masterplan | Master Planning (PHASE - 1A) Apartment Buildings Terraces | 100% Detailed Design | Ashraf / Qadry | ECG | 2025-05-25 | 2025-05-25 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph - 1A | Masterplan | Master Planning (PHASE - 1A) Apartment Buildings Terraces | HAP Review - 100% DD | Ashraf / Qadry |  | 2025-06-08 | 2025-06-08 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph - 1A | Masterplan | Master Planning (PHASE - 1A) Apartment Buildings Terraces | Ministerial Decree Package | Ashraf / Qadry | ECG | 2025-06-22 | 2025-06-22 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph - 1A | Masterplan | Master Planning (PHASE - 1A) Apartment Buildings Terraces | Tender Package | Ashraf / Qadry | ECG | 2025-10-06 | 2026-03-18 | Completed | 163 | - | 0 | Red |  |  |  | 0
Ph - 1A | Masterplan | Master Planning (PHASE - 1A) Apartment Buildings Terraces | HAP Review - TD | Ashraf / Qadry |  | 2025-10-20 | 2026-04-05 | Completed | 167 | - | 0 | Red |  |  |  | 0
Ph - 1A | Masterplan | Master Planning (PHASE - 1A) Apartment Buildings Terraces | IFT Submission | Ashraf / Qadry |  | 2025-11-03 | 2026-04-06 | Completed | 154 | - | 0 | Red |  |  |  | 0
Ph - 1A | Infrastructure |  |  |  |  | 2026-02-16 | 2026-07-20 |  | 154 |  | 36 | Green |  | Ph - 1A¦Infrastructure |  | 0
Ph - 1A | Infrastructure | Infrastructure & roads (PHASE - 1A) Apartment Buildings Terraces | 50% Concept Design | Ashraf / Qadry | ECG | 2024-11-10 | 2024-11-10 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph - 1A | Infrastructure | Infrastructure & roads (PHASE - 1A) Apartment Buildings Terraces | HAP Review - 50% CD | Ashraf / Qadry |  | 2024-12-01 | 2024-12-01 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph - 1A | Infrastructure | Infrastructure & roads (PHASE - 1A) Apartment Buildings Terraces | 100% Concept Design Review | Ashraf / Qadry | ECG | 2024-12-15 | 2024-12-15 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph - 1A | Infrastructure | Infrastructure & roads (PHASE - 1A) Apartment Buildings Terraces | HAP Review - 100% CD | Ashraf / Qadry |  | 2024-12-29 | 2024-12-29 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph - 1A | Infrastructure | Infrastructure & roads (PHASE - 1A) Apartment Buildings Terraces | 100% Schematic Design & BODR | Ashraf / Qadry | ECG | 2025-01-12 | 2025-01-12 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph - 1A | Infrastructure | Infrastructure & roads (PHASE - 1A) Apartment Buildings Terraces | HAP Review - 100% SD | Ashraf / Qadry |  | 2025-01-26 | 2025-01-26 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph - 1A | Infrastructure | Infrastructure & roads (PHASE - 1A) Apartment Buildings Terraces | 50% Detailed Design | Ashraf / Qadry | ECG | 2025-03-16 | 2025-03-16 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph - 1A | Infrastructure | Infrastructure & roads (PHASE - 1A) Apartment Buildings Terraces | HAP Review - 50% DD | Ashraf / Qadry |  | 2025-06-08 | 2025-06-08 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph - 1A | Infrastructure | Infrastructure & roads (PHASE - 1A) Apartment Buildings Terraces | 100% Detailed Design | Ashraf / Qadry | ECG | 2025-08-31 | 2025-08-31 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph - 1A | Infrastructure | Infrastructure & roads (PHASE - 1A) Apartment Buildings Terraces | HAP Review - 100% DD | Ashraf / Qadry |  | 2025-09-14 | 2025-09-14 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph - 1A | Infrastructure | Infrastructure & roads (PHASE - 1A) Apartment Buildings Terraces | Tender Package | Ashraf / Qadry | ECG | 2025-10-06 | 2026-04-09 | Completed | 185 | - | 0 | Red |  |  |  | 0
Ph - 1A | Infrastructure | Infrastructure & roads (PHASE - 1A) Apartment Buildings Terraces | HAP Review - TD | Ashraf / Qadry |  | 2025-10-20 | 2026-05-05 | Completed | 197 | - | 0 | Red |  |  |  | 0
Ph - 1A | Infrastructure | Infrastructure & roads (PHASE - 1A) Apartment Buildings Terraces | MIDAR Approval - 1A | Ashraf / Qadry / Afifi |  | 2026-02-02 | 2026-07-06 | Inprogress | 154 | No | 22 | Green |  |  |  | 0
Ph - 1A | Infrastructure | Infrastructure & roads (PHASE - 1A) Apartment Buildings Terraces | IFT Submission After Midar Comments | Ashraf / Qadry |  | 2026-02-16 | 2026-07-20 | Not Started | 154 | No | 36 | Green |  |  |  | 0
Ph - 1A Ancillary Buildings | Authorities |  |  |  |  | 2026-04-27 | 2026-12-06 |  | 223 |  | 175 | Green |  | Ph - 1A Ancillary Buildings¦Authorities |  | 0
Ph - 1A | Authorities | Authorities Issuance (Ancillary Buildings) | Ministerial decree-NUCA | Afifi |  | 2025-12-08 | 2026-09-13 | Inprogress | 279 | No | 91 | Green |  |  |  | 0
Ph - 1A | Authorities | Authorities Issuance (Ancillary Buildings) | Construction licenses- Ancillary Buildings Permits | Afifi |  | 2026-04-27 | 2026-12-06 | Not Started | 223 | No | 175 | Green |  |  |  | 0
Ph - 1A | Landscape |  |  |  |  | 2027-09-22 | 2026-10-06 |  | -351 |  | 114 | Green |  | Ph - 1A¦Landscape |  | 0
Ph - 1A | Landscape | Landscape Phase 1-A (Teracces) | 50% Detailed Design | Hoda / Roshdy | ECG | 2026-06-03 | 2026-06-23 | Inprogress | 20 | Yes | 9 | Amber |  |  | 7 | 1 | 7
Ph - 1A | Landscape | Landscape Phase 1-A (Teracces) | HAP Review - 50% DD | Hoda / Roshdy |  | 2026-06-17 | 2026-07-07 | Not Started | 20 | No | 23 | Green |  |  |  | 0
Ph - 1A | Landscape | Landscape Phase 1-A (Teracces) | 100% Detailed Design | Hoda / Roshdy | ECG | 2026-07-15 | 2026-08-04 | Not Started | 20 | No | 51 | Green |  |  |  | 0
Ph - 1A | Landscape | Landscape Phase 1-A (Teracces) | HAP Review - 100% DD | Hoda / Roshdy |  | 2026-07-29 | 2026-08-18 | Not Started | 20 | No | 65 | Green |  |  |  | 0
Ph - 1A | Landscape | Landscape Phase 1-A (Teracces) | Cost Plan - 100% DD | Nour / Noha |  | 2026-07-29 | 2026-08-18 | Not Started | 20 | No | 65 | Green |  |  |  | 0
Ph - 1A | Landscape | Landscape Phase 1-A (Teracces) | Tender Package - 1A Left | Hoda / Roshdy | ECG | 2026-08-19 | 2026-09-08 | Not Started | 20 | No | 86 | Green |  |  |  | 0
Ph - 1A | Landscape | Landscape Phase 1-A (Teracces) | HAP Review - TD 1A Left | Hoda / Roshdy |  | 2026-09-02 | 2026-09-22 | Not Started | 20 | No | 100 | Green |  |  |  | 0
Ph - 1A | Landscape | Landscape Phase 1-A (Teracces) | Tender Package - 1A Right | Hoda / Roshdy | ECG | 2026-09-09 | 2026-09-29 | Not Started | 20 | No | 107 | Green |  |  |  | 0
Ph - 1A | Landscape | Landscape Phase 1-A (Teracces) | HAP Review - TD 1A Right | Hoda / Roshdy |  | 2026-09-16 | 2026-10-06 | Not Started | 20 | No | 114 | Green |  |  |  | 0
Ph - 2A 2B | Buildings |  |  |  |  | 2026-08-09 | 2027-01-21 |  | 165 |  | 221 | Green |  | Ph - 2A 2B¦Buildings |  | 0
Ph - 2A 2B | Buildings | 2 buildings of the great lawn (Phase - 2A 2B) & Teracce 2 | 50% Concept Design | Ashraf / Qadry | KAD | 2025-08-17 | 2025-08-17 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph - 2A 2B | Buildings | 2 buildings of the great lawn (Phase - 2A 2B) & Teracce 2 | 100% Concept Design | Ashraf / Qadry | KAD | 2025-08-31 | 2025-08-31 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph - 2A 2B | Buildings | 2 buildings of the great lawn (Phase - 2A 2B) & Teracce 2 | HAP & Consultant Review - 100% Concept Verification | Ashraf / Qadry |  | 2025-10-12 | 2025-10-28 | Completed | 16 | - | 0 | Red |  |  |  | 0
Ph - 2A 2B | Buildings | 2 buildings of the great lawn (Phase - 2A 2B) & Teracce 2 | 100% Schematic Design | Ashraf / Qadry | KAD | 2025-11-02 | 2025-12-09 | Completed | 37 | - | 0 | Red |  |  |  | 0
Ph - 2A 2B | Buildings | 2 buildings of the great lawn (Phase - 2A 2B) & Teracce 2 | HAP Review - 100% SD | Ashraf / Qadry |  | 2025-11-16 | 2025-12-17 | Completed | 31 | - | 0 | Red |  |  |  | 0
Ph - 2A 2B | Buildings | 2 buildings of the great lawn (Phase - 2A 2B) & Teracce 2 | Cost Plan - 100% SD | Nour / Noha | Survtec | 2025-11-16 | 2026-03-03 | Completed | 107 | - | 0 | Red |  |  |  | 0
Ph - 2A 2B | Buildings | 2 buildings of the great lawn (Phase - 2A 2B) & Teracce 2 | 50% Detailed Design | Ashraf / Qadry | KAD | 2025-12-18 | 2026-01-19 | Completed | 32 | - | 0 | Red |  |  |  | 0
Ph - 2A 2B | Buildings | 2 buildings of the great lawn (Phase - 2A 2B) & Teracce 2 | HAP Review - 50% DD | Ashraf / Qadry |  | 2026-01-01 | 2026-02-02 | Completed | 32 | - | 0 | Red |  |  |  | 0
Ph - 2A 2B | Buildings | 2 buildings of the great lawn (Phase - 2A 2B) & Teracce 2 | 100% Detailed Design | Ashraf / Qadry | KAD | 2026-01-22 | 2026-03-04 | Completed | 41 | - | 0 | Red |  |  |  | 0
Ph - 2A 2B | Buildings | 2 buildings of the great lawn (Phase - 2A 2B) & Teracce 2 | Permits Drawings | Ashraf / Qadry | KAD | 2026-01-29 | 2026-01-19 | Completed | -10 | - | 0 | Red |  |  |  | 0
Ph - 2A 2B | Buildings | 2 buildings of the great lawn (Phase - 2A 2B) & Teracce 2 | HAP Review - 100% DD | Ashraf / Qadry |  | 2026-02-12 | 2026-04-07 | Completed | 54 | - | 0 | Red |  |  |  | 0
Ph - 2A 2B | Buildings | 2 buildings of the great lawn (Phase - 2A 2B) & Teracce 2 | Structure Peer Review - 100% DD | Ashraf / Qadry | KAD | 2026-02-12 | 2026-03-30 | Completed | 46 | - | 0 | Red |  |  |  | 0
Ph - 2A 2B | Buildings | 2 buildings of the great lawn (Phase - 2A 2B) & Teracce 2 | Cost Plan for Detailed Design | Nour / Noha | Survtec | 2026-02-05 | 2026-07-01 | Inprogress | 146 | Yes | 17 | Amber |  |  | 8 | 1 | 8
Ph - 2A 2B | Buildings | 2 buildings of the great lawn (Phase - 2A 2B) & Teracce 2 | Updated Permits Drawings | Ashraf / Qadry | KAD |  | 2026-04-15 | Completed |  | - | 0 | Red |  |  |  | 0
Ph - 2A 2B | Buildings | 2 buildings of the great lawn (Phase - 2A 2B) & Teracce 2 | Tender Package (Great Lawn B1&B2) | Ashraf / Qadry | KAD | 2026-03-05 | 2026-06-28 | Inprogress | 115 | Yes | 14 | Amber |  |  | 9 | 1 | 9
Ph - 2A 2B | Buildings | 2 buildings of the great lawn (Phase - 2A 2B) & Teracce 2 | HAP Review - TD (Great Lawn B1&B2) | Ashraf / Qadry |  | 2026-03-19 | 2026-07-12 | Not Started | 115 | No | 28 | Green |  |  |  | 0
Ph - 2A 2B | Buildings | 2 buildings of the great lawn (Phase - 2A 2B) & Teracce 2 | Design Development - Teracce 01&02 | Ashraf / Qadry | KAD | 2026-04-05 | 2026-08-06 | Not Started | 123 | No | 53 | Green |  |  |  | 0
Ph - 2A 2B | Buildings | 2 buildings of the great lawn (Phase - 2A 2B) & Teracce 2 | HAP Review - DD Teracce 01&02 | Ashraf / Qadry |  | 2026-04-12 | 2026-08-13 | Not Started | 123 | No | 60 | Green |  |  |  | 0
Ph - 2A 2B | Buildings | 2 buildings of the great lawn (Phase - 2A 2B) & Teracce 2 | Tender Package - Teracce 01&02 |  |  | 2026-04-26 | 2026-08-27 | Not Started | 123 | No | 74 | Green |  |  |  | 0
Ph - 2A 2B | Buildings | 2 buildings of the great lawn (Phase - 2A 2B) & Teracce 2 | HAP Review - TD Teracce 01&02 |  |  | 2026-05-03 | 2026-09-03 | Not Started | 123 | No | 81 | Green |  |  |  | 0
Ph - 2A 2B | Authorities |  |  |  |  | 2026-06-18 | 2026-09-27 |  | 101 |  | 105 | Green |  | Ph - 2A 2B¦Authorities |  | 0
Ph - 2A 2B | Authorities | Authorities Issuance | Ministerial decree-NUCA | Afifi |  | 2025-12-08 | 2026-03-25 | Completed | 107 | - | 0 | Red |  |  |  | 0
Ph - 2A 2B | Authorities | Authorities Issuance | Egyptian Institution for Construction Civil Liability Insurance & Civil Defense | Afifi |  | 2026-02-12 | 2026-07-05 | Inprogress | 143 | No | 21 | Amber |  |  |  | 0
Ph - 2A 2B | Authorities | Authorities Issuance | Construction licenses-Permits | Afifi |  | 2026-03-26 | 2026-08-02 | Not Started | 129 | No | 49 | Green |  |  |  | 0
Ph - 2A 2B | Authorities | Authorities Issuance | Mineral licenses-Excavation | Afifi |  | 2026-06-18 | 2026-09-27 | Not Started | 101 | No | 105 | Green |  |  |  | 0
Ph - 2A 2B | Masterplan |  |  |  |  | 2026-01-11 | 2026-08-13 |  | 214 |  | 60 | Green |  | Ph - 2A 2B¦Masterplan |  | 0
Ph - 2A 2B | Masterplan | Master Planning (PHASE - Buildings 2A 2B) Great Lawn | 50% Concept Design Review | Ashraf / Qadry | ECG | 2024-11-10 | 2024-11-10 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph - 2A 2B | Masterplan | Master Planning (PHASE - Buildings 2A 2B) Great Lawn | HAP Review - 50% CD | Ashraf / Qadry |  | 2024-11-24 | 2024-11-24 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph - 2A 2B | Masterplan | Master Planning (PHASE - Buildings 2A 2B) Great Lawn | 100% Concept Design Review | Ashraf / Qadry | ECG | 2024-12-08 | 2024-12-08 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph - 2A 2B | Masterplan | Master Planning (PHASE - Buildings 2A 2B) Great Lawn | HAP Review - 100% CD | Ashraf / Qadry |  | 2024-12-22 | 2024-12-22 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph - 2A 2B | Masterplan | Master Planning (PHASE - Buildings 2A 2B) Great Lawn | 100% Schematic Design & BODR | Ashraf / Qadry | ECG | 2025-01-05 | 2025-01-05 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph - 2A 2B | Masterplan | Master Planning (PHASE - Buildings 2A 2B) Great Lawn | HAP Review - 100% SD | Ashraf / Qadry |  | 2025-01-19 | 2025-01-19 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph - 2A 2B | Masterplan | Master Planning (PHASE - Buildings 2A 2B) Great Lawn | 50% Detailed Design | Ashraf / Qadry | ECG | 2025-09-07 | 2025-09-07 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph - 2A 2B | Masterplan | Master Planning (PHASE - Buildings 2A 2B) Great Lawn | HAP Review - 50% DD | Ashraf / Qadry |  | 2025-09-21 | 2025-09-21 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph - 2A 2B | Masterplan | Master Planning (PHASE - Buildings 2A 2B) Great Lawn | 100% Detailed Design | Ashraf / Qadry | ECG | 2025-11-09 | 2025-12-08 | Completed | 29 | - | 0 | Red |  |  |  | 0
Ph - 2A 2B | Masterplan | Master Planning (PHASE - Buildings 2A 2B) Great Lawn | HAP Review - 100% DD | Ashraf / Qadry |  | 2025-11-23 | 2026-01-19 | Completed | 57 | - | 0 | Red |  |  |  | 0
Ph - 2A 2B | Masterplan | Master Planning (PHASE - Buildings 2A 2B) Great Lawn | Tender Package | Ashraf / Qadry | ECG | 2025-12-14 | 2026-04-02 | Completed | 109 | - | 0 | Red |  |  |  | 0
Ph - 2A 2B | Masterplan | Master Planning (PHASE - Buildings 2A 2B) Great Lawn | HAP Review - TD | Ashraf / Qadry |  | 2025-12-28 | 2026-04-07 | Completed | 100 | - | 0 | Red |  |  |  | 0
Ph - 2A 2B | Masterplan | Master Planning (PHASE - Buildings 2A 2B) Great Lawn | IFT Submission | Ashraf / Qadry |  | 2026-01-11 | 2026-08-13 | Not Started | 214 | No | 60 | Green |  |  |  | 0
Ph - 2A 2B | Infrastructure |  |  |  |  | 2026-03-09 | 2026-05-05 |  | 57 |  | -40 | Red |  | Ph - 2A 2B¦Infrastructure |  | 0
Ph - 2A 2B | Infrastructure | Infrastructure & roads (PHASE - Buildings 2A 2B) Great Lawn | 50% Concept Design | Ashraf / Qadry | ECG | 2024-11-10 | 2024-11-10 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph - 2A 2B | Infrastructure | Infrastructure & roads (PHASE - Buildings 2A 2B) Great Lawn | HAP Review - 50% CD | Ashraf / Qadry |  | 2024-12-01 | 2024-12-01 | Completed | 0 | - | -560 | Red |  |  |  | 0
Ph - 2A 2B | Infrastructure | Infrastructure & roads (PHASE - Buildings 2A 2B) Great Lawn | 100% Concept Design | Ashraf / Qadry | ECG | 2024-12-15 | 2024-12-15 | Completed | 0 | - | -546 | Red |  |  |  | 0
Ph - 2A 2B | Infrastructure | Infrastructure & roads (PHASE - Buildings 2A 2B) Great Lawn | HAP Review - 100% CD | Ashraf / Qadry |  | 2024-12-29 | 2024-12-29 | Completed | 0 | - | -532 | Red |  |  |  | 0
Ph - 2A 2B | Infrastructure | Infrastructure & roads (PHASE - Buildings 2A 2B) Great Lawn | 100% Schematic Design & BODR | Ashraf / Qadry | ECG | 2025-01-12 | 2025-01-12 | Completed | 0 | - | -518 | Red |  |  |  | 0
Ph - 2A 2B | Infrastructure | Infrastructure & roads (PHASE - Buildings 2A 2B) Great Lawn | HAP Review - 100% SD | Ashraf / Qadry |  | 2025-01-26 | 2025-01-26 | Completed | 0 | - | -504 | Red |  |  |  | 0
Ph - 2A 2B | Infrastructure | Infrastructure & roads (PHASE - Buildings 2A 2B) Great Lawn | 50% Detailed Design | Ashraf / Qadry | ECG | 2025-09-07 | 2025-09-07 | Completed | 0 | - | -280 | Red |  |  |  | 0
Ph - 2A 2B | Infrastructure | Infrastructure & roads (PHASE - Buildings 2A 2B) Great Lawn | HAP Review - 50% DD | Ashraf / Qadry |  | 2025-09-21 | 2025-09-21 | Completed | 0 | - | -266 | Red |  |  |  | 0
Ph - 2A 2B | Infrastructure | Infrastructure & roads (PHASE - Buildings 2A 2B) Great Lawn | 100% Detailed Design | Ashraf / Qadry | ECG | 2025-11-09 | 2025-12-08 | Completed | 29 | - | -188 | Red |  |  |  | 0
Ph - 2A 2B | Infrastructure | Infrastructure & roads (PHASE - Buildings 2A 2B) Great Lawn | HAP Review - 100% DD | Ashraf / Qadry |  | 2025-11-23 | 2026-02-25 | Completed | 94 | - | -109 | Red |  |  |  | 0
Ph - 2A 2B | Infrastructure | Infrastructure & roads (PHASE - Buildings 2A 2B) Great Lawn | Tender Package | Ashraf / Qadry | ECG | 2026-02-23 | 2026-04-02 | Completed | 38 | - | -73 | Red |  |  |  | 0
Ph - 2A 2B | Infrastructure | Infrastructure & roads (PHASE - Buildings 2A 2B) Great Lawn | HAP Review - TD | Ashraf / Qadry |  | 2026-03-09 | 2026-05-05 | Completed | 57 | - | -40 | Red |  |  |  | 0
Ph - 2A 2B | Infrastructure | Infrastructure & roads (PHASE - Buildings 2A 2B) Great Lawn | MIDAR Approval | Ashraf / Qadry / Afifi |  | 2026-02-02 | 2026-07-06 | Inprogress | 154 | No | 22 | Green |  |  |  | 0
Ph - 2A 2B | Landscape |  |  |  |  | 2027-09-22 | 2027-02-02 |  | -232 |  | 233 | Green |  | Ph - 2A 2B¦Landscape |  | 0
Ph - 2A 2B | Landscape | Landscape Phase 2A & 2B Great Lawn | 50% Detailed Design | Hoda / Roshdy | ECG | 2026-10-14 | 2026-11-03 | Not Started | 20 | No | 142 | Green |  |  |  | 0
Ph - 2A 2B | Landscape | Landscape Phase 2A & 2B Great Lawn | HAP Review - 50% DD | Hoda / Roshdy |  | 2026-10-28 | 2026-11-17 | Not Started | 20 | No | 156 | Green |  |  |  | 0
Ph - 2A 2B | Landscape | Landscape Phase 2A & 2B Great Lawn | 100% Detailed Design | Hoda / Roshdy | ECG | 2026-11-25 | 2026-12-15 | Not Started | 20 | No | 184 | Green |  |  |  | 0
Ph - 2A 2B | Landscape | Landscape Phase 2A & 2B Great Lawn | HAP Review - 100% DD | Hoda / Roshdy |  | 2026-12-09 | 2026-12-29 | Not Started | 20 | No | 198 | Green |  |  |  | 0
Ph - 2A 2B | Landscape | Landscape Phase 2A & 2B Great Lawn | Cost Plan - 100% DD | Nour / Noha |  | 2026-12-09 | 2026-12-29 | Not Started | 20 | No | 198 | Green |  |  |  | 0
Ph - 2A 2B | Landscape | Landscape Phase 2A & 2B Great Lawn | Tender Package - 2B | Hoda / Roshdy | ECG | 2026-12-30 | 2027-01-19 | Not Started | 20 | No | 219 | Green |  |  |  | 0
Ph - 2A 2B | Landscape | Landscape Phase 2A & 2B Great Lawn | HAP Review - TD 2B | Hoda / Roshdy |  | 2027-01-13 | 2027-02-02 | Not Started | 20 | No | 233 | Green |  |  |  | 0
Ph - 2A 2B | Landscape | Landscape Phase 2A & 2B Great Lawn | Tender Package - 2A | Hoda / Roshdy | ECG | 2027-01-20 | 2027-02-09 | Not Started | 20 | No | 240 | Green |  |  |  | 0
Ph - 2A 2B | Landscape | Landscape Phase 2A & 2B Great Lawn | HAP Review - TD 2A | Hoda / Roshdy |  | 2027-01-27 | 2027-02-16 | Not Started | 20 | No | 247 | Green |  |  |  | 0
Ph - 1B | Buildings |  |  |  |  | 2027-02-07 | 2027-02-28 |  | 21 |  | 259 | Green |  | Ph - 1B¦Buildings |  | 0
Ph - 1B | Buildings | Phase-1B Standalone Villas ( 7 Prototypes Twins&Towns &Standalone) | 50% Concept Design | Ashraf / Qadry | KMA | 2025-09-04 | 2025-09-04 | Completed | 0 | - | -283 | Red |  |  |  | 0
Ph - 1B | Buildings | Phase-1B Standalone Villas ( 7 Prototypes Twins&Towns &Standalone) | 100% Concept Design | Ashraf / Qadry | KMA | 2025-10-02 | 2025-10-02 | Completed | 0 | - | -255 | Red |  |  |  | 0
Ph - 1B | Buildings | Phase-1B Standalone Villas ( 7 Prototypes Twins&Towns &Standalone) | HAP Review - 100% CD | Ashraf / Qadry |  | 2025-10-16 | 2025-10-16 | Completed | 0 | - | -241 | Red |  |  |  | 0
Ph - 1B 2C | Buildings | Phase-1B Standalone Villas ( 7 Prototypes Twins&Towns &Standalone) | Tender to assign Consultant |  |  | 2025-11-13 | 2026-04-07 | Completed | 145 | - | -68 | Red |  | Ph - 1B 2C¦Buildings |  | 0
Ph - 1B 2C | Buildings | Phase-1B Standalone Villas ( 7 Prototypes Twins&Towns &Standalone) | Concept Verification | Ashraf / Qadry | KAD | 2025-11-27 | 2026-04-27 | Completed | 151 | - | -48 | Red |  |  |  | 0
Ph - 1B 2C | Buildings | Phase-1B Standalone Villas ( 7 Prototypes Twins&Towns &Standalone) | HAP Review - CV | Ashraf / Qadry |  | 2025-12-04 | 2026-05-05 | Completed | 152 | - | -40 | Red |  |  |  | 0
Ph - 1B 2C | Buildings | Phase-1B Standalone Villas ( 7 Prototypes Twins&Towns &Standalone) | 100% Schematic Design | Ashraf / Qadry | KAD | 2026-01-01 | 2026-06-21 | Completed | 171 | - | 7 | Amber |  |  |  | 0
Ph - 1B 2C | Buildings | Phase-1B Standalone Villas ( 7 Prototypes Twins&Towns &Standalone) | HAP Review - 100% SD | Ashraf / Qadry |  | 2026-01-15 | 2026-07-05 | Inprogress | 171 | No | 21 | Amber |  |  |  | 0
Ph - 1B 2C | Buildings | Phase-1B Standalone Villas ( 7 Prototypes Twins&Towns &Standalone) | Cost Plan - 100% SD | Nour / Noha | Survtec | 2026-01-15 | 2026-07-05 | Not Started | 171 | No | 21 | Amber |  |  |  | 0
Ph - 1B 2C | Buildings | Phase-1B Standalone Villas ( 7 Prototypes Twins&Towns &Standalone) | 50% Detailed Design | Ashraf / Qadry | KAD | 2026-02-12 | 2026-08-02 | Not Started | 171 | No | 49 | Green |  |  |  | 0
Ph - 1B 2C | Buildings | Phase-1B Standalone Villas ( 7 Prototypes Twins&Towns &Standalone) | HAP Review - 50% DD | Ashraf / Qadry |  | 2026-02-26 | 2026-08-16 | Not Started | 171 | No | 63 | Green |  |  |  | 0
Ph - 1B 2C | Buildings | Phase-1B Standalone Villas ( 7 Prototypes Twins&Towns &Standalone) | 100% Detailed Design | Ashraf / Qadry | KAD | 2026-03-19 | 2026-09-06 | Not Started | 171 | No | 84 | Green |  |  |  | 0
Ph - 1B 2C | Buildings | Phase-1B Standalone Villas ( 7 Prototypes Twins&Towns &Standalone) | Structure Peer Review - 100% DD |  |  |  | 2026-09-20 | Not Started |  | No | 98 | Green |  |  |  | 0
Ph - 1B 2C | Buildings | Phase-1B Standalone Villas ( 7 Prototypes Twins&Towns &Standalone) | HAP Review - 100% DD | Ashraf / Qadry |  | 2026-04-02 | 2026-09-20 | Not Started | 171 | No | 98 | Green |  |  |  | 0
Ph - 1B 2C | Buildings | Phase-1B Standalone Villas ( 7 Prototypes Twins&Towns &Standalone) | Cost Plan - 100% DD | Nour / Noha | Survtec | 2026-04-02 | 2026-09-20 | Not Started | 171 | No | 98 | Green |  |  |  | 0
Ph - 1B 2C | Buildings | Phase-1B Standalone Villas ( 7 Prototypes Twins&Towns &Standalone) | Permits Drawings - 1B | Ashraf / Qadry | KAD | 2026-04-16 | 2026-10-04 | Not Started | 171 | No | 112 | Green |  |  |  | 0
Ph - 1B 2C | Buildings | Phase-1B Standalone Villas ( 7 Prototypes Twins&Towns &Standalone) | Tender Package | Ashraf / Qadry | KAD | 2026-04-16 | 2026-10-04 | Not Started | 171 | No | 112 | Green |  |  |  | 0
Ph - 1B 2C | Buildings | Phase-1B Standalone Villas ( 7 Prototypes Twins&Towns &Standalone) | Structure Peer Review - TD |  |  |  | 2026-10-18 | Not Started |  | No | 126 | Green |  |  |  | 0
Ph - 1B 2C | Buildings | Phase-1B Standalone Villas ( 7 Prototypes Twins&Towns &Standalone) | HAP Review - TD | Ashraf / Qadry |  | 2026-04-30 | 2026-10-18 | Not Started | 171 | No | 126 | Green |  |  |  | 0
Ph - 1B 2C | Buildings | Phase-1B Standalone Villas ( 7 Prototypes Twins&Towns &Standalone) | Tender Action |  |  | 2026-08-20 | 2027-02-07 | Not Started | 171 | No | 238 | Green |  |  |  | 0
Ph - 1B 2C | Buildings | Phase-1B Standalone Villas ( 7 Prototypes Twins&Towns &Standalone) | BLDGs Construction Tender |  |  | 2026-09-03 | 2027-02-21 | Not Started | 171 | No | 252 | Green |  |  |  | 0
Ph - 1B 2C & Towers | Authorities |  |  |  |  | 2027-02-07 | 2027-02-28 |  | 21 |  | 259 | Green |  | Ph - 1B 2C & Towers¦Authorities |  | 0
Ph - 1B 2C & Towers | Authorities | Authorities Issuance | Ministerial decree-MIDAR | Afifi |  | 2026-05-03 | 2026-05-24 | Completed | 21 | - | -21 | Red |  |  |  | 0
Ph - 1B 2C & Towers | Authorities | Authorities Issuance | Ministerial decree NUCA (Villas) | Afifi |  | 2026-08-23 | 2026-09-13 | Inprogress | 21 | No | 91 | Green |  |  |  | 0
Ph - 1B 2C & Towers | Authorities | Authorities Issuance | Egyptian Institution for Construction Civil Liability Insurance | Afifi |  | 2026-10-04 | 2026-10-25 | Not Started | 21 | No | 133 | Green |  |  |  | 0
Ph - 1B 2C & Towers | Authorities | Authorities Issuance | Construction licenses-Permits | Afifi |  | 2026-11-15 | 2026-12-06 | Not Started | 21 | No | 175 | Green |  |  |  | 0
Ph - 1B 2C & Towers | Authorities | Authorities Issuance | Mineral licenses-Excavation | Afifi |  | 2027-02-07 | 2027-02-28 | Not Started | 21 | No | 259 | Green |  |  |  | 0
Ph - 1B 2C | Masterplan |  |  |  |  | 2026-09-06 | 2026-09-08 |  | 2 |  | 86 | Green |  | Ph - 1B 2C¦Masterplan |  | 0
Ph - 1B 2C | Masterplan | Master Planning (PHASE - Villas 1B & 2C) | 50% Detailed Design | Ashraf / Qadry | ECG | 2026-05-31 | 2026-05-25 | Completed | -6 | - | -20 | Red |  |  |  | 0
Ph - 1B 2C | Masterplan | Master Planning (PHASE - Villas 1B & 2C) | HAP Review - 50% DD | Ashraf / Qadry |  | 2026-06-14 | 2026-06-16 | Completed | 2 | - | 2 | Amber |  |  |  | 0
Ph - 1B 2C | Masterplan | Master Planning (PHASE - Villas 1B & 2C) | 100% Detailed Design | Ashraf / Qadry | ECG | 2026-07-12 | 2026-07-14 | Inprogress | 2 | No | 30 | Green |  |  |  | 0
Ph - 1B 2C | Masterplan | Master Planning (PHASE - Villas 1B & 2C) | HAP Review - 100% DD | Ashraf / Qadry |  | 2026-07-26 | 2026-07-28 | Not Started | 2 | No | 44 | Green |  |  |  | 0
Ph - 1B 2C | Masterplan | Master Planning (PHASE - Villas 1B & 2C) | Ministerial Decree Package - Phase 2 (Villas) | Ashraf / Qadry | ECG | 2026-03-08 | 2026-03-10 | Completed | 2 | Yes | -96 | Red |  |  | 10 | 1 | 10
Ph - 1B 2C | Masterplan | Master Planning (PHASE - Villas 1B & 2C) | Updated Ministerial Decree Package - Phase 2 (Villas), Phase 2E & 2D | Ashraf / Qadry | ECG | 2026-04-16 | 2026-04-16 | Completed | 0 | Yes | -59 | Red |  |  | 11 | 1 | 11
Ph - 1B 2C | Masterplan | Master Planning (PHASE - Villas 1B & 2C) | Tender Package | Ashraf / Qadry | ECG | 2026-08-09 | 2026-08-11 | Not Started | 2 | No | 58 | Green |  |  |  | 0
Ph - 1B 2C | Masterplan | Master Planning (PHASE - Villas 1B & 2C) | HAP Review - TD | Ashraf / Qadry |  | 2026-08-23 | 2026-08-25 | Not Started | 2 | No | 72 | Green |  |  |  | 0
|  | Master Planning (PHASE - Villas 1B & 2C) | IFC Submission |  |  | 2026-09-06 | 2026-09-08 | Not Started | 2 | No | 86 | Green |  | ¦ |  | 0
Ph - 1B 2C | Infrastructure |  |  |  |  | 2026-10-04 | 2026-10-06 |  | 2 | No | 114 | Green |  | Ph - 1B 2C¦Infrastructure |  | 0
Ph - 1B 2C | Infrastructure | Infrastructure & roads (PHASE - Villas 1B & 2C) | 50% Detailed Design | Ashraf / Qadry | ECG | 2026-05-31 | 2026-05-25 | Completed | -6 | Yes | -20 | Red |  |  | 12 | 1 | 12
Ph - 1B 2C | Infrastructure | Infrastructure & roads (PHASE - Villas 1B & 2C) | HAP Review - 50% DD | Ashraf / Qadry |  | 2026-06-14 | 2026-06-16 | Completed | 2 | Yes | 2 | Amber |  |  | 13 | 1 | 13
Ph - 1B 2C | Infrastructure | Infrastructure & roads (PHASE - Villas 1B & 2C) | 100% Detailed Design | Ashraf / Qadry | ECG | 2026-08-09 | 2026-08-11 | Inprogress | 2 | No | 58 | Green |  |  |  | 0
Ph - 1B 2C | Infrastructure | Infrastructure & roads (PHASE - Villas 1B & 2C) | HAP Review - 100% DD | Ashraf / Qadry |  | 2026-08-23 | 2026-08-25 | Not Started | 2 | No | 72 | Green |  |  |  | 0
Ph - 1B 2C | Infrastructure | Infrastructure & roads (PHASE - Villas 1B & 2C) | Midar Approval - 1B & 2C | Ashraf / Qadry / Afifi |  | 2026-09-06 | 2026-09-08 | Not Started | 2 | No | 86 | Green |  |  |  | 0
Ph - 1B 2C | Infrastructure | Infrastructure & roads (PHASE - Villas 1B & 2C) | Tender Package | Ashraf / Qadry | ECG | 2026-09-20 | 2026-09-22 | Not Started | 2 | No | 100 | Green |  |  |  | 0
Ph - 1B 2C | Infrastructure | Infrastructure & roads (PHASE - Villas 1B & 2C) | HAP Review - TD | Ashraf / Qadry |  | 2026-10-04 | 2026-10-06 | Not Started | 2 | No | 114 | Green |  |  |  | 0
Ph - 1B | Landscape |  |  |  |  | 2027-09-22 | 2027-02-02 |  | -232 | No | 233 | Green |  | Ph - 1B¦Landscape |  | 0
Ph - 1B | Landscape | Landscape Phase 1-B Villas | 50% Detailed Design | Hoda / Roshdy | ECG | 2026-10-14 | 2026-11-03 | Not Started | 20 | No | 142 | Green |  |  |  | 0
Ph - 1B | Landscape | Landscape Phase 1-B Villas | HAP Review - 50% DD | Hoda / Roshdy |  | 2026-10-28 | 2026-11-17 | Not Started | 20 | No | 156 | Green |  |  |  | 0
Ph - 1B | Landscape | Landscape Phase 1-B Villas | 100% Detailed Design | Hoda / Roshdy | ECG | 2026-11-25 | 2026-12-15 | Not Started | 20 | No | 184 | Green |  |  |  | 0
Ph - 1B | Landscape | Landscape Phase 1-B Villas | HAP Review - 100% DD | Hoda / Roshdy |  | 2026-12-09 | 2026-12-29 | Not Started | 20 | No | 198 | Green |  |  |  | 0
Ph - 1B | Landscape | Landscape Phase 1-B Villas | Cost Plan - 100% DD | Nour / Noha |  | 2026-12-09 | 2026-12-29 | Not Started | 20 | No | 198 | Green |  |  |  | 0
Ph - 1B | Landscape | Landscape Phase 1-B Villas | Tender Package | Hoda / Roshdy | ECG | 2026-12-30 | 2027-01-19 | Not Started | 20 | No | 219 | Green |  |  |  | 0
Ph - 1B | Landscape | Landscape Phase 1-B Villas | HAP Review - TD | Hoda / Roshdy |  | 2027-01-13 | 2027-02-02 | Not Started | 20 | No | 233 | Green |  |  |  | 0
Ph - 2C | Landscape |  |  |  |  | 2027-05-12 | 2027-06-01 |  | 20 | Yes | 352 | Green |  | Ph - 2C¦Landscape | 14 | 1 | 14
Ph - 2C | Landscape | Landscape Phase 2-C Villas | 50% Detailed Design | Hoda / Roshdy | ECG | 2027-02-10 | 2027-03-02 | Not Started | 20 | Yes | 261 | Green |  |  | 15 | 1 | 15
Ph - 2C | Landscape | Landscape Phase 2-C Villas | HAP Review - 50% DD | Hoda / Roshdy |  | 2027-02-24 | 2027-03-16 | Not Started | 20 | Yes | 275 | Green |  |  | 16 | 1 | 16
Ph - 2C | Landscape | Landscape Phase 2-C Villas | 100% Detailed Design | Hoda / Roshdy | ECG | 2027-03-24 | 2027-04-13 | Not Started | 20 | Yes | 303 | Green |  |  | 17 | 1 | 17
Ph - 2C | Landscape | Landscape Phase 2-C Villas | HAP Review - 100% DD | Hoda / Roshdy |  | 2027-04-07 | 2027-04-27 | Not Started | 20 | Yes | 317 | Green |  |  | 18 | 1 | 18
Ph - 2C | Landscape | Landscape Phase 2-C Villas | Cost Plan - 100% DD | Nour / Noha |  | 2027-04-07 | 2027-04-27 | Not Started | 20 | Yes | 317 | Green |  |  | 19 | 1 | 19
Ph - 2C | Landscape | Landscape Phase 2-C Villas | Tender Package | Hoda / Roshdy | ECG | 2027-04-28 | 2027-05-18 | Not Started | 20 | Yes | 338 | Green |  |  | 20 | 1 | 20
Ph - 2C | Landscape | Landscape Phase 2-C Villas | HAP Review - TD | Hoda / Roshdy |  | 2027-05-12 | 2027-06-01 | Not Started | 20 | Yes | 352 | Green |  |  | 21 | 1 | 21
External Fences and Gates | Landscape |  |  |  |  | 2026-11-29 | 2026-11-30 |  | 1 | Yes | 169 | Green |  | External Fences and Gates¦Landscape | 22 | 1 | 22
External Fences and Gates | Landscape | External Fences and Gates | 100% Concept Design (International Consultant) | Hoda / Roshdy | Cracknell | 2025-09-29 | 2025-11-02 | Completed | 34 | No | -224 | Red |  |  |  | 0
External Fences and Gates | Landscape | External Fences and Gates | HAP Review - 100% CD | Hoda / Roshdy |  | 2025-10-13 | 2026-01-12 | Completed | 91 | No | -153 | Red |  |  |  | 0
External Fences and Gates | Landscape | External Fences and Gates | Midar Approval | Ashraf / Qadry / Afifi |  |  | 2026-03-24 | Completed |  | No | -82 | Red |  |  |  | 0
External Fences and Gates | Landscape | External Fences and Gates | 100% Schematic Design (International Consultant) VO | Hoda / Roshdy | Cracknell | 2025-11-10 | 2026-04-27 | Completed | 168 | No | -48 | Red |  |  |  | 0
External Fences and Gates | Landscape | External Fences and Gates | HAP Review - 100% SD | Hoda / Roshdy |  | 2025-11-24 | 2026-05-04 | Completed | 161 | No | -41 | Red |  |  |  | 0
External Fences and Gates | Landscape | External Fences and Gates | Schematic Verification | Hoda / Roshdy | ECG | 2026-05-10 | 2026-05-18 | Completed | 8 | No | -27 | Red |  |  |  | 0
External Fences and Gates | Landscape | External Fences and Gates | HAP Review - SV | Hoda / Roshdy |  | 2026-05-24 | 2026-05-25 | Completed | 1 | No | -20 | Red |  |  |  | 0
External Fences and Gates | Landscape | External Fences and Gates | 50% Detailed Design | Hoda / Roshdy | ECG | 2026-06-21 | 2026-06-22 | Not Started | 1 | No | 8 | Amber |  |  |  | 0
External Fences and Gates | Landscape | External Fences and Gates | HAP Review - 50% DD | Hoda / Roshdy |  | 2026-07-05 | 2026-07-06 | Not Started | 1 | Yes | 22 | Green |  |  | 23 | 1 | 23
External Fences and Gates | Landscape | External Fences and Gates | 100% Detailed Design | Hoda / Roshdy | ECG | 2026-08-23 | 2026-08-24 | Not Started | 1 | Yes | 71 | Green |  |  | 24 | 1 | 24
External Fences and Gates | Landscape | External Fences and Gates | HAP Review - 100% DD | Hoda / Roshdy |  | 2026-09-06 | 2026-09-07 | Not Started | 1 | Yes | 85 | Green |  |  | 25 | 1 | 25
External Fences and Gates | Landscape | External Fences and Gates | Permits Drawings | Hoda / Roshdy | ECG | 2026-09-06 | 2026-09-07 | Not Started | 1 | Yes | 85 | Green |  |  | 26 | 1 | 26
External Fences and Gates | Landscape | External Fences and Gates | Tender Package | Hoda / Roshdy | ECG | 2026-10-18 | 2026-10-19 | Not Started | 1 | Yes | 127 | Green |  |  | 27 | 1 | 27
External Fences and Gates | Landscape | External Fences and Gates | HAP Review - TD | Hoda / Roshdy |  | 2026-11-01 | 2026-11-02 | Not Started | 1 | Yes | 141 | Green |  |  | 28 | 1 | 28
|  | External Fences and Gates | IFC Submission |  |  | 2026-11-15 | 2026-11-16 | Not Started | 1 | Yes | 155 | Green |  | ¦ | 29 | 1 | 29
External Fences and Gates | Authorities | External Fences and Gates | Authorities Issuance (Fences and Gates) |  |  | 2026-11-29 | 2026-11-30 | Not Started | 1 | Yes | 169 | Green |  | External Fences and Gates¦Authorities | 30 | 1 | 30
External Fences and Gates | Authorities | External Fences and Gates | Ministerial decree-NUCA | Afifi |  | 2025-12-08 | 2026-03-25 | Completed | 107 | No | -81 | Red |  |  |  | 0
External Fences and Gates | Authorities | External Fences and Gates | Construction licenses- Fences Buildings Permits | Afifi |  | 2026-11-29 | 2026-11-30 | Not Started | 1 | Yes | 169 | Green |  |  | 31 | 1 | 31
Ph - 2D 2E | Masterplan |  |  |  |  | 2027-01-24 | 2027-01-26 |  | 2 | Yes | 226 | Green |  | Ph - 2D 2E¦Masterplan | 32 | 1 | 32
Ph - 2D 2E | Masterplan | Master Planning (PHASE - Apartments 2D 2E) | 50% Detailed Design | Ashraf / Qadry | ECG | 2026-09-20 | 2026-09-22 | Not Started | 2 | Yes | 100 | Green |  |  | 33 | 1 | 33
Ph - 2D 2E | Masterplan | Master Planning (PHASE - Apartments 2D 2E) | HAP Review - 50% DD | Ashraf / Qadry |  | 2026-10-04 | 2026-10-06 | Not Started | 2 | Yes | 114 | Green |  |  | 34 | 1 | 34
Ph - 2D 2E | Masterplan | Master Planning (PHASE - Apartments 2D 2E) | 100% Detailed Design | Ashraf / Qadry | ECG | 2026-11-29 | 2026-12-01 | Not Started | 2 | Yes | 170 | Green |  |  | 35 | 1 | 35
Ph - 2D 2E | Masterplan | Master Planning (PHASE - Apartments 2D 2E) | HAP Review - 100% DD | Ashraf / Qadry |  | 2026-12-13 | 2026-12-15 | Not Started | 2 | Yes | 184 | Green |  |  | 36 | 1 | 36
Ph - 2D 2E | Masterplan | Master Planning (PHASE - Apartments 2D 2E) | Tender Package | Ashraf / Qadry | ECG | 2026-12-27 | 2026-12-29 | Not Started | 2 | Yes | 198 | Green |  |  | 37 | 1 | 37
Ph - 2D 2E | Masterplan | Master Planning (PHASE - Apartments 2D 2E) | HAP Review - TD | Ashraf / Qadry |  | 2027-01-10 | 2027-01-12 | Not Started | 2 | Yes | 212 | Green |  |  | 38 | 1 | 38
|  | Master Planning (PHASE - Apartments 2D 2E) | IFC Submission |  |  | 2027-01-24 | 2027-01-26 | Not Started | 2 | Yes | 226 | Green |  | ¦ | 39 | 1 | 39
Ph - 2D 2E | Infrastructure |  |  |  |  | 2027-01-24 | 2027-01-26 |  | 2 | Yes | 226 | Green |  | Ph - 2D 2E¦Infrastructure | 40 | 1 | 40
Ph - 2D 2E | Infrastructure | Infrastructure & roads (PHASE - Apartments 2D 2E) | 50% Detailed Design | Ashraf / Qadry | ECG | 2026-09-20 | 2026-09-22 | Not Started | 2 | Yes | 100 | Green |  |  | 41 | 1 | 41
Ph - 2D 2E | Infrastructure | Infrastructure & roads (PHASE - Apartments 2D 2E) | HAP Review - 50% DD | Ashraf / Qadry |  | 2026-10-04 | 2026-10-06 | Not Started | 2 | Yes | 114 | Green |  |  | 42 | 1 | 42
Ph - 2D 2E | Infrastructure | Infrastructure & roads (PHASE - Apartments 2D 2E) | 100% Detailed Design | Ashraf / Qadry | ECG | 2026-11-29 | 2026-12-01 | Not Started | 2 | Yes | 170 | Green |  |  | 43 | 1 | 43
Ph - 2D 2E | Infrastructure | Infrastructure & roads (PHASE - Apartments 2D 2E) | HAP Review - 100% DD | Ashraf / Qadry |  | 2026-12-13 | 2026-12-15 | Not Started | 2 | Yes | 184 | Green |  |  | 44 | 1 | 44
Ph - 2D 2E | Infrastructure | Infrastructure & roads (PHASE - Apartments 2D 2E) | Tender Package | Ashraf / Qadry | ECG | 2026-12-27 | 2026-12-29 | Not Started | 2 | Yes | 198 | Green |  |  | 45 | 1 | 45
Ph - 2D 2E | Infrastructure | Infrastructure & roads (PHASE - Apartments 2D 2E) | HAP Review - TD | Ashraf / Qadry |  | 2027-01-10 | 2027-01-12 | Not Started | 2 | Yes | 212 | Green |  |  | 46 | 1 | 46
|  | Infrastructure & roads (PHASE - Apartments 2D 2E) | IFC Submission |  |  | 2027-01-24 | 2027-01-26 | Not Started | 2 | Yes | 226 | Green |  | ¦ | 47 | 1 | 47
Ph - 2D 2E | Landscape |  |  |  |  | 2027-09-22 | 2027-10-12 |  | 20 | Yes | 485 | Green |  | Ph - 2D 2E¦Landscape | 48 | 1 | 48
Ph - 2D 2E | Landscape | Landscape Phase 2E & 2D Apartments | 50% Detailed Design | Hoda / Roshdy | ECG | 2027-06-09 | 2027-06-29 | Not Started | 20 | Yes | 380 | Green |  |  | 49 | 1 | 49
Ph - 2D 2E | Landscape | Landscape Phase 2E & 2D Apartments | HAP Review - 50% DD | Hoda / Roshdy |  | 2027-06-23 | 2027-07-13 | Not Started | 20 | Yes | 394 | Green |  |  | 50 | 1 | 50
Ph - 2D 2E | Landscape | Landscape Phase 2E & 2D Apartments | 100% Detailed Design | Hoda / Roshdy | ECG | 2027-07-21 | 2027-08-10 | Not Started | 20 | Yes | 422 | Green |  |  | 51 | 1 | 51
Ph - 2D 2E | Landscape | Landscape Phase 2E & 2D Apartments | HAP Review - 100% DD | Hoda / Roshdy |  | 2027-08-04 | 2027-08-24 | Not Started | 20 | Yes | 436 | Green |  |  | 52 | 1 | 52
Ph - 2D 2E | Landscape | Landscape Phase 2E & 2D Apartments | Cost Plan - 100% DD | Hoda / Roshdy |  | 2027-08-04 | 2027-08-24 | Not Started
Ph - 2D 2E | Landscape | Landscape Phase 2E & 2D Apartments | Tender Package - 2E | Hoda / Roshdy | ECG | 2027-08-25 | 2027-09-14 | Not Started
Ph - 2D 2E | Landscape | Landscape Phase 2E & 2D Apartments | HAP Review - TD 2E | Hoda / Roshdy |  | 2027-09-08 | 2027-09-28 | Not Started
Ph - 2D 2E | Landscape | Landscape Phase 2E & 2D Apartments | Tender Package - 2D | Hoda / Roshdy | ECG | 2027-09-15 | 2027-10-05 | Not Started
Ph - 2D 2E | Landscape | Landscape Phase 2E & 2D Apartments | HAP Review - TD 2D | Hoda / Roshdy |  | 2027-09-22 | 2027-10-12 | Not Started
Commercial | Buildings | Landscape Phase 2E & 2D Apartments | Commercial Buildings |  |  | 2027-08-08 | 2027-08-10 | Not Started
Commercial | Buildings | Landscape Phase 2E & 2D Apartments | Submission of Concept Design - 50% |  |  | 2026-07-12 | 2026-07-14 | Not Started
Commercial | Buildings | Landscape Phase 2E & 2D Apartments | HAP Review |  |  | 2026-07-26 | 2026-07-28 | Not Started
Commercial | Buildings | Landscape Phase 2E & 2D Apartments | Submission of Concept Design - 100% |  |  | 2026-08-09 | 2026-08-11 | Not Started
Commercial | Buildings | Landscape Phase 2E & 2D Apartments | HAP & Consultant Review - 100% Concept Verification |  |  | 2026-08-16 | 2026-08-18 | Not Started
Commercial | Buildings | Landscape Phase 2E & 2D Apartments | Schematic Design |  |  | 2026-09-20 | 2026-09-22 | Not Started
Commercial | Buildings | Landscape Phase 2E & 2D Apartments | HAP Review |  |  | 2026-10-04 | 2026-10-06 | Not Started
Commercial | Buildings | Landscape Phase 2E & 2D Apartments | Cost Plan for Schematic Design |  |  | 2026-10-04 | 2026-10-06 | Not Started
Commercial | Buildings | Landscape Phase 2E & 2D Apartments | Detailed Design 50% |  |  | 2026-11-15 | 2026-11-17 | Not Started
Commercial | Buildings | Landscape Phase 2E & 2D Apartments | HAP Review |  |  | 2026-11-29 | 2026-12-01 | Not Started
Commercial | Buildings | Landscape Phase 2E & 2D Apartments | Detailed Design 100% |  |  | 2027-01-24 | 2027-01-26 | Not Started
Commercial | Buildings | Landscape Phase 2E & 2D Apartments | HAP Review |  |  | 2027-02-07 | 2027-02-09 | Not Started
Commercial | Buildings | Landscape Phase 2E & 2D Apartments | Cost Plan for Detailed Design |  |  | 2027-02-07 | 2027-02-09 | Not Started
Commercial | Buildings | Landscape Phase 2E & 2D Apartments | Permit Drawings & Documents (IFP, IFDL, IFCD) |  |  | 2027-02-21 | 2027-02-23 | Not Started
Commercial | Buildings | Landscape Phase 2E & 2D Apartments | Tender Package |  |  | 2027-03-14 | 2027-03-16 | Not Started
Commercial | Buildings | Landscape Phase 2E & 2D Apartments | HAP Review |  |  | 2027-03-21 | 2027-03-23 | Not Started
Commercial | Buildings | Landscape Phase 2E & 2D Apartments | BOQ Preperation |  |  | 2027-03-28 | 2027-03-30 | Not Started
Commercial | Authorities | Landscape Phase 2E & 2D Apartments |  |  |  | 2027-08-08 | 2027-08-10 | Not Started
Commercial | Authorities | Landscape Phase 2E & 2D Apartments | Ministerial decree-MIDAR |  |  | 2027-04-04 | 2027-04-06 | Not Started
Commercial | Authorities | Landscape Phase 2E & 2D Apartments | Egyptian Institution for Construction Civil Liability Insurance & Civil Defense |  |  | 2027-04-04 | 2027-04-06 | Not Started
Commercial | Authorities | Landscape Phase 2E & 2D Apartments | Construction licenses-Permits |  |  | 2027-05-16 | 2027-05-18 | Not Started
Commercial | Authorities | Landscape Phase 2E & 2D Apartments | Mineral licenses-Excavation |  |  | 2027-08-08 | 2027-08-10 | Not Started
Formulas:
Overdue? = IF([Parent]="","",IF([Actual / Forecast Finish]="","",IF([Status]="completed","-",IF([Actual / Forecast Finish]>TODAY(),"No","Yes"))))
Overdue? = IF([Actual / Forecast Finish]="","",IF([Actual / Forecast Finish]>TODAY(),"No","Yes"))

## HPT
HPT | [5 empty] | 2027-03-17 02:24 | 2027-06-28 |  | 102.9
Phase | Trade | Parent | Task | Task Owner | Consultant | Baseline Finish | Actual / Forecast Finish | Status | Slippage (days) | Overdue? | Days to Finish/Delay | RAG | Notes | CurKey | OvdRank | ShowFlag | DesignRank
Park 226 | Authorities |  |  |  |  | 2025-11-25 | 2025-12-31 |  | 36 |  | -165 | Red |  | #REF! |  | 0
Park 226 | Authorities |  |  |  |  | 2025-11-25 | 2025-12-31 |  | 36 |  | -165 | Red |  |  |  | 0
Park 226 | Authorities | Permits Issuance - Park 226 | Ministerial decree |  |  | 2025-05-26 13:00 | 2025-07-21 13:00 | Completed | 56 | - | 0 | Red |  |  |  | 0
Park 226 | Authorities | Permits Issuance - Park 226 | Egyptian Institution for Construction Civil Liability Insurance |  |  | 2025-07-07 13:00 | 2025-09-01 13:00 | Completed | 56 | - | 0 | Red |  |  |  | 0
Park 226 | Authorities | Permits Issuance - Park 226 | Construction licenses |  |  | 2025-08-18 13:00 | 2025-09-24 | Completed | 36.4583 | - | 0 | Red |  |  |  | 0
Park 226 | Authorities | Permits Issuance - Park 226 | Mineral licenses |  |  | 2025-11-25 | 2025-12-01 | Completed | 6 | - | 0 | Red |  |  |  | 0
Park 226 | Authorities | Permits Issuance - Park 226 | Mineral licenses Duration |  |  | 2025-11-25 | 2025-12-31 | Completed | 36 | - | 0 | Red |  |  |  | 0
Park 226 | Authorities | Permits Issuance - Park 226 | Mineral licenses Renew |  |  |  |  | Not Started |  |  |  | Amber |  |  |  | 0
Park 226 | Masterplan |  |  |  |  | 2025-02-03 13:00 | 2025-02-03 13:00 |  | 0 |  | -495.4583 | Red |  | Park 226¦Masterplan |  | 0
Park 226 | Masterplan | Master Planning - Park 226 | Master Plan Concept |  |  | Done |  | Not Started |  |  |  | Amber |  |  |  | 0
Park 226 | Masterplan | Master Planning - Park 226 | HAP Review |  |  | Done |  | Not Started |  |  |  | Amber |  |  |  | 0
Park 226 | Masterplan | Master Planning - Park 226 | MD Approval 1st round |  |  | 2023-07-10 | 2023-07-10 | Completed | 0 | - | 0 | Red |  |  |  | 0
Park 226 | Masterplan | Master Planning - Park 226 | Master Plan Schematic Design |  |  | 2022-08-31 | 2022-08-31 | Completed | 0 | - | 0 | Red |  |  |  | 0
Park 226 | Masterplan | Master Planning - Park 226 | HAP Review |  |  | 2022-09-20 | 2022-09-20 | Completed | 0 | - | 0 | Red |  |  |  | 0
Park 226 | Masterplan | Master Planning - Park 226 | Master Plan Detailed Design (Staking and Levels) |  |  | 2023-02-01 | 2023-02-01 | Completed | 0 | - | 0 | Red |  |  |  | 0
Park 226 | Masterplan | Master Planning - Park 226 | HAP Review |  |  | 2023-02-09 | 2023-02-09 | Completed | 0 | - | 0 | Red |  |  |  | 0
Park 226 | Masterplan | Master Planning - Park 226 | MD Preparation |  |  | 2023-02-20 | 2023-02-20 | Completed | 0 | - | 0 | Red |  |  |  | 0
Park 226 | Masterplan | Master Planning - Park 226 | MD Approval 1st round |  |  | 2023-06-15 16:00 | 2023-06-15 16:00 | Completed | 0 | - | 0 | Red |  |  |  | 0
Park 226 | Masterplan | Master Planning - Park 226 | Master Plan Detailed Design (Staking and Levels) |  |  | 2023-11-16 | 2023-11-16 | Completed | 0 | - | 0 | Red |  |  |  | 0
Park 226 | Masterplan | Master Planning - Park 226 | HAP Review |  |  | 2023-11-30 | 2023-11-30 | Completed | 0 | - | 0 | Red |  |  |  | 0
Park 226 | Masterplan | Master Planning - Park 226 | MD Preparation |  |  | 2024-04-18 | 2024-04-18 | Completed | 0 | - | 0 | Red |  |  |  | 0
Park 226 | Masterplan | Master Planning - Park 226 | MD Approval Updated 2nd Round (mostkbal comments) |  |  | 2024-05-21 | 2024-05-21 | Completed | 0 | - | 0 | Red |  |  |  | 0
Park 226 | Masterplan | Master Planning - Park 226 | MD Approval Updated 2nd Round |  |  | 2025-02-03 13:00 | 2025-02-03 13:00 | Completed | 0 | - | 0 | Red |  |  |  | 0
Park 226 | Infrastructure |  |  |  |  | 2025-12-17 | 2025-12-15 |  | -2 |  | -181 | Red |  | Park 226¦Infrastructure |  | 0
Park 226 | Infrastructure | Infrastructure & roads - Park 226 | Concept Validation |  |  | Done |  | Not Started |  |  |  | Amber |  |  |  | 0
Park 226 | Infrastructure | Infrastructure & roads - Park 226 | Schematic Design |  |  | 2022-07-28 | 2022-07-28 | Completed | 0 | - | 0 | Red |  |  |  | 0
Park 226 | Infrastructure | Infrastructure & roads - Park 226 | HAP Review |  |  | 2022-08-11 | 2022-08-11 | Completed | 0 | - | 0 | Red |  |  |  | 0
Park 226 | Infrastructure | Infrastructure & roads - Park 226 | Detailed Design |  |  | 2023-09-18 | 2023-09-18 | Completed | 0 | - | 0 | Red |  |  |  | 0
Park 226 | Infrastructure | Infrastructure & roads - Park 226 | HAP Review |  |  | 2023-09-25 | 2023-09-25 | Completed | 0 | - | 0 | Red |  |  |  | 0
Park 226 | Infrastructure | Infrastructure & roads - Park 226 | Detailed Design Redesign |  |  | 2023-12-28 | 2023-12-28 | Completed | 0 | - | 0 | Red |  |  |  | 0
Park 226 | Infrastructure | Infrastructure & roads - Park 226 | HAP Review |  |  | 2024-01-04 | 2024-01-04 | Completed | 0 | - | 0 | Red |  |  |  | 0
Park 226 | Infrastructure | Infrastructure & roads - Park 226 | Mostakbal city approval |  |  | 2025-03-18 19:00 | 2025-03-18 19:00 | Completed | 0 | - | 0 | Red |  |  |  | 0
Park 226 | Infrastructure | Infrastructure & roads - Park 226 | Infrastructure IFP |  |  | 2025-10-02 | 2025-11-25 | Completed | 54 | - | 0 | Red |  |  |  | 0
Park 226 | Infrastructure | Infrastructure & roads - Park 226 | Mostakbal city approval (Rev.02 - Due to Kioshks) |  |  |  | 2025-12-15 | Completed |  | - | 0 | Red |  |  |  | 0
Park 226 | Infrastructure | Infrastructure & roads - Park 226 | Infrastructure IFT |  |  | 2025-11-02 | 2025-10-30 | Completed | -3 | - | 0 | Red |  |  |  | 0
Park 226 | Infrastructure | Infrastructure & roads - Park 226 | HAP Review |  |  | 2025-11-17 | 2025-12-10 | Completed | 23 | - | 0 | Red |  |  |  | 0
[6 empty] | 2026-01-25 | 2026-07-07 |  | 163 |  | 23 | Green |  | ¦ |  | 0
Park 226 | Landscape | External Works - Park 226 | Landscape Concept Review & validation |  |  | 2025-05-07 | 2025-05-07 | Completed | 0 | - | 0 | Red |  | Park 226¦Landscape |  | 0
Park 226 | Landscape | External Works - Park 226 | HAP Review |  |  | 2025-05-21 | 2025-05-21 | Completed | 0 | - | 0 | Red |  |  |  | 0
Park 226 | Landscape | External Works - Park 226 | Cost Plan |  |  | 2025-05-21 | 2025-05-21 | Completed | 0 | - | 0 | Red |  |  |  | 0
Park 226 | Landscape | External Works - Park 226 | Landscape Schematic Review & validation |  |  | 2025-06-04 | 2025-06-04 | Completed | 0 | - | 0 | Red |  |  |  | 0
Park 226 | Landscape | External Works - Park 226 | HAP Review |  |  | 2025-06-18 | 2025-06-18 | Completed | 0 | - | 0 | Red |  |  |  | 0
Park 226 | Landscape | External Works - Park 226 | Cost Plan |  |  | 2025-06-25 | 2025-06-25 | Completed | 0 | - | 0 | Red |  |  |  | 0
Park 226 | Landscape | External Works - Park 226 | Detailed Design 50% |  |  | 2025-07-23 | 2025-07-23 | Completed | 0 | - | 0 | Red |  |  |  | 0
Park 226 | Landscape | External Works - Park 226 | HAP Review |  |  | 2025-09-30 | 2025-10-01 | Completed | 1 | - | 0 | Red |  |  |  | 0
Park 226 | Landscape | External Works - Park 226 | Detailed Design 100% |  |  | 2025-10-29 | 2025-10-16 | Completed | -13 | - | 0 | Red |  |  |  | 0
Park 226 | Landscape | External Works - Park 226 | HAP Review |  |  | 2025-11-13 | 2025-11-04 | Completed | -9 | - | 0 | Red |  |  |  | 0
Park 226 | Landscape | External Works - Park 226 | Landscape IFT | Hoda / Ayman | ARDS | 2025-12-11 | 2026-06-30 | Inprogress | 201 | Yes | 16 | Amber |  |  | 1 | 1 | 1
Park 226 | Landscape | External Works - Park 226 | HAP Review | Hoda / Ayman |  | 2025-12-27 | 2026-07-07 | Not Started | 192 | No | 23 | Green |  |  |  | 0
Linear Park | Landscape |  |  |  |  | 2026-01-12 | 2026-02-25 |  | 44 |  | -109 | Red |  | Linear Park¦Landscape |  | 0
Linear Park | Landscape | Landscape - Linear Park | Receive Master Plan after review |  |  | 2025-04-23 |  | Not Started |  |  |  | Amber |  |  |  | 0
Linear Park | Landscape | Landscape - Linear Park | Landscape Concept Review & validation |  |  | 2025-05-07 | 2025-05-07 | Completed | 0 | - | 0 | Red |  |  |  | 0
Linear Park | Landscape | Landscape - Linear Park | HAP Review - 100% CD |  |  | 2025-05-21 | 2025-05-21 | Completed | 0 | - | 0 | Red |  |  |  | 0
Linear Park | Landscape | Landscape - Linear Park | Cost Plan - 100% CD |  |  | 2025-05-21 | 2025-05-21 | Completed | 0 | - | 0 | Red |  |  |  | 0
Linear Park | Landscape | Landscape - Linear Park | Landscape Schematic Review & validation |  | Sites | 2025-06-04 | 2025-06-04 | Completed | 0 | - | 0 | Red |  |  |  | 0
Linear Park | Landscape | Landscape - Linear Park | HAP Review - 100% SD |  |  | 2025-06-18 | 2025-06-18 | Completed | 0 | - | 0 | Red |  |  |  | 0
Linear Park | Landscape | Landscape - Linear Park | Cost Plan - 100% SD |  |  | 2025-06-25 | 2025-06-25 | Completed | 0 | - | 0 | Red |  |  |  | 0
Linear Park | Landscape | Landscape - Linear Park | 50% Detailed Design |  | Sites | 2025-07-23 | 2025-07-23 | Completed | 0 | - | 0 | Red |  |  |  | 0
Linear Park | Landscape | Landscape - Linear Park | HAP Review - 50% DD |  |  | 2025-08-06 | 2025-08-06 | Completed | 0 | - | 0 | Red |  |  |  | 0
Linear Park | Landscape | Landscape - Linear Park | 100% Detailed Design |  | Sites | 2025-10-12 | 2025-10-12 | Completed | 0 | - | 0 | Red |  |  |  | 0
Linear Park | Landscape | Landscape - Linear Park | HAP Review - 100% DD |  |  | 2025-10-27 | 2025-10-27 | Completed | 0 | - | 0 | Red |  |  |  | 0
Linear Park | Landscape | Landscape - Linear Park | Tender Package - (Phase.01) |  | Sites | 2025-11-23 | 2025-11-30 | Completed | 7 | - | 0 | Red |  |  |  | 0
Linear Park | Landscape | Landscape - Linear Park | HAP Review - TD (Phase.01) |  |  | 2025-12-08 | 2025-12-10 | Completed | 2 | - | 0 | Red |  |  |  | 0
Linear Park | Landscape | Landscape - Linear Park | Tender Package - (Phase.02) |  | Sites | 2026-01-04 | 2026-02-18 | Completed | 45 | - | 0 | Red |  |  |  | 0
Linear Park | Landscape | Landscape - Linear Park | HAP Review - TD (Phase.02) |  |  | 2026-01-12 | 2026-02-25 | Completed | 44 | - | 0 | Red |  |  |  | 0
Community Club | General |  |  |  |  | 2026-11-26 | 2027-01-03 |  | 38 |  | 203 | Green |  | Community Club¦General |  | 0
Community Club | General | Masterplan, Landscape, Infra, Blgds (Include ID) | 100% Concept Design |  |  | 2025-07-16 | 2025-07-16 | Completed | 0 | - | 0 | Red |  |  |  | 0
Community Club | General | Masterplan, Landscape, Infra, Blgds (Include ID) | HAP Review - 100% CD |  |  | 2025-07-23 | 2025-07-23 | Completed | 0 | - | 0 | Red |  |  |  | 0
Community Club | General | Masterplan, Landscape, Infra, Blgds (Include ID) | 100% Schematic Design |  |  | 2025-10-08 | 2025-10-08 | Completed | 0 | - | 0 | Red |  |  |  | 0
Community Club | General | Masterplan, Landscape, Infra, Blgds (Include ID) | HAP Review - 100% SD |  |  | 2025-10-15 | 2025-10-21 | Completed | 6 | - | 0 | Red |  |  |  | 0
Community Club | General | Masterplan, Landscape, Infra, Blgds (Include ID) | Cost Plan - 100% SD |  |  | 2025-10-22 | 2025-11-24 | Completed | 33 | - | 0 | Red |  |  |  | 0
Ph.01 Community Club | General |  |  |  |  | 2025-12-31 | 2026-07-12 |  | 193 |  | 28 | Green |  | Ph.01 Community Club¦General |  | 0
Ph.01 Community Club | General | Phase 01 (Playground and Changing Room) | HAP Review and Consultant Validation |  | GDG | 2025-11-05 | 2025-11-25 | Completed | 20 | - | 0 | Red |  |  |  | 0
Ph.01 Community Club | General | Phase 01 (Playground and Changing Room) | 50% Detailed Design |  | GDG | 2025-11-19 | 2025-11-10 | Completed | -9 | - | 0 | Red |  |  |  | 0
Ph.01 Community Club | General | Phase 01 (Playground and Changing Room) | HAP Review - 50% DD |  |  | 2025-11-26 | 2025-11-10 | Completed | -16 | - | 0 | Red |  |  |  | 0
Ph.01 Community Club | General | Phase 01 (Playground and Changing Room) | 100% Detailed Design |  | GDG | 2025-12-10 | 2026-01-21 | Completed | 42 | - | 0 | Red |  |  |  | 0
Ph.01 Community Club | General | Phase 01 (Playground and Changing Room) | Permits Drawings |  | GDG | 2025-12-10 | 2026-01-06 | Completed | 27 | - | 0 | Red |  |  |  | 0
Ph.01 Community Club | General | Phase 01 (Playground and Changing Room) | HAP Review - 100% DD |  |  | 2025-12-17 | 2026-02-01 | Completed | 46 | - | 0 | Red |  |  |  | 0
Ph.01 Community Club | General | Phase 01 (Playground and Changing Room) | Cost Plan - 100% DD | Nour / Noha |  | 2025-12-24 | 2026-07-12 | Inprogress | 200 | No | 28 | Green |  |  |  | 0
Ph.01 Community Club | General | Phase 01 (Playground and Changing Room) | Tender Package |  | GDG | 2025-12-24 | 2026-03-18 | Completed | 84 | - | 0 | Red |  |  |  | 0
Ph.01 Community Club | General | Phase 01 (Playground and Changing Room) | HAP Review - TD |  |  | 2025-12-31 | 2026-04-08 | Completed | 98 | - | 0 | Red |  |  |  | 0
Ph.01 Community Club | Authorities |  |  |  |  | 2026-04-01 | 2026-07-22 |  | 112 |  | 38 | Green |  | Ph.01 Community Club¦Authorities |  | 0
Ph.01 Community Club | Authorities | Permits Issuance - Ph.01 Community Club | Ministerial Decree - Club | Afifi |  |  | 2026-03-30 | Completed |  | - | 0 | Red |  |  |  | 0
Ph.01 Community Club | Authorities | Permits Issuance - Ph.01 Community Club | Construction licenses | Afifi |  | 2026-01-07 | 2026-04-29 | Completed | 112 | - | 0 | Red |  |  |  | 0
Ph.02 Community Club | General | Permits Issuance - Ph.01 Community Club | Mineral licenses | Afifi |  | 2026-04-01 | 2026-07-22 | Inprogress | 112 | No | 38 | Green |  | Ph.02 Community Club¦General |  | 0
Ph.02 Community Club | General |  |  |  |  | 2026-04-09 | 2026-08-16 |  | 129 |  | 63 | Green |  |  |  | 0
Ph.02 Community Club | General | Phase 02 Community Club | 100% Concept Design - Gym Building | Osama / Ramadan | KH Studio | 2026-01-29 | 2026-01-11 | Completed | -18 | - | 0 | Red |  |  |  | 0
Ph.02 Community Club | General | Phase 02 Community Club | HAP Review - 100% CD Gym Building | Osama / Ramadan |  | 2026-02-05 | 2026-01-27 | Completed | -9 | - | 0 | Red |  |  |  | 0
Ph.02 Community Club | General | Phase 02 Community Club | 100% Schematic Design - Gym Building | Osama / Ramadan | KH Studio | 2026-01-29 | 2026-05-24 | Completed | 115 | - | 0 | Red |  |  |  | 0
Ph.02 Community Club | General | Phase 02 Community Club | HAP Review - 100% SD Gym Building | Osama / Ramadan |  | 2026-02-05 | 2026-05-25 | Completed | 109 | - | 0 | Red |  |  |  | 0
Ph.02 Community Club | General | Phase 02 Community Club | 50% Detailed Design | Osama / Ramadan | GDG | 2026-01-29 | 2026-04-30 | Completed | 91 | - | 0 | Red |  |  |  | 0
Ph.02 Community Club | General | Phase 02 Community Club | HAP Review - 50% DD | Osama / Ramadan |  | 2026-02-05 | 2026-05-19 | Completed | 103 | - | 0 | Red |  |  |  | 0
Ph.02 Community Club | General | Phase 02 Community Club | 100% Detailed Design | Osama / Ramadan | GDG | 2026-02-26 | 2026-07-05 | Inprogress | 129 | No | 21 | Amber |  |  |  | 0
Ph.02 Community Club | General | Phase 02 Community Club | HAP Review - 100% DD | Osama / Ramadan |  | 2026-03-05 | 2026-07-19 | Not Started | 136 | No | 35 | Green |  |  |  | 0
Ph.02 Community Club | General | Phase 02 Community Club | Cost Plan - 100% DD | Osama / Ramadan |  | 2026-03-12 | 2026-07-26 | Not Started | 136 | No | 42 | Green |  |  |  | 0
Ph.02 Community Club | General | Phase 02 Community Club | Permits Drawings | Osama / Ramadan | GDG | 2026-03-19 | 2026-08-02 | Not Started | 136 | No | 49 | Green |  |  |  | 0
Ph.02 Community Club | General | Phase 02 Community Club | Tender Package | Osama / Ramadan | GDG | 2026-03-19 | 2026-08-02 | Not Started | 136 | No | 49 | Green |  |  |  | 0
Ph.02 Community Club | General | Phase 02 Community Club | HAP Review - TD | Osama / Ramadan |  | 2026-03-26 | 2026-08-16 | Not Started | 143 | No | 63 | Green |  |  |  | 0
Ph.02 Community Club | Authorities |  |  |  |  | 2026-11-26 | 2027-01-03 |  | 38 |  | 203 | Green |  | Ph.02 Community Club¦Authorities |  | 0
Ph.02 Community Club | Authorities | Permits Issuance Ph.02 Community Club | Ministerial decree - Club | Afifi |  | 2026-07-09 | 2026-03-30 | Completed | -101 | - | 0 | Red |  |  |  | 0
Ph.02 Community Club | Authorities | Permits Issuance Ph.02 Community Club | Egyptian Institution for Construction Civil Liability Insurance | Afifi |  | 2026-08-06 | 2026-09-13 | Not Started | 38 | No | 91 | Green |  |  |  | 0
Ph.02 Community Club | Authorities | Permits Issuance Ph.02 Community Club | Construction licenses | Afifi |  | 2026-09-03 | 2026-10-11 | Not Started | 38 | No | 119 | Green |  |  |  | 0
Ph.02 Community Club | Authorities | Permits Issuance Ph.02 Community Club | Mineral licenses | Afifi |  | 2026-11-26 | 2027-01-03 | Not Started | 38 | No | 203 | Green |  |  |  | 0
Commercial | Buildings |  |  |  |  | 2026-10-07 02:24 | 2027-01-11 |  | 95.9 |  | 211 | Green |  | Commercial¦Buildings |  | 0
Commercial | Buildings | Buildings - Commercial | RFP | Mostafa Abdel-Aziz |  | 2025-11-17 | 2025-11-17 | Completed | 0 | - | 0 | Red |  |  |  | 0
Commercial | Buildings | Buildings - Commercial | Price Negotiations and Contract | Mostafa Abdel-Aziz |  | 2025-12-24 02:24 | 2025-12-24 02:24 | Completed | 0 | - | 0 | Red |  |  |  | 0
Commercial | Buildings | Buildings - Commercial | Kick-off | Mostafa Abdel-Aziz |  | 2025-12-24 02:24 | 2025-12-24 02:24 | Completed | 0 | - | 0 | Red |  |  |  | 0
Commercial | Buildings | Buildings - Commercial | Pre-Concept Design | Mostafa Abdel-Aziz | Raeef Fahmy | 2026-01-14 02:24 | 2026-01-14 02:24 | Completed | 0 | - | 0 | Red |  |  |  | 0
Commercial | Buildings | Buildings - Commercial | HAP Review - PC | Mostafa Abdel-Aziz |  | 2026-01-28 02:24 | 2026-02-15 | Completed | 17.9 | - | 0 | Red |  |  |  | 0
Commercial | Buildings | Buildings - Commercial | 50% Concept Design | Mostafa Abdel-Aziz | Raeef Fahmy | 2026-02-18 02:24 | 2026-04-07 | Completed | 47.9 | - | 0 | Red |  |  |  | 0
Commercial | Buildings | Buildings - Commercial | HAP Review - 50% CD | Mostafa Abdel-Aziz |  | 2026-03-04 02:24 | 2026-04-14 | Completed | 40.9 | - | 0 | Red |  |  |  | 0
Commercial | Buildings | Buildings - Commercial | 100% Concept Design | Mostafa Abdel-Aziz | Raeef Fahmy | 2026-03-18 02:24 | 2026-07-05 | Inprogress | 108.9 | No | 21 | Amber |  |  |  | 0
Commercial | Buildings | Buildings - Commercial | HAP Review - 100% CD | Mostafa Abdel-Aziz |  | 2026-04-01 02:24 | 2026-07-12 | Not Started | 101.9 | No | 28 | Green |  |  |  | 0
Commercial | Buildings | Buildings - Commercial | Colored Plans (Marketing Material) | Mostafa Abdel-Aziz |  | 2026-04-15 02:24 | 2026-06-08 | Completed | 53.9 | - | 0 | Red |  |  |  | 0
Commercial | Buildings | Buildings - Commercial | Plans Annexes (Marketing Materials) | Mostafa Abdel-Aziz |  | 2026-04-15 02:24 | 2026-06-08 | Completed | 53.9 | - | 0 | Red |  |  |  | 0
Commercial | Buildings | Buildings - Commercial | 50% Schematic Design |  | Raeef Fahmy | 2026-04-22 02:24 | 2026-08-03 | Not Started | 102.9 | No | 50 | Green |  |  |  | 0
Commercial | Buildings | Buildings - Commercial | HAP Review - 50% SD |  |  | 2026-05-06 02:24 | 2026-08-17 | Not Started | 102.9 | No | 64 | Green |  |  |  | 0
Commercial | Buildings | Buildings - Commercial | 100% Schematic Design |  | Raeef Fahmy | 2026-05-27 02:24 | 2026-09-07 | Not Started | 102.9 | No | 85 | Green |  |  |  | 0
Commercial | Buildings | Buildings - Commercial | HAP Review - 100% SD |  |  | 2026-06-10 02:24 | 2026-09-21 | Not Started | 102.9 | No | 99 | Green |  |  |  | 0
Commercial | Buildings | Buildings - Commercial | Cost Plan - 100% SD |  |  | 2026-06-17 02:24 | 2026-09-28 | Not Started | 102.9 | No | 106 | Green |  |  |  | 0
Commercial | Buildings | Buildings - Commercial | 50% Detailed Design |  | Raeef Fahmy | 2026-07-15 02:24 | 2026-10-26 | Not Started | 102.9 | No | 134 | Green |  |  |  | 0
Commercial | Buildings | Buildings - Commercial | HAP Review - 50% DD |  |  | 2026-07-29 02:24 | 2026-11-09 | Not Started | 102.9 | No | 148 | Green |  |  |  | 0
Commercial | Buildings | Buildings - Commercial | 100% Detailed Design |  | Raeef Fahmy | 2026-08-19 02:24 | 2026-11-23 | Not Started | 95.9 | No | 162 | Green |  |  |  | 0
Commercial | Buildings | Buildings - Commercial | HAP Review - 100% DD |  |  | 2026-09-02 02:24 | 2026-12-07 | Not Started | 95.9 | No | 176 | Green |  |  |  | 0
Commercial | Buildings | Buildings - Commercial | Cost Plan - 100% DD |  |  | 2026-09-09 02:24 | 2026-12-14 | Not Started | 95.9 | No | 183 | Green |  |  |  | 0
Commercial | Buildings | Buildings - Commercial | Permits Drawings |  | Raeef Fahmy | 2026-08-19 02:24 | 2026-11-23 | Not Started | 95.9 | No | 162 | Green |  |  |  | 0
Commercial | Buildings | Buildings - Commercial | HAP Review - PD |  |  | 2026-09-02 02:24 | 2026-12-07 | Not Started | 95.9 | No | 176 | Green |  |  |  | 0
Commercial | Buildings | Buildings - Commercial | Tender Package |  | Raeef Fahmy | 2026-09-23 02:24 | 2026-12-28 | Not Started | 95.9 | No | 197 | Green |  |  |  | 0
Commercial | Buildings | Buildings - Commercial | HAP Review - TD |  |  | 2026-10-07 02:24 | 2027-01-11 | Not Started | 95.9 | No | 211 | Green |  |  |  | 0
Commercial | Masterplan |  |  |  |  | 2026-09-09 02:24 | 2026-12-21 |  | 102.9 |  | 190 | Green |  | Commercial¦Masterplan |  | 0
Commercial | Masterplan | Master Plan - Commercial | Pre-Concept Design | Mostafa Abdel-Aziz | Raeef Fahmy | 2026-01-14 02:24 | 2026-01-14 02:24 | Completed | 0 | - | 0 | Red |  |  |  | 0
Commercial | Masterplan | Master Plan - Commercial | HAP Review - PC | Mostafa Abdel-Aziz |  | 2026-01-28 02:24 | 2026-02-15 | Completed | 17.9 | - | 0 | Red |  |  |  | 0
Commercial | Masterplan | Master Plan - Commercial | 50% Concept Design | Mostafa Abdel-Aziz | Raeef Fahmy | 2026-02-18 02:24 |  | Inprogress |  |  |  | Amber |  |  |  | 0
Commercial | Masterplan | Master Plan - Commercial | HAP Review - 50% CD | Mostafa Abdel-Aziz |  | 2026-03-04 02:24 |  | Not Started |  |  |  | Amber |  |  |  | 0
Commercial | Masterplan | Master Plan - Commercial | 100% Concept Design | Mostafa Abdel-Aziz | Raeef Fahmy | 2026-03-18 02:24 | 2026-07-05 | Inprogress | 108.9 | No | 21 | Amber |  |  |  | 0
Commercial | Masterplan | Master Plan - Commercial | HAP Review - 100% CD | Mostafa Abdel-Aziz |  | 2026-04-01 02:24 | 2026-07-12 | Not Started | 101.9 | No | 28 | Green |  |  |  | 0
Commercial | Masterplan | Master Plan - Commercial | MP Annexes (Marketing Materials) | Mostafa Abdel-Aziz |  | 2026-04-15 02:24 | 2026-06-08 | Completed | 53.9 | - | 0 | Red |  |  |  | 0
Commercial | Masterplan | Master Plan - Commercial | 100% Schematic Design |  | Raeef Fahmy | 2026-05-13 02:24 | 2026-08-24 | Not Started | 102.9 | No | 71 | Green |  |  |  | 0
Commercial | Masterplan | Master Plan - Commercial | HAP Review - 100% SD |  |  | 2026-05-27 02:24 | 2026-09-07 | Not Started | 102.9 | No | 85 | Green |  |  |  | 0
Commercial | Masterplan | Master Plan - Commercial | Ministerial decree Package |  |  | 2026-05-27 02:24 | 2026-09-07 | Not Started | 102.9 | No | 85 | Green |  |  |  | 0
Commercial | Masterplan | Master Plan - Commercial | 50% Detailed Design |  | Raeef Fahmy | 2026-06-17 02:24 | 2026-09-28 | Not Started | 102.9 | No | 106 | Green |  |  |  | 0
Commercial | Masterplan | Master Plan - Commercial | HAP Review - 50% DD |  |  | 2026-07-01 02:24 | 2026-10-12 | Not Started | 102.9 | No | 120 | Green |  |  |  | 0
Commercial | Masterplan | Master Plan - Commercial | 100% Detailed Design |  | Raeef Fahmy | 2026-07-22 02:24 | 2026-11-02 | Not Started | 102.9 | No | 141 | Green |  |  |  | 0
Commercial | Masterplan | Master Plan - Commercial | HAP Review - 100% DD |  |  | 2026-08-05 02:24 | 2026-11-16 | Not Started | 102.9 | No | 155 | Green |  |  |  | 0
Commercial | Masterplan | Master Plan - Commercial | Tender Package |  | Raeef Fahmy | 2026-08-26 02:24 | 2026-12-07 | Not Started | 102.9 | No | 176 | Green |  |  |  | 0
Commercial | Masterplan | Master Plan - Commercial | HAP Review - TD |  |  | 2026-09-09 02:24 | 2026-12-21 | Not Started | 102.9 | No | 190 | Green |  |  |  | 0
Commercial | Landscape |  |  |  |  | 2027-01-06 02:24 | 2027-02-14 |  | 38.9 |  | 245 | Green |  | Commercial¦Landscape |  | 0
Commercial | Landscape | Landscape - Commercial | RFP | Mostafa Abdel-Aziz |  | 2025-11-24 | 2025-11-24 | Completed | 0 | - | 0 | Red |  |  |  | 0
Commercial | Landscape | Landscape - Commercial | Tender to assign Consultant |  |  | 2025-12-22 | 2025-12-22 | Completed | 0 | - | 0 | Red |  |  |  | 0
Commercial | Landscape | Landscape - Commercial | Pre-Concept Design | Mostafa Abdel-Aziz |  | 2026-02-25 02:24 |  | Inprogress |  |  |  | Amber |  |  |  | 0
Commercial | Landscape | Landscape - Commercial | HAP Review - PC | Mostafa Abdel-Aziz |  | 2026-03-11 02:24 |  | Not Started |  |  |  | Amber |  |  |  | 0
Commercial | Landscape | Landscape - Commercial | 50% Concept Design | Mostafa Abdel-Aziz | Raeef Fahmy | 2026-04-08 02:24 | 2026-04-07 | Completed | -1.1 | - | 0 | Red |  |  |  | 0
Commercial | Landscape | Landscape - Commercial | HAP Review - 50% CD | Mostafa Abdel-Aziz |  | 2026-04-22 02:24 | 2026-04-14 | Completed | -8.1 | - | 0 | Red |  |  |  | 0
Commercial | Landscape | Landscape - Commercial | Colored MP (Marketing Materials) | Mostafa Abdel-Aziz |  | 2026-05-06 02:24 | 2026-05-03 | Completed | -3.1 | - | 0 | Red |  |  |  | 0
Commercial | Landscape | Landscape - Commercial | 100% Concept Design | Mostafa Abdel-Aziz |  | 2026-05-20 02:24 | 2026-07-05 | Inprogress | 45.9 | No | 21 | Amber |  |  |  | 0
Commercial | Landscape | Landscape - Commercial | HAP Review - 100% CD | Mostafa Abdel-Aziz |  | 2026-06-03 02:24 | 2026-07-12 | Not Started | 38.9 | No | 28 | Green |  |  |  | 0
Commercial | Landscape | Landscape - Commercial | 50% Schematic Design |  | Raeef Fahmy | 2026-07-01 02:24 | 2026-08-09 | Not Started | 38.9 | No | 56 | Green |  |  |  | 0
Commercial | Landscape | Landscape - Commercial | HAP Review - 50% SD |  |  | 2026-07-15 02:24 | 2026-08-23 | Not Started | 38.9 | No | 70 | Green |  |  |  | 0
Commercial | Landscape | Landscape - Commercial | 100% Schematic Design |  | Raeef Fahmy | 2026-08-12 02:24 | 2026-09-20 | Not Started | 38.9 | No | 98 | Green |  |  |  | 0
Commercial | Landscape | Landscape - Commercial | HAP Review - 100% SD |  |  | 2026-08-26 02:24 | 2026-10-04 | Not Started | 38.9 | No | 112 | Green |  |  |  | 0
Commercial | Landscape | Landscape - Commercial | Cost Plan - 100% SD |  |  | 2026-09-02 02:24 | 2026-10-11 | Not Started | 38.9 | No | 119 | Green |  |  |  | 0
Commercial | Landscape | Landscape - Commercial | 50% Detailed Design |  | Raeef Fahmy | 2026-09-30 02:24 | 2026-11-08 | Not Started | 38.9 | No | 147 | Green |  |  |  | 0
Commercial | Landscape | Landscape - Commercial | HAP Review - 50% DD |  |  | 2026-10-14 02:24 | 2026-11-22 | Not Started | 38.9 | No | 161 | Green |  |  |  | 0
Commercial | Landscape | Landscape - Commercial | 100% Detailed Design |  | Raeef Fahmy | 2026-11-11 02:24 | 2026-12-20 | Not Started | 38.9 | No | 189 | Green |  |  |  | 0
Commercial | Landscape | Landscape - Commercial | HAP Review - 100% DD |  |  | 2026-11-25 02:24 | 2027-01-03 | Not Started | 38.9 | No | 203 | Green |  |  |  | 0
Commercial | Landscape | Landscape - Commercial | Cost Plan - 100% DD |  |  | 2026-12-02 02:24 | 2027-01-10 | Not Started | 38.9 | No | 210 | Green |  |  |  | 0
Commercial | Landscape | Landscape - Commercial | Tender Package |  | Raeef Fahmy | 2026-12-23 02:24 | 2027-01-31 | Not Started | 38.9 | No | 231 | Green |  |  |  | 0
|  | Landscape - Commercial | HAP Review - TD |  |  | 2027-01-06 02:24 | 2027-02-14 | Not Started | 38.9 | No | 245 | Green |  | ¦ |  | 0
Commercial | Authorities |  |  |  |  | 2027-03-17 02:24 | 2027-06-28 |  | 102.9 |  | 379 | Green |  | Commercial¦Authorities |  | 0
Commercial | Authorities | Authorities Issuance - Commercial | Ministerial decree-MIDAR | Afifi |  | 2026-07-22 02:24 | 2026-11-02 | Not Started | 102.9 | No | 141 | Green |  |  |  | 0
Commercial | Authorities | Authorities Issuance - Commercial | Ministerial decree NUCA | Afifi |  | 2026-10-14 02:24 | 2027-01-25 | Not Started | 102.9 | No | 225 | Green |  |  |  | 0
Commercial | Authorities | Authorities Issuance - Commercial | Egyptian Institution for Construction Civil Liability Insurance & Civil Defense | Afifi |  | 2026-11-25 02:24 | 2027-03-08 | Not Started | 102.9 | No | 267 | Green |  |  |  | 0
Commercial | Authorities | Authorities Issuance - Commercial | Construction licenses-Permits | Afifi |  | 2027-01-06 02:24 | 2027-04-19 | Not Started | 102.9 | No | 309 | Green |  |  |  | 0
Commercial | Authorities | Authorities Issuance - Commercial | Mineral licenses-Excavation | Afifi |  | 2027-03-17 02:24 | 2027-06-28 | Not Started | 102.9 | No | 379 | Green |  |  |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
Formulas:
Overdue? = IF([Parent]="","",IF([Actual / Forecast Finish]="","",IF([Status]="completed","-",IF([Actual / Forecast Finish]>TODAY(),"No","Yes"))))
Overdue? = IF([Actual / Forecast Finish]="","",IF([Actual / Forecast Finish]>TODAY(),"No","Yes"))

## CRI
CRI | [5 empty] | 2027-05-04 | 2027-05-04 |  | 0
Phase | Trade | Parent | Task | Task Owner | Consultant | Baseline Finish | Actual / Forecast Finish | Status | Slippage (days) | Overdue? | Days to Finish/Delay | RAG | Notes | CurKey | OvdRank | ShowFlag | DesignRank
Ph.01&02 | Buildings |  |  |  |  | 2025-10-15 12:00 | 2024-06-17 |  | -485.5 |  | -727 | Red |  | #REF! |  | 0
Ph.01&02 | Buildings | Villas All 6 types - Phase #1&2 | Concept validation |  |  | 2024-01-15 | 2024-01-15 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph.01&02 | Buildings | Villas All 6 types - Phase #1&2 | HAP Review |  |  | 2024-01-29 | 2024-01-29 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph.01&02 | Buildings | Villas All 6 types - Phase #1&2 | Schematic Design |  |  | 2024-02-26 | 2024-02-26 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph.01&02 | Buildings | Villas All 6 types - Phase #1&2 | HAP Review |  |  | 2024-03-11 | 2024-03-11 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph.01&02 | Buildings | Villas All 6 types - Phase #1&2 | Cost Plan for Schematic Design |  |  | 2024-03-11 | 2024-03-11 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph.01&02 | Buildings | Villas All 6 types - Phase #1&2 | Detailed Design 50% |  |  | 2024-04-08 | 2024-04-08 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph.01&02 | Buildings | Villas All 6 types - Phase #1&2 | HAP Review |  |  | 2024-04-22 | 2024-04-22 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph.01&02 | Buildings | Villas All 6 types - Phase #1&2 | Detailed Design 100% |  |  | 2024-05-06 | 2024-05-06 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph.01&02 | Buildings | Villas All 6 types - Phase #1&2 | HAP Review |  |  | 2024-05-20 | 2024-05-20 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph.01&02 | Buildings | Villas All 6 types - Phase #1&2 | Cost Plan for Detailed Design |  |  | 2024-05-20 | 2024-05-20 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph.01&02 | Buildings | Villas All 6 types - Phase #1&2 | Permit Drawings & Documents (IFP, IFDL, IFCD) |  |  | 2024-04-22 | 2024-04-22 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph.01&02 | Buildings | Villas All 6 types - Phase #1&2 | Tender Package |  |  | 2024-06-03 | 2024-06-03 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph.01&02 | Buildings | Villas All 6 types - Phase #1&2 | HAP Review |  |  | 2024-06-17 | 2024-06-17 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph.01&02 | Authorities |  |  |  |  | 2025-10-15 12:00 | 2026-03-18 |  | 153.5 |  | -88 | Red |  | Ph.01&02¦Authorities |  | 0
Ph.01&02 | Authorities | Permits Issuance | Ministerial decree |  |  | 2024-10-03 12:00 | 2025-04-16 12:00 | Completed | 195 | - | 0 | Red |  |  |  | 0
Ph.01&02 | Authorities | Permits Issuance | Egyptian Institution for Construction Civil Liability Insurance |  |  | 2024-11-18 | 2025-06-01 | Completed | 195 | - | 0 | Red |  |  |  | 0
Ph.01&02 | Authorities | Permits Issuance | Construction licenses |  |  | 2025-01-02 12:00 | 2025-07-16 12:00 | Completed | 195 | - | 0 | Red |  |  |  | 0
Ph.01&02 | Authorities | Permits Issuance | Mineral licenses |  |  | 2025-10-15 12:00 | 2025-12-01 | Completed | 46.5 | - | 0 | Red |  |  |  | 0
Ph.01&02 | Authorities | Permits Issuance | Mineral licenses Duration |  |  | 2025-10-15 12:00 | 2025-12-31 | Completed | 76.5 | - | 0 | Red |  |  |  | 0
Ph.01&02 | Authorities | Permits Issuance | Mineral licenses Renew |  |  |  | 2026-03-18 | Completed |  | - | 0 | Red |  |  |  | 0
Ph.01&02 | Masterplan |  |  |  |  | 2024-08-11 21:00 | 2024-08-11 21:00 |  | 0 |  | -671.125 | Red |  | Ph.01&02¦Masterplan |  | 0
Ph.01&02 | Masterplan | Master Plan Schematic Design Validation | HAP Review |  |  | 2024-08-18 21:00 | 2024-08-18 21:00 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph.01&02 | Masterplan | Master Plan Schematic Design Validation | Master Plan Detailed Design 50% |  |  | 2024-09-01 21:00 | 2024-09-01 21:00 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph.01&02 | Masterplan | Master Plan Schematic Design Validation | HAP Review |  |  | 2024-09-15 21:00 | 2024-09-15 21:00 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph.01&02 | Masterplan | Master Plan Schematic Design Validation | Master Plan Detailed Design 100% |  |  | 2024-10-13 21:00 | 2024-10-13 21:00 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph.01&02 | Masterplan | Master Plan Schematic Design Validation | HAP Review |  |  | 2024-10-27 21:00 | 2024-10-27 21:00 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph.01&02 | Masterplan | Master Plan Schematic Design Validation | IFT |  |  | 2024-11-10 21:00 | 2024-11-10 21:00 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph.01&02 | Masterplan | Master Plan Schematic Design Validation | HAP Review |  |  | 2024-11-24 21:00 | 2024-11-24 21:00 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph.01&02 | Masterplan | Master Plan Schematic Design Validation | IFC Submission |  |  | 2024-12-08 21:00 | 2024-12-08 21:00 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph.03&04 | Buildings |  |  |  |  | 2026-04-20 | 2026-10-19 |  | 182 |  | 127 | Green |  | Ph.03&04¦Buildings |  | 0
Ph.03&04 | Buildings | Villas All 7 types-Phase#03&4 | Concept validation |  | Archimid | 2025-03-12 | 2025-04-14 | Completed | 33 | - | 0 | Red |  |  |  | 0
Ph.03&04 | Buildings | Villas All 7 types-Phase#03&4 | HAP Review |  |  | 2025-03-26 | 2025-05-01 | Completed | 36 | - | 0 | Red |  |  |  | 0
Ph.03&04 | Buildings | Villas All 7 types-Phase#03&4 | Schematic Design |  | Archimid | 2025-04-23 | 2025-05-31 | Completed | 38 | - | 0 | Red |  |  |  | 0
Ph.03&04 | Buildings | Villas All 7 types-Phase#03&4 | HAP Review |  |  | 2025-05-07 | 2025-06-14 | Completed | 38 | - | 0 | Red |  |  |  | 0
Ph.03&04 | Buildings | Villas All 7 types-Phase#03&4 | Cost Plan for Schematic Design |  |  | 2025-05-07 | 2025-06-14 | Completed | 38 | - | 0 | Red |  |  |  | 0
Ph.03&04 | Buildings | Villas All 7 types-Phase#03&4 | Detailed Design 50% |  | Archimid | 2025-06-04 | 2025-07-14 | Completed | 40 | - | 0 | Red |  |  |  | 0
Ph.03&04 | Buildings | Villas All 7 types-Phase#03&4 | HAP Review |  |  | 2025-06-18 | 2025-07-30 | Completed | 42 | - | 0 | Red |  |  |  | 0
Ph.03&04 | Buildings | Villas All 7 types-Phase#03&4 | Detailed Design 100% |  | Archimid | 2025-07-02 | 2025-09-01 | Completed | 61 | - | 0 | Red |  |  |  | 0
Ph.03&04 | Buildings | Villas All 7 types-Phase#03&4 | HAP Review |  |  | 2025-07-16 | 2025-09-14 | Completed | 60 | - | 0 | Red |  |  |  | 0
Ph.03&04 | Buildings | Villas All 7 types-Phase#03&4 | Cost Plan for Detailed Design |  |  | 2025-07-16 | 2025-09-15 | Completed | 61 | - | 0 | Red |  |  |  | 0
Ph.03&04 | Buildings | Villas All 7 types-Phase#03&4 | Tender Package |  | Archimid | 2025-07-30 | 2026-04-23 | Completed | 267 | - | 0 | Red |  |  |  | 0
Ph.03&04 | Buildings | Villas All 7 types-Phase#03&4 | HAP Review |  |  | 2025-10-12 | 2026-05-04 | Completed | 204 | - | 0 | Red |  |  |  | 0
Ph.03&04 | Buildings | Villas All 7 types-Phase#03&4 | Permits DWGs |  |  | 2025-07-30 | 2026-02-26 | Completed | 211 | - | 0 | Red |  |  |  | 0
Ph.03&04 | Buildings | Villas All 7 types-Phase#03&4 | HAP Review |  |  | 2025-10-12 | 2026-03-15 | Completed | 154 | - | 0 | Red |  |  |  | 0
Ph.03&04 | Authorities |  |  |  |  | 2026-04-20 | 2026-07-22 |  | 93 |  | 38 | Green |  | Ph.03&04¦Authorities |  | 0
Ph.03&04 | Authorities | Permits Issuance - Ph.03, 04 | Ministerial decree |  |  | 2025-10-20 | 2026-03-10 | Completed | 141 | - | 0 | Red |  |  |  | 0
Ph.03&04 | Authorities | Permits Issuance - Ph.03, 04 | Egyptian Institution for Construction Deccenial Liability Insurance |  |  | 2025-12-04 12:00 | 2026-04-12 | Completed | 128.5 | - | 0 | Red |  |  |  | 0
Ph.03&04 | Authorities | Permits Issuance - Ph.03, 04 | Construction licenses |  |  | 2026-01-19 | 2026-04-29 | Completed | 100 | - | 0 | Red |  |  |  | 0
Ph.03&04 | Authorities | Permits Issuance - Ph.03, 04 | Mineral licenses |  |  | 2026-04-20 | 2026-07-22 | Inprogress | 93 | No | 38 | Green |  |  |  | 0
Ph. 01, 02, 03 & 04 | Fit-out |  |  |  |  | 2026-10-29 | 2026-12-07 |  | 39 |  | 176 | Green |  | Ph. 01, 02, 03 & 04¦Fit-out |  | 0
Ph. 01, 02, 03 & 04 | Fit-out | Interior Ph. 01, 02, 03 & 04 | 100% Schematic Design | Osama / Lina | Archimid | 2026-05-14 | 2026-06-04 | Completed | 21 | - | 0 | Red |  |  |  | 0
Ph. 01, 02, 03 & 04 | Fit-out | Interior Ph. 01, 02, 03 & 04 | HAP Review - 100% SD | Osama / Lina |  | 2026-05-21 | 2026-06-29 | Inprogress | 39 | Yes | 15 | Amber |  |  | 1 | 1 | 1
Ph. 01, 02, 03 & 04 | Fit-out | Interior Ph. 01, 02, 03 & 04 | 100% Detailed Design | Osama / Lina | Archimid | 2026-06-04 | 2026-07-13 | Not Started | 39 | No | 29 | Green |  |  |  | 0
Ph. 01, 02, 03 & 04 | Fit-out | Interior Ph. 01, 02, 03 & 04 | HAP Review - 100% DD | Osama / Lina |  | 2026-06-18 | 2026-07-27 | Not Started | 39 | No | 43 | Green |  |  |  | 0
Ph. 01, 02, 03 & 04 | Fit-out | Interior Ph. 01, 02, 03 & 04 | Tender Package | Osama / Lina | Archimid | 2026-07-02 | 2026-08-10 | Not Started | 39 | No | 57 | Green |  |  |  | 0
Ph. 01, 02, 03 & 04 | Fit-out | Interior Ph. 01, 02, 03 & 04 | HAP Review - TD | Osama / Lina |  | 2026-07-09 | 2026-08-17 | Not Started | 39 | No | 64 | Green |  |  |  | 0
Ph. 01, 02, 03 & 04 | Masterplan |  |  |  |  | 2025-09-07 21:36 | 2025-09-07 21:36 |  | 0 |  | -279.1 | Red |  | Ph. 01, 02, 03 & 04¦Masterplan |  | 0
Ph. 01, 02, 03 & 04 | Masterplan | Master Planning | Master Plan Schematic Design Validation | Osama / Lina |  | 2025-05-25 21:36 | 2025-05-25 21:36 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph. 01, 02, 03 & 04 | Masterplan | Master Planning | HAP Review | Osama / Lina |  | 2025-06-01 21:36 | 2025-06-01 21:36 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph. 01, 02, 03 & 04 | Masterplan | Master Planning | Master Plan Detailed Design 50% | Osama / Lina |  | 2025-06-15 21:36 | 2025-06-15 21:36 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph. 01, 02, 03 & 04 | Masterplan | Master Planning | HAP Review | Osama / Lina |  | 2025-06-29 21:36 | 2025-06-29 21:36 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph. 01, 02, 03 & 04 | Masterplan | Master Planning | Master Plan Detailed Design 100% | Osama / Lina |  | 2025-07-27 21:36 | 2025-07-27 21:36 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph. 01, 02, 03 & 04 | Masterplan | Master Planning | HAP Review | Osama / Lina |  | 2025-08-10 21:36 | 2025-08-10 21:36 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph. 01, 02, 03 & 04 | Masterplan | Master Planning | IFT | Osama / Lina |  | 2025-08-24 21:36 | 2025-08-24 21:36 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph. 01, 02, 03 & 04 | Masterplan | Master Planning | HAP Review | Osama / Lina |  | 2025-09-07 21:36 | 2025-09-07 21:36 | Completed | 0 | - | 0 | Red |  |  |  | 0
Ph. 01, 02, 03 & 04 | Plot Fences | Master Planning | IFT For Plot Fences |  |  |  | 2026-04-23 | Completed |  | - | 0 | Red |  | Ph. 01, 02, 03 & 04¦Plot Fences |  | 0
Ph. 01, 02, 03 & 04 | Plot Fences | Master Planning | HAP Review |  |  |  | 2026-05-04 | Completed |  | - | 0 | Red |  |  |  | 0
Ph. 01, 02, 03 & 04 | Infrastructure |  |  |  |  | 2025-11-08 | 2026-06-01 |  | 205 |  | -13 | Red |  | Ph. 01, 02, 03 & 04¦Infrastructure |  | 0
Ph. 01, 02, 03 & 04 | Infrastructure | Overall Infrastructure & roads (Main Utilities) | Concept Design + (BODR) | Osama / Lina | Archimid | 2024-04-04 21:00 | 2025-03-12 | Completed | 341.125 | - | 0 | Red |  |  |  | 0
Ph. 01, 02, 03 & 04 | Infrastructure | Overall Infrastructure & roads (Main Utilities) | HAP Review | Osama / Lina |  | 2024-04-18 21:00 | 2025-03-30 | Completed | 345.125 | - | 0 | Red |  |  |  | 0
Ph. 01, 02, 03 & 04 | Infrastructure | Overall Infrastructure & roads (Main Utilities) | Schematic Design | Osama / Lina | Archimid | 2024-09-15 21:00 | 2025-04-30 | Completed | 226.125 | - | 0 | Red |  |  |  | 0
Ph. 01, 02, 03 & 04 | Infrastructure | Overall Infrastructure & roads (Main Utilities) | HAP Review | Osama / Lina |  | 2024-09-29 21:00 | 2025-05-14 | Completed | 226.125 | - | 0 | Red |  |  |  | 0
Ph. 01, 02, 03 & 04 | Infrastructure | Overall Infrastructure & roads (Main Utilities) | Detailed Design 50% | Osama / Lina | Archimid | 2024-10-13 21:00 | 2025-05-29 | Completed | 227.125 | - | 0 | Red |  |  |  | 0
Ph. 01, 02, 03 & 04 | Infrastructure | Overall Infrastructure & roads (Main Utilities) | HAP Review | Osama / Lina |  | 2024-10-27 21:00 | 2025-06-14 | Completed | 229.125 | - | 0 | Red |  |  |  | 0
Ph. 01, 02, 03 & 04 | Infrastructure | Overall Infrastructure & roads (Main Utilities) | Detailed Design 100% | Osama / Lina | Archimid | 2024-11-24 21:00 | 2025-07-14 | Completed | 231.125 | - | 0 | Red |  |  |  | 0
Ph. 01, 02, 03 & 04 | Infrastructure | Overall Infrastructure & roads (Main Utilities) | HAP Review | Osama / Lina |  | 2024-12-08 21:00 | 2025-07-30 | Completed | 233.125 | - | 0 | Red |  |  |  | 0
Ph. 01, 02, 03 & 04 | Infrastructure | Overall Infrastructure & roads (Main Utilities) | Infrastructure IFP | Osama / Lina | Archimid | 2024-12-22 21:00 | 2025-08-14 | Completed | 234.125 | - | 0 | Red |  |  |  | 0
Ph. 01, 02, 03 & 04 | Infrastructure | Overall Infrastructure & roads (Main Utilities) | HAP Review + Auth. Approval | Osama / Lina |  | 2025-10-11 | 2025-11-27 | Completed | 47 | - | 0 | Red |  |  |  | 0
Ph. 01, 02, 03 & 04 | Infrastructure | Overall Infrastructure & roads (Main Utilities) | Infrastructure IFT + Permit Drawings | Osama / Lina | Archimid | 2025-10-25 | 2026-04-27 | Completed | 184 | - | 0 | Red |  |  |  | 0
Ph. 01, 02, 03 & 04 | Infrastructure | Overall Infrastructure & roads (Main Utilities) | HAP Review | Osama / Lina |  | 2025-11-08 | 2026-05-04 | Completed | 177 | - | 0 | Red |  |  |  | 0
Ph. 01, 02, 03 & 04 | Infrastructure | Overall Infrastructure & roads (Main Utilities) | Midar Approval' | Osama / Lina |  | 2025-11-08 | 2026-06-01 | Completed | 205 | - | 0 | Red |  |  |  | 0
Valleys | Landscape |  |  |  |  | 2025-12-29 | 2026-06-25 |  | 178 |  | 11 | Amber |  | Valleys¦Landscape |  | 0
Valleys | Landscape | Overall Landscape | Receive Master Plan after review |  |  | 2025-05-04 |  | Not Started |  |  |  | Amber |  |  |  | 0
Valleys | Landscape | Overall Landscape | Landscape Concept | Hoda / Ayman | ARDS | 2025-05-18 | 2025-08-14 | Completed | 88 | - | 0 | Red |  |  |  | 0
Valleys | Landscape | Overall Landscape | HAP Review | Hoda / Ayman |  | 2025-06-01 | 2025-09-08 | Completed | 99 | - | 0 | Red |  |  |  | 0
Valleys | Landscape | Overall Landscape | Cost Plan | Hoda / Ayman |  | 2025-08-28 | 2025-08-28 | Completed | 0 | - | 0 | Red |  |  |  | 0
Valleys | Landscape | Overall Landscape | 50% Schematic | Hoda / Ayman | ARDS | 2025-10-07 | 2025-10-16 | Completed | 9 | - | 0 | Red |  |  |  | 0
Valleys | Landscape | Overall Landscape | HAP Review | Hoda / Ayman |  | 2025-10-26 | 2025-11-02 | Completed | 7 | - | 0 | Red |  |  |  | 0
Valleys | Landscape | Overall Landscape | 100% Schematic Development | Hoda / Ayman | ARDS | 2025-11-16 | 2026-01-06 | Completed | 51 | - | 0 | Red |  |  |  | 0
Valleys | Landscape | Overall Landscape | HAP Review | Hoda / Ayman |  | 2025-12-07 | 2026-04-02 | Completed | 116 | - | 0 | Red |  |  |  | 0
Valleys | Landscape | Overall Landscape | Cost Plan | Nour / Noha | Survtec | 2025-12-29 | 2026-06-25 | Inprogress | 178 | Yes | 11 | Amber |  |  | 2 | 1 | 2
Ph.01 | Landscape |  |  |  |  | 2026-02-15 | 2026-08-25 |  | 191 |  | 72 | Green |  | Ph.01¦Landscape |  | 0
Ph.01 | Landscape | Phase 01 Landscape | 100% Design Development | Hoda / Ayman | ARDS | 2026-01-04 | 2026-06-16 | Completed | 163 | - | 0 | Amber |  |  |  | 0
Ph.01 | Landscape | Phase 01 Landscape | HAP Review | Hoda / Ayman |  | 2026-01-18 | 2026-06-30 | Inprogress | 163 | Yes | 16 | Amber |  |  | 3 | 1 | 3
Ph.01 | Landscape | Phase 01 Landscape | Cost Plan | Nour / Noha |  | 2026-01-18 | 2026-06-30 | Not Started | 163 | Yes | 16 | Amber |  |  | 4 | 1 | 4
Ph.01 | Landscape | Phase 01 Landscape | Conslidated Comments | Hoda / Ayman |  | 2026-01-18 | 2026-07-14 | Not Started | 177 | No | 30 | Green |  |  |  | 0
Ph.01 | Landscape | Phase 01 Landscape | Landscape IFT | Hoda / Ayman | ARDS | 2026-02-01 | 2026-08-11 | Not Started | 191 | No | 58 | Green |  |  |  | 0
Ph.01 | Landscape | Phase 01 Landscape | HAP Review | Hoda / Ayman |  | 2026-02-15 | 2026-08-25 | Not Started | 191 | No | 72 | Green |  |  |  | 0
Ph.02 | Landscape |  |  |  |  | 2026-02-15 | 2026-08-25 |  | 191 |  | 72 | Green |  | Ph.02¦Landscape |  | 0
Ph.02 | Landscape | Phase 02 Landscape | 100% Design Development | Hoda / Ayman | ARDS | 2026-01-04 | 2026-06-16 | Completed | 163 | - | 0 | Amber |  |  |  | 0
Ph.02 | Landscape | Phase 02 Landscape | HAP Review | Hoda / Ayman |  | 2026-01-18 | 2026-06-30 | Inprogress | 163 | Yes | 16 | Amber |  |  | 5 | 1 | 5
Ph.02 | Landscape | Phase 02 Landscape | Cost Plan | Nour / Noha |  | 2026-01-18 | 2026-06-30 | Not Started | 163 | Yes | 16 | Amber |  |  | 6 | 1 | 6
Ph.02 | Landscape | Phase 02 Landscape | Conslidated Comments | Hoda / Ayman |  | 2026-01-18 | 2026-07-14 | Not Started | 177 | No | 30 | Green |  |  |  | 0
Ph.02 | Landscape | Phase 02 Landscape | Landscape IFT | Hoda / Ayman | ARDS | 2026-02-01 | 2026-08-11 | Not Started | 191 | No | 58 | Green |  |  |  | 0
Ph.02 | Landscape | Phase 02 Landscape | HAP Review | Hoda / Ayman |  | 2026-02-15 | 2026-08-25 | Not Started | 191 | No | 72 | Green |  |  |  | 0
Main Valley | Landscape |  |  |  |  | 2026-02-15 | 2026-08-25 |  | 191 |  | 72 | Green |  | Main Valley¦Landscape |  | 0
Main Valley | Landscape | Main Valley | 100% Design Development | Hoda / Ayman | ARDS | 2026-01-04 | 2026-06-16 | Completed | 163 | - | 0 | Amber |  |  |  | 0
Main Valley | Landscape | Main Valley | HAP Review | Hoda / Ayman |  | 2026-01-18 | 2026-06-30 | Inprogress | 163 | Yes | 16 | Amber |  |  | 7 | 1 | 7
Main Valley | Landscape | Main Valley | Cost Plan | Nour / Noha |  | 2026-01-18 | 2026-06-30 | Not Started | 163 | Yes | 16 | Amber |  |  | 8 | 1 | 8
Main Valley | Landscape | Main Valley | Conslidated Comments | Hoda / Ayman |  | 2026-01-18 | 2026-07-14 | Not Started | 177 | No | 30 | Green |  |  |  | 0
Main Valley | Landscape | Main Valley | Landscape IFT | Hoda / Ayman | ARDS | 2026-02-01 | 2026-08-11 | Not Started | 191 | No | 58 | Green |  |  |  | 0
Main Valley | Landscape | Main Valley | HAP Review | Hoda / Ayman |  | 2026-02-15 | 2026-08-25 | Not Started | 191 | No | 72 | Green |  |  |  | 0
Ph.03 | Landscape |  |  |  |  | 2026-02-15 | 2026-12-01 |  | 289 |  | 170 | Green |  | Ph.03¦Landscape |  | 0
Ph.03 | Landscape | Phase 03 Landscape | 100% Design Development | Hoda / Ayman | ARDS | 2026-01-04 | 2026-09-29 | Not Started | 268 | No | 107 | Green |  |  |  | 0
Ph.03 | Landscape | Phase 03 Landscape | HAP Review | Hoda / Ayman |  | 2026-01-18 | 2026-10-13 | Not Started | 268 | No | 121 | Green |  |  |  | 0
Ph.03 | Landscape | Phase 03 Landscape | Cost Plan | Nour / Noha |  | 2026-01-18 | 2026-10-13 | Not Started | 268 | No | 121 | Green |  |  |  | 0
Ph.03 | Landscape | Phase 03 Landscape | Conslidated Comments | Hoda / Ayman |  | 2026-01-18 | 2026-10-27 | Not Started | 282 | No | 135 | Green |  |  |  | 0
Ph.03 | Landscape | Phase 03 Landscape | Landscape IFT | Hoda / Ayman | ARDS | 2026-02-01 | 2026-11-17 | Not Started | 289 | No | 156 | Green |  |  |  | 0
Ph.03 | Landscape | Phase 03 Landscape | HAP Review | Hoda / Ayman |  | 2026-02-15 | 2026-12-01 | Not Started | 289 | No | 170 | Green |  |  |  | 0
Ph.04 | Landscape |  |  |  |  | 2026-02-15 | 2026-12-01 |  | 289 |  | 170 | Green |  | Ph.04¦Landscape |  | 0
Ph.04 | Landscape | Phase 04 Landscape | 100% Design Development | Hoda / Ayman | ARDS | 2026-01-04 | 2026-09-29 | Not Started | 268 | No | 107 | Green |  |  |  | 0
Ph.04 | Landscape | Phase 04 Landscape | HAP Review | Hoda / Ayman |  | 2026-01-18 | 2026-10-13 | Not Started | 268 | No | 121 | Green |  |  |  | 0
Ph.04 | Landscape | Phase 04 Landscape | Cost Plan | Nour / Noha |  | 2026-01-18 | 2026-10-13 | Not Started | 268 | No | 121 | Green |  |  |  | 0
Ph.04 | Landscape | Phase 04 Landscape | Conslidated Comments | Hoda / Ayman |  | 2026-01-18 | 2026-10-27 | Not Started | 282 | No | 135 | Green |  |  |  | 0
Ph.04 | Landscape | Phase 04 Landscape | Landscape IFT | Hoda / Ayman | ARDS | 2026-02-01 | 2026-11-17 | Not Started | 289 | No | 156 | Green |  |  |  | 0
Ph.04 | Landscape | Phase 04 Landscape | HAP Review | Hoda / Ayman |  | 2026-02-15 | 2026-12-01 | Not Started | 289 | No | 170 | Green |  |  |  | 0
FM Building | Buildings |  |  |  |  | 2026-08-06 | 2026-09-19 |  | 44 |  | 97 | Green |  | FM Building¦Buildings |  | 0
FM Building | Buildings | Buildings - FM | 100% Concept Design | Osama / Lina | KMA | 2026-01-26 | 2026-01-26 | Completed | 0 | - | 0 | Red |  |  |  | 0
FM Building | Buildings | Buildings - FM | HAP Review - 100% CD | Osama / Lina |  | 2026-02-09 | 2026-02-09 | Completed | 0 | - | 0 | Red |  |  |  | 0
FM Building | Buildings | Buildings - FM | Cost Plan - 100% CD | Nour / Noha |  | 2026-02-19 | 2026-02-19 | Completed | 0 | - | 0 | Red |  |  |  | 0
FM Building | Buildings | Buildings - FM | 100% Schematic Design | Osama / Lina | Archimid | 2026-04-15 | 2026-05-25 | Completed | 40 | - | 0 | Red |  |  |  | 0
FM Building | Buildings | Buildings - FM | HAP Review - 100% SD | Osama / Lina |  | 2026-04-29 | 2026-06-15 | Completed | 47 | - | 0 | Amber |  |  |  | 0
FM Building | Buildings | Buildings - FM | Cost Plan - 100% SD | Nour / Noha |  | 2026-05-06 | 2026-08-15 | Not Started | 101 | No | 62 | Green |  |  |  | 0
FM Building | Buildings | Buildings - FM | 100% Detailed Design | Osama / Lina | Archimid | 2026-06-25 | 2026-08-08 | Not Started | 44 | No | 55 | Green |  |  |  | 0
FM Building | Buildings | Buildings - FM | HAP Review - 100% DD | Osama / Lina |  | 2026-07-09 | 2026-08-22 | Not Started | 44 | No | 69 | Green |  |  |  | 0
FM Building | Buildings | Buildings - FM | Peer Review - 100% DD | Osama / Lina | KH Studio | 2026-07-02 | 2026-08-15 | Not Started | 44 | No | 62 | Green |  |  |  | 0
FM Building | Buildings | Buildings - FM | Tender Package | Osama / Lina | Archimid | 2026-07-23 | 2026-09-05 | Not Started | 44 | No | 83 | Green |  |  |  | 0
FM Building | Buildings | Buildings - FM | HAP Review - TD | Osama / Lina |  | 2026-08-06 | 2026-09-19 | Not Started | 44 | No | 97 | Green |  |  |  | 0
FM Building | Buildings | Buildings - FM | Peer Review - TD | Osama / Lina | KH Studio | 2026-07-30 | 2026-09-12 | Not Started | 44 | No | 90 | Green |  |  |  | 0
FM Building | Buildings | Buildings - FM | Permits Drawings | Osama / Lina | Archimid | 2026-07-23 | 2026-09-05 | Not Started | 44 | No | 83 | Green |  |  |  | 0
FM Building | Buildings | Buildings - FM | HAP Review - PD | Osama / Lina |  | 2026-08-06 | 2026-09-19 | Not Started | 44 | No | 97 | Green |  |  |  | 0
FM Building | Authorities |  |  |  |  | 2027-05-04 | 2027-05-04 |  | 0 |  | 324 | Green |  | FM Building¦Authorities |  | 0
FM Building | Authorities | Permits Issuance - FM | Ministerial decree-MIDAR | Afifi |  | 2026-09-08 | 2026-09-08 | Not Started | 0 | No | 86 | Green |  |  |  | 0
FM Building | Authorities | Permits Issuance - FM | Ministerial decree NUCA | Afifi |  | 2026-12-01 | 2026-12-01 | Not Started | 0 | No | 170 | Green |  |  |  | 0
FM Building | Authorities | Permits Issuance - FM | Egyptian Institution for Construction Civil Liability Insurance | Afifi |  | 2027-01-12 | 2027-01-12 | Not Started | 0 | No | 212 | Green |  |  |  | 0
FM Building | Authorities | Permits Issuance - FM | Construction licenses | Afifi |  | 2027-02-23 | 2027-02-23 | Not Started | 0 | No | 254 | Green |  |  |  | 0
FM Building | Authorities | Permits Issuance - FM | Mineral licenses | Afifi |  | 2027-05-04 | 2027-05-04 | Not Started | 0 | No | 324 | Green |  |  |  | 0
FM Building | Fit-out |  |  |  |  | 2026-06-11 | 2026-08-30 |  | 80 |  | 77 | Green |  | FM Building¦Fit-out |  | 0
FM Building | Fit-out | Interior - FM | Commencement | Osama / Lina |  | 2026-04-02 | 2026-06-21 | Completed | 80 | - | 0 | Amber |  |  |  | 0
FM Building | Fit-out | Interior - FM | 100% Concept Design | Osama / Lina | KH Studio | 2026-04-29 | 2026-07-18 | Inprogress | 80 | No | 34 | Green |  |  |  | 0
FM Building | Fit-out | Interior - FM | HAP Review - 100% CD | Osama / Lina |  | 2026-05-06 | 2026-07-25 | Not Started | 80 | No | 41 | Green |  |  |  | 0
FM Building | Fit-out | Interior - FM | 100% Schematic Design | Osama / Lina | KH Studio | 2026-06-04 | 2026-08-23 | Not Started | 80 | No | 70 | Green |  |  |  | 0
FM Building | Fit-out | Interior - FM | HAP Review - 100% SD | Osama / Lina |  | 2026-06-11 | 2026-08-30 | Not Started | 80 | No | 77 | Green |  |  |  | 0
Clubhouse | Buildings |  |  |  |  | 2026-08-19 | 2026-10-01 |  | 43 |  | 109 | Green |  | Clubhouse¦Buildings |  | 0
Clubhouse | Buildings | Clubhouse - Building (Include ID) | 100% Concept Design | Dina / Wahby | KH Studio | 2026-05-06 | 2026-06-18 | Completed | 43 | - | 0 | Amber |  |  |  | 0
Clubhouse | Buildings | Clubhouse - Building (Include ID) | HAP Review - 100% CD | Dina / Wahby |  | 2026-05-20 | 2026-07-02 | Inprogress | 43 | No | 18 | Amber |  |  |  | 0
Clubhouse | Buildings | Clubhouse - Building (Include ID) | Marketing Materials & Renders | Dina / Wahby | KH Studio | 2026-06-24 | 2026-08-06 | Not Started | 43 | No | 53 | Green |  |  |  | 0
Clubhouse | Buildings | Clubhouse - Building (Include ID) | HAP Review | Dina / Wahby |  | 2026-07-01 | 2026-08-13 | Not Started | 43 | No | 60 | Green |  |  |  | 0
Clubhouse | Buildings | Clubhouse - Building (Include ID) | 100% Schematic Design | Dina / Wahby | KH Studio | 2026-08-05 | 2026-09-17 | Not Started | 43 | No | 95 | Green |  |  |  | 0
Clubhouse | Buildings | Clubhouse - Building (Include ID) | HAP Review - 100% SD | Dina / Wahby |  | 2026-08-19 | 2026-10-01 | Not Started | 43 | No | 109 | Green |  |  |  | 0
Clubhouse | Buildings | Clubhouse - Building (Include ID) | Cost Plan - 100% SD |  |  | 2026-08-19 | 2026-10-01 | Not Started | 43 | No | 109 | Green |  |  |  | 0
|  | Clubhouse - Building (Include ID) | Permits Issuance |  |  |  |  | Not Started |  |  |  | Amber |  | ¦ |  | 0
|  | Clubhouse - Building (Include ID) | Ministerial decree |  |  |  |  | Not Started |  |  |  | Amber |  | ¦ |  | 0
|  | Clubhouse - Building (Include ID) | Egyptian Institution for Construction Civil Liability Insurance |  |  |  |  | Not Started |  |  |  | Amber |  | ¦ |  | 0
|  | Clubhouse - Building (Include ID) | Construction licenses |  |  |  |  | Not Started |  |  |  | Amber |  | ¦ |  | 0
|  | Clubhouse - Building (Include ID) | Mineral licenses |  |  |  |  | Not Started |  |  |  | Amber |  | ¦ |  | 0
|  | Clubhouse - Building (Include ID) | IFC Submission |  |  |  |  | Not Started |  |  |  | Amber |  | ¦ |  | 0
|  | Clubhouse - Building (Include ID) | Tender Action |  |  |  |  | Not Started |  |  |  | Amber |  | ¦ |  | 0
|  | Clubhouse - Building (Include ID) | Tender Services |  |  |  |  | Not Started |  |  |  | Amber |  | ¦ |  | 0
|  | Clubhouse - Building (Include ID) | IFC Submission |  |  |  |  | Not Started |  |  |  | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
Formulas:
Overdue? = IF([Parent]="","",IF([Actual / Forecast Finish]="","",IF([Status]="completed","-",IF([Actual / Forecast Finish]>TODAY(),"No","Yes"))))
Overdue? = IF([Actual / Forecast Finish]="","",IF([Actual / Forecast Finish]>TODAY(),"No","Yes"))

## SLR
SLR | [5 empty] | 2030-07-09 | 2030-08-28 | 50
Phase | Trade | Parent | Task | Task Owner | Consultant | Baseline Finish | Actual / Forecast Finish | Status | Slippage (days) | Overdue? | Days to Finish/Delay | RAG | Notes | CurKey | OvdRank | ShowFlag | DesignRank
Selina | Buildings | Buildings - Selina | Tender Package | Ashraf / Sara | KAD | 2024-11-28 | 2024-11-28 | Completed | 0 | - | 0 | Red |  | #REF! |  | 0
Selina | Buildings | Buildings - Selina | Peer Review | Ashraf / Sara |  | 2025-01-28 | 2025-01-28 | Completed | 0 | - | 0 | Red |  |  |  | 0
Selina | Buildings | Buildings - Selina | HAP Review | Ashraf / Sara |  | 2025-04-26 | 2025-04-26 | Completed | 0 | - | 0 | Red |  |  |  | 0
Selina | Buildings | Buildings - Selina | VE | Ashraf / Sara |  | 2025-04-26 | 2025-04-26 | Completed | 0 | - | 0 | Red |  |  |  | 0
Selina | Buildings | Buildings - Selina | Phase 02 Revised Tender Package | Ashraf / Sara | KAD | 2025-06-23 | 2025-06-23 | Completed | 0 | - | 0 | Red |  |  |  | 0
Selina | Buildings | Buildings - Selina | HAP Review | Ashraf / Sara |  | 2025-06-24 | 2025-06-24 | Completed | 0 | - | 0 | Red |  |  |  | 0
Selina | Buildings | Buildings - Selina | Phase 01 Revised Tender Package | Ashraf / Sara | KAD | 2025-07-09 | 2025-07-09 | Completed | 0 | - | 0 | Red |  |  |  | 0
Selina | Buildings | Buildings - Selina | HAP Review | Ashraf / Sara |  | 2025-07-13 | 2025-07-13 | Completed | 0 | - | 0 | Red |  |  |  | 0
Selina | Infrastructure |  |  |  |  | 2025-09-08 | 2025-09-08 |  | 0 |  | -279 | Red |  | Selina¦Infrastructure |  | 0
Selina | Infrastructure | Infra - Selina | Data to be send by HAP | Ashraf / Sara |  | 2024-12-02 | 2024-12-02 | Not Started | 0 | Yes | -559 | Red |  |  | 1 | 1 | 1
Selina | Infrastructure | Infra - Selina | Infra DD Submission | Ashraf / Sara | Shaker | 2025-02-02 | 2025-02-02 | Completed | 0 | - | 0 | Red |  |  |  | 0
Selina | Infrastructure | Infra - Selina | HAP Review | Ashraf / Sara |  | 2025-02-10 | 2025-02-10 | Completed | 0 | - | 0 | Red |  |  |  | 0
Selina | Infrastructure | Infra - Selina | Infra IFT Submission | Ashraf / Sara | Shaker | 2025-02-25 | 2025-02-25 | Completed | 0 | - | 0 | Red |  |  |  | 0
Selina | Infrastructure | Infra - Selina | HAP Review + Final IFT Submission | Ashraf / Sara |  | 2025-09-08 | 2025-09-08 | Completed | 0 | - | 0 | Red |  |  |  | 0
Selina | Landscape |  |  |  |  | 2026-02-12 | 2026-09-02 |  | 202 |  | 80 | Green |  | Selina¦Landscape |  | 0
Selina | Landscape | Landscape - Selina | Schematic Package | Hoda / Dina | ARDS | 2024-12-19 | 2024-12-19 | Not Started | 0 | Yes | -542 | Red |  |  | 2 | 1 | 2
Selina | Landscape | Landscape - Selina | HAP Review | Hoda / Dina |  | 2025-01-21 | 2025-01-21 | Completed | 0 | - | 0 | Red |  |  |  | 0
Selina | Landscape | Landscape - Selina | Cost Verification | Nour / Noha |  | 2025-01-21 | 2025-01-21 | Completed | 0 | - | 0 | Red |  |  |  | 0
Selina | Landscape | Landscape - Selina | Revised Schematic Package | Hoda / Dina | ARDS | 2025-11-06 | 2026-02-22 | Completed | 108 | - | 0 | Red |  |  |  | 0
Selina | Landscape | Landscape - Selina | HAP Review - 100% SD | Hoda / Dina |  | 2025-11-13 | 2026-05-04 | Completed | 172 | - | 0 | Red |  |  |  | 0
Selina | Landscape | Landscape - Selina | 50% Detailed Design | Hoda / Dina | ARDS | 2025-12-11 | 2026-06-24 | Inprogress | 195 | Yes | 10 | Amber |  |  | 3 | 1 | 3
Selina | Landscape | Landscape - Selina | HAP Review - 50% DD | Hoda / Dina |  | 2025-12-18 | 2026-07-01 | Not Started | 195 | Yes | 17 | Amber |  |  | 4 | 1 | 4
Selina | Landscape | Landscape - Selina | 100% Detailed Design | Hoda / Dina | ARDS | 2026-01-08 | 2026-07-22 | Not Started | 195 | No | 38 | Green |  |  |  | 0
Selina | Landscape | Landscape - Selina | HAP Review - 100% DD | Hoda / Dina |  | 2026-01-15 | 2026-07-29 | Not Started | 195 | No | 45 | Green |  |  |  | 0
Selina | Landscape | Landscape - Selina | Cost Plan - 100% DD | Nour / Noha |  | 2026-01-22 | 2026-08-05 | Not Started | 195 | No | 52 | Green |  |  |  | 0
Selina | Landscape | Landscape - Selina | Tender Package | Hoda / Dina | ARDS | 2026-01-29 | 2026-08-19 | Not Started | 202 | No | 66 | Green |  |  |  | 0
Selina | Landscape | Landscape - Selina | HAP Review + Final IFT Submission | Hoda / Dina |  | 2026-02-12 | 2026-09-02 | Not Started | 202 | No | 80 | Green |  |  |  | 0
Selina | Plot Fences | [5 empty] | 2026-07-02 |  |  |  | 18 | Amber |  | Selina¦Plot Fences |  | 0
Selina | Plot Fences | Plot Fences - Selina | 50% Tender Package | Hoda / Dina | Sites |  | 2025-07-01 | Not Started |  | Yes | -348 | Red |  |  | 5 | 1 | 5
Selina | Plot Fences | Plot Fences - Selina | HAP Review - 50% TD | Hoda / Dina |  |  | 2026-04-19 | Completed |  | - | 0 | Red |  |  |  | 0
Selina | Plot Fences | Plot Fences - Selina | 100% Tender Package | Hoda / Dina | Sites |  | 2026-06-25 | Inprogress |  | Yes | 11 | Amber |  |  | 6 | 1 | 6
Selina | Plot Fences | Plot Fences - Selina | HAP Review + Final IFT Submission | Hoda / Dina |  |  | 2026-07-02 | Not Started |  | No | 18 | Amber |  |  |  | 0
Selina | Parcel Fence | [5 empty] | 2026-02-10 |  |  |  | -124 | Red |  | Selina¦Parcel Fence |  | 0
Selina | Parcel Fence | Parcel Fence | HAP Review - TD | Hoda / Dina |  |  | 2026-02-10 | Completed |  | - | 0 | Red |  |  |  | 0
Amaia | Buildings |  |  |  |  | 2026-01-01 | 2026-04-23 |  | 112 |  | -52 | Red |  | Amaia¦Buildings |  | 0
Amaia | Buildings | Buildings - Amaia | Tender Package |  |  |  | 2025-02-18 | Completed |  | - | 0 | Red |  |  |  | 0
Amaia | Buildings | Buildings - Amaia | HAP Review - TD |  |  |  | 2025-02-24 | Completed |  | - | 0 | Red |  |  |  | 0
Amaia | Buildings | Buildings - Amaia | Work continued with Constructive |  |  | 2025-11-20 | 2025-10-20 | Completed | -31 | - | 0 | Red |  |  |  | 0
Amaia | Buildings | Buildings - Amaia | Revised Buildings IFT Package (Signature Villas) |  | Archimid | 2025-11-09 | 2026-01-14 | Completed | 66 | - | 0 | Red |  |  |  | 0
Amaia | Buildings | Buildings - Amaia | HAP Review + Final IFT Submission (Signature Villas) |  |  | 2025-11-20 | 2026-01-15 | Completed | 56 | - | 0 | Red |  |  |  | 0
Amaia | Buildings | Buildings - Amaia | Revised Buildings IFT Package (Solos Villas) |  | Archimid | 2025-12-18 | 2026-02-23 | Completed | 67 | - | 0 | Red |  |  |  | 0
Amaia | Buildings | Buildings - Amaia | HAP Review + Final IFT Submission (Solos Villas) |  |  | 2026-01-01 | 2026-02-26 | Completed | 56 | - | 0 | Red |  |  |  | 0
Amaia | Buildings | Buildings - Amaia | Revised Buildings IFT Package (Monos Villas) |  | Archimid | 2025-12-18 | 2026-04-19 | Completed | 122 | - | 0 | Red |  |  |  | 0
Amaia | Buildings | Buildings - Amaia | HAP Review + Final IFT Submission (Monos Villas) |  |  | 2026-01-01 | 2026-04-23 | Completed | 112 | - | 0 | Red |  |  |  | 0
Villa 103&108 | Buildings |  |  |  |  | 2026-02-23 | 2026-06-09 |  | 106 |  | -5 | Red |  | Villa 103&108¦Buildings |  | 0
Villa 103&108 | Buildings | Villa 103&108 | 100% Schematic Design |  |  | 2025-12-22 | 2025-12-29 | Completed | 7 | - | 0 | Red |  |  |  | 0
Villa 103&108 | Buildings | Villa 103&108 | HAP Review - 100% SD |  |  | 2025-12-29 | 2026-02-11 | Completed | 44 | - | 0 | Red |  |  |  | 0
Villa 103&108 | Buildings | Villa 103&108 | 100% Detailed Design |  |  | 2026-01-12 |  | Not Started |  |  |  | Amber |  |  |  | 0
Villa 103&108 | Buildings | Villa 103&108 | HAP Review - 100% DD |  | Archimid | 2026-01-19 |  | Not Started |  |  |  | Amber |  |  |  | 0
Villa 103&108 | Buildings | Villa 103&108 | Permits Drawings |  |  | 2026-01-26 | 2026-03-15 | Completed | 48 | - | 0 | Red |  |  |  | 0
Villa 103&108 | Buildings | Villa 103&108 | Updated Permits Drawings |  |  |  | 2026-05-13 | Completed |  | - | 0 | Red |  |  |  | 0
Villa 103&108 | Buildings | Villa 103&108 | Hap Review - PD | Ashraf / Sara | Archimid | 2026-02-02 | 2026-06-09 | Completed | 127 | - | 0 | Red |  |  |  | 0
Villa 103&108 | Buildings | Villa 103&108 | Tender Package |  |  | 2026-02-16 | 2026-03-03 | Completed | 15 | - | 0 | Red |  |  |  | 0
Villa 103&108 | Buildings | Villa 103&108 | HAP Review - TD |  | Archimid | 2026-02-23 | 2026-03-05 | Completed | 10 | - | 0 | Red |  |  |  | 0
Amaia | Authorities |  |  |  |  | 2026-07-12 | 2026-11-04 |  | 115 |  | 143 | Green |  | Amaia¦Authorities |  | 0
Amaia | Masterplan |  |  |  |  | 2026-03-29 | 2026-03-11 |  | -18 |  | -95 | Red |  | Amaia¦Masterplan |  | 0
Amaia | Masterplan | Amaia - Masterplan | Detailed Design Validation |  | Oko Plan | 2026-02-08 | 2026-02-08 | Completed | 0 | - | 0 | Red |  |  |  | 0
Amaia | Masterplan | Amaia - Masterplan | 100% Detailed Design (Optional) |  |  | 2026-03-01 |  | Not Started |  |  |  | Amber |  |  |  | 0
Amaia | Masterplan | Amaia - Masterplan | HAP Review |  |  | 2026-03-08 |  | Not Started |  |  |  | Amber |  |  |  | 0
Amaia | Masterplan | Amaia - Masterplan | Tender Package |  | Oko Plan | 2026-03-22 | 2026-03-11 | Completed | -11 | - | 0 | Red |  |  |  | 0
Amaia | Masterplan | Amaia - Masterplan | HAP Review |  |  | 2026-03-29 | 2026-03-11 | Completed | -18 | - | 0 | Red |  |  |  | 0
|  | Amaia - Masterplan | Tender Action |  |  | 2026-07-19 | 2026-07-01 | Not Started | -18 | Yes | 17 | Amber |  | ¦ | 7 | 1 | 7
|  | Amaia - Masterplan | IFC |  |  | 2026-07-12 | 2026-06-24 | Not Started | -18 | Yes | 10 | Amber |  | ¦ | 8 | 1 | 8
|  | Amaia - Masterplan | HAP Review |  |  | 2026-07-19 | 2026-07-01 | Not Started | -18 | Yes | 17 | Amber |  | ¦ | 9 | 1 | 9
Amaia | Infrastructure |  |  |  |  | 2025-07-14 | 2025-07-14 |  | 0 |  | -335 | Red |  | Amaia¦Infrastructure |  | 0
Amaia | Infrastructure | Infra | Comments on Schematic to be send by HAP |  |  | 2025-01-25 | 2025-01-25 | Not Started | 0 | Yes | -505 | Red |  |  | 10 | 1 | 10
Amaia | Infrastructure | Infra | Infra DD Submission |  |  | 2025-03-15 | 2025-03-15 | Completed | 0 | - | 0 | Red |  |  |  | 0
Amaia | Infrastructure | Infra | HAP Review |  |  | 2025-04-16 | 2025-04-16 | Completed | 0 | - | 0 | Red |  |  |  | 0
Amaia | Infrastructure | Infra | Infra IFT Submission |  |  | 2025-05-13 | 2025-05-13 | Completed | 0 | - | 0 | Red |  |  |  | 0
Amaia | Infrastructure | Infra | HAP Review + Final IFT Submission |  |  | 2025-07-14 | 2025-07-14 | Completed | 0 | - | 0 | Red |  |  |  | 0
Amaia | Landscape |  |  |  |  | 2026-06-21 | 2026-09-20 |  | 91 |  | 98 | Green |  | Amaia¦Landscape |  | 0
Amaia | Landscape | Landscape | Concept Validation | Hoda / Roshdy | Oko Plan | 2026-02-22 | 2026-04-23 | Completed | 60 | - | 0 | Red |  |  |  | 0
Amaia | Landscape | Landscape | HAP Review - CV | Hoda / Roshdy |  | 2026-03-01 | 2026-05-17 | Completed | 77 | - | 0 | Red |  |  |  | 0
Amaia | Landscape | Landscape | 50% Detailed Design | Hoda / Roshdy | Oko Plan | 2026-04-12 | 2026-07-12 | Inprogress | 91 | No | 28 | Green |  |  |  | 0
Amaia | Landscape | Landscape | HAP Review - 50% DD | Hoda / Roshdy |  | 2026-04-19 | 2026-07-19 | Not Started | 91 | No | 35 | Green |  |  |  | 0
Amaia | Landscape | Landscape | 100% Detailed Design | Hoda / Roshdy | Oko Plan | 2026-05-17 | 2026-08-16 | Not Started | 91 | No | 63 | Green |  |  |  | 0
Amaia | Landscape | Landscape | HAP Review - 100% DD | Hoda / Roshdy |  | 2026-05-24 | 2026-08-23 | Not Started | 91 | No | 70 | Green |  |  |  | 0
Amaia | Landscape | Landscape | Tender Package | Hoda / Roshdy | Oko Plan | 2026-06-14 | 2026-09-13 | Not Started | 91 | No | 91 | Green |  |  |  | 0
Amaia | Landscape | Landscape | HAP Review - TD | Hoda / Roshdy |  | 2026-06-21 | 2026-09-20 | Not Started | 91 | No | 98 | Green |  |  |  | 0
|  | Landscape | Tender Action |  |  | 2026-10-11 | 2027-01-10 | Not Started | 91 | No | 210 | Green |  | ¦ |  | 0
|  | Landscape | IFC |  | Oko Plan | 2026-10-04 | 2027-01-03 | Not Started | 91 | No | 203 | Green |  | ¦ |  | 0
|  | Landscape | HAP Review |  |  | 2026-10-11 | 2027-01-10 | Not Started | 91 | No | 210 | Green |  | ¦ |  | 0
[7 empty] | 2026-07-05 |  |  |  | 21 | Amber |  | ¦ |  | 0
Amaia | Plot Fences | Plot Fence - Amaia | Tender Package | Hoda / Roshdy |  |  | 2026-06-28 | Inprogress |  | Yes | 14 | Amber |  | Amaia¦Plot Fences | 11 | 1 | 11
Amaia | Plot Fences | Plot Fence - Amaia | HAP Review - TD | Hoda / Roshdy |  |  | 2026-07-05 | Not Started |  | No | 21 | Amber |  |  |  | 0
Pheonix | Buildings |  |  |  |  | 2026-02-25 | 2026-05-31 |  | 95 |  | -14 | Red |  | Pheonix¦Buildings |  | 0
Pheonix | Buildings | Buildings - Pheonix | Buildings IFT Package + ID | Ashraf / Sara | Emdad | 2025-10-08 | 2025-11-20 | Completed | 43 | - | 0 | Red |  |  |  | 0
Pheonix | Buildings | Buildings - Pheonix | HAP Review + Final IFT Submission | Ashraf / Sara |  | 2025-10-22 | 2025-11-30 | Completed | 39 | - | 0 | Red |  |  |  | 0
Pheonix | Buildings | Buildings - Pheonix | Fitout BOQ preperation CL01 to CL05 | Ashraf / Sara | Emdad | 2025-12-03 | 2026-01-11 | Completed | 39 | - | 0 | Red |  |  |  | 0
Pheonix | Buildings | Buildings - Pheonix | Fitout BOQ preperation CL06 to CL15 | Ashraf / Sara | Emdad | 2026-01-28 | 2026-03-08 | Completed | 39 | - | 0 | Red |  |  |  | 0
Pheonix | Buildings | Buildings - Pheonix | Fitout Tender Process CL01 to CL05 | Ashraf / Sara | Emdad | 2026-01-14 | 2026-04-05 | Completed | 81 | - | 0 | Red |  |  |  | 0
Pheonix | Buildings | Buildings - Pheonix | Fitout Tender Process CL06 to CL15 | Ashraf / Sara | Emdad | 2026-02-25 | 2026-05-31 | Completed | 95 | - | 0 | Red |  |  |  | 0
Pheonix | Authorities | [5 empty] | 2026-10-11 |  |  |  | 119 | Green |  | Pheonix¦Authorities |  | 0
Pheonix | Landscape |  |  |  |  | 2026-07-30 | 2026-08-17 07:12 |  | 18.3 |  | 64.3 | Green |  | Pheonix¦Landscape |  | 0
Pheonix | Landscape | Landscape - Pheonix | Basemap with Grading | Hoda / Dina | OKO Plan | 2026-05-10 | 2026-06-07 | Completed | 28 | - | 0 | Red |  |  |  | 0
Pheonix | Landscape | Landscape - Pheonix | HAP Review - 100% SD | Hoda / Dina |  | 2026-05-12 | 2026-06-09 | Completed | 28 | - | 0 | Red |  |  |  | 0
Pheonix | Landscape | Landscape - Pheonix | 50% Detailed Design | Hoda / Dina | OKO Plan | 2026-06-07 | 2026-07-01 | Inprogress | 24 | Yes | 17 | Amber |  |  | 12 | 1 | 12
Pheonix | Landscape | Landscape - Pheonix | HAP Review - 50% DD | Hoda / Dina |  | 2026-06-10 | 2026-07-07 | Not Started | 27 | No | 23 | Green |  |  |  | 0
Pheonix | Landscape | Landscape - Pheonix | 100% Detailed Design | Hoda / Dina | OKO Plan | 2026-06-29 | 2026-07-26 | Not Started | 27 | No | 42 | Green |  |  |  | 0
Pheonix | Landscape | Landscape - Pheonix | HAP Review - 100% DD | Hoda / Dina |  | 2026-07-05 | 2026-07-29 | Not Started | 24 | No | 45 | Green |  |  |  | 0
Pheonix | Landscape | Landscape - Pheonix | Cost Plan - 100% DD | Nour / Noha |  | 2026-07-13 | 2026-08-10 | Not Started | 28 | No | 57 | Green |  |  |  | 0
Pheonix | Landscape | Landscape - Pheonix | Tender Package | Hoda / Dina | OKO Plan | 2026-07-19 | 2026-08-12 07:12 | Not Started | 24.3 | No | 59.3 | Green |  |  |  | 0
Pheonix | Landscape | Landscape - Pheonix | HAP Review - TD + Comments Implementation | Hoda / Dina |  | 2026-07-30 | 2026-08-17 07:12 | Not Started | 18.3 | No | 64.3 | Green |  |  |  | 0
|  | Landscape - Pheonix | Tender Process |  |  | 2026-11-22 | 2026-12-10 07:12 | Not Started | 18.3 | No | 179.3 | Green |  | ¦ |  | 0
|  | Landscape - Pheonix | IFC |  |  | 2026-11-22 | 2026-12-10 07:12 | Not Started | 18.3 | No | 179.3 | Green |  | ¦ |  | 0
Pheonix | Plot Fences |  |  |  |  | 2026-06-01 | 2026-06-30 |  | 29 |  | 16 | Amber |  | Pheonix¦Plot Fences |  | 0
Pheonix | Plot Fences | Garden Plot Fences - Pheonix | Fence Typology | Hoda / Dina | OKO Plan | 2026-05-10 | 2026-05-25 | Completed | 15 | - | 0 | Red |  |  |  | 0
Pheonix | Plot Fences | Garden Plot Fences - Pheonix | HAP Review - Fence Typology | Hoda / Dina |  | 2026-05-12 | 2026-06-01 | Completed | 20 | - | 0 | Red |  |  |  | 0
Pheonix | Plot Fences | Garden Plot Fences - Pheonix | Tender Package | Hoda / Dina | OKO Plan | 2026-05-19 | 2026-06-23 | Inprogress | 35 | Yes | 9 | Amber |  |  | 13 | 1 | 13
Pheonix | Plot Fences | Garden Plot Fences - Pheonix | HAP Review - TD + Comments Implementation | Hoda / Dina |  | 2026-06-01 | 2026-06-30 | Not Started | 29 | Yes | 16 | Amber |  |  | 14 | 1 | 14
IRIS 01&02 | Landscape |  |  |  |  | 2025-12-15 | 2026-02-23 |  | 70 |  | -111 | Red |  | IRIS 01&02¦Landscape |  | 0
IRIS 01&02 | Landscape | Landscape - IRIS 01&02 | Pre-Concept Design - IRIS 01 & 02 |  |  | 2025-03-01 | 2025-03-01 | Completed | 0 | - | 0 | Red |  |  |  | 0
IRIS 01&02 | Landscape | Landscape - IRIS 01&02 | HAP Review - PC |  |  | 2025-03-30 | 2025-03-30 | Completed | 0 | - | 0 | Red |  |  |  | 0
IRIS 01&02 | Landscape | Landscape - IRIS 01&02 | Final Concept Design - IRIS |  |  | 2025-04-28 | 2025-04-28 | Completed | 0 | - | 0 | Red |  |  |  | 0
IRIS 01&02 | Landscape | Landscape - IRIS 01&02 | HAP Review - 100% CD |  |  | 2025-05-13 | 2025-05-13 | Completed | 0 | - | 0 | Red |  |  |  | 0
IRIS 01&02 | Landscape | Landscape - IRIS 01&02 | Cost Verification - 100% CD |  |  | 2025-05-13 | 2025-05-13 | Completed | 0 | - | 0 | Red |  |  |  | 0
IRIS 01&02 | Landscape | Landscape - IRIS 01&02 | 50% Schematic Design - Iris 01 & 02 |  |  | 2025-06-11 | 2025-06-11 | Completed | 0 | - | 0 | Red |  |  |  | 0
IRIS 01&02 | Landscape | Landscape - IRIS 01&02 | HAP Review - 50% SD |  |  | 2025-06-26 | 2025-06-26 | Completed | 0 | - | 0 | Red |  |  |  | 0
IRIS 01&02 | Landscape | Landscape - IRIS 01&02 | Cost Verification - 50% SD |  |  | 2025-07-03 | 2025-07-03 | Completed | 0 | - | 0 | Red |  |  |  | 0
IRIS 01&02 | Landscape | Landscape - IRIS 01&02 | 100% Schematic Design - Iris 01 & 02 |  |  | 2025-08-02 | 2025-08-02 | Completed | 0 | - | 0 | Red |  |  |  | 0
IRIS 01&02 | Landscape | Landscape - IRIS 01&02 | HAP Review - 100% SD |  |  | 2025-08-17 | 2025-08-17 | Completed | 0 | - | 0 | Red |  |  |  | 0
IRIS 01&02 | Landscape | Landscape - IRIS 01&02 | 100% Detailed Design - Iris 01 & 02 - Hardscape |  |  | 2025-10-15 | 2025-11-17 | Completed | 33 | - | 0 | Red |  |  |  | 0
IRIS 01&02 | Landscape | Landscape - IRIS 01&02 | 100% Detailed Design - Iris 01 & 02 - Softscape |  |  | 2025-10-15 | 2026-01-08 | Completed | 85 | - | 0 | Red |  |  |  | 0
IRIS 01&02 | Landscape | Landscape - IRIS 01&02 | HAP Review - 100% DD |  |  | 2025-10-30 | 2026-01-14 | Completed | 76 | - | 0 | Red |  |  |  | 0
IRIS 01&02 | Landscape | Landscape - IRIS 01&02 | Tender Package |  |  | 2025-11-30 | 2026-02-19 | Completed | 81 | - | 0 | Red |  |  |  | 0
IRIS 01&02 | Landscape | Landscape - IRIS 01&02 | HAP Review - TD |  |  | 2025-12-15 | 2026-02-23 | Completed | 70 | - | 0 | Red |  |  |  | 0
IRIS 01&02 | Plot Fences |  |  |  |  | 2026-12-10 | 2026-03-09 |  | -276 |  | -97 | Red |  | IRIS 01&02¦Plot Fences |  | 0
IRIS 01&02 | Plot Fences | Plot Fences | Plot Fences IFC |  |  |  | 2026-03-03 | Completed |  | - | 0 | Red |  |  |  | 0
IRIS 01&02 | Plot Fences | Plot Fences | HAP Review |  |  |  | 2026-03-09 | Completed |  | - | 0 | Red |  |  |  | 0
IRIS 03 | Buildings |  |  |  |  | 2026-10-27 | 2026-03-30 |  | -211 |  | -76 | Red |  | IRIS 03¦Buildings |  | 0
IRIS 03 | Buildings | Concept (MIMAR) | Pre Concept |  |  | 2026-09-22 | 2025-11-27 | Completed | -299 | - | 0 | Red |  |  |  | 0
IRIS 03 | Buildings | Concept (MIMAR) | HAP Review |  |  | 2026-09-29 | 2025-12-04 | Completed | -299 | - | 0 | Red |  |  |  | 0
IRIS 03 | Buildings | Concept (MIMAR) | Concept |  |  | 2026-10-20 | 2026-03-15 | Completed | -219 | - | 0 | Red |  |  |  | 0
IRIS 03 | Buildings | Concept (MIMAR) | HAP Review |  |  | 2026-10-27 | 2026-03-30 | Completed | -211 | - | 0 | Red |  |  |  | 0
IRIS 03 | Buildings |  |  |  |  | 2026-12-10 | 2026-05-18 |  | -206 |  | -27 | Red |  |  |  | 0
IRIS 03 | Buildings | Concept Vaildation (KAD) | Kickoff |  | KAD |  | 2026-04-14 | Completed |  | - | 0 | Red |  |  |  | 0
IRIS 03 | Buildings | Concept Vaildation (KAD) | Enabling Package for Basement Boundaries | Ashraf / Sara | KAD | 2026-11-10 | 2026-04-27 | Completed | -197 | - | 0 | Red |  |  |  | 0
IRIS 03 | Buildings | Concept Vaildation (KAD) | BODR and Validation report for B01 & B02 | Ashraf / Sara | KAD | 2026-12-02 | 2026-05-11 | Completed | -205 | - | 0 | Red |  |  |  | 0
IRIS 03 | Buildings | Concept Vaildation (KAD) | HAP Review | Ashraf / Sara |  | 2026-12-10 | 2026-05-18 | Completed | -206 | - | 0 | Red |  |  |  | 0
IRIS 03 B.01 | Buildings |  |  |  |  | 2027-01-30 | 2026-07-26 16:48 |  | -187.3 |  | 42.7 | Green |  | IRIS 03 B.01¦Buildings |  | 0
IRIS 03 B.01 | Buildings | Schematic | Schematic Design (Arch & STR) | Ashraf / Sara | KAD | 2027-01-14 | 2026-06-28 07:12 | Inprogress | -199.7 | Yes | 14.3 | Amber |  |  | 15 | 1 | 15
IRIS 03 B.01 | Buildings | Schematic | HAP Review | Ashraf / Sara |  | 2027-01-23 | 2026-07-05 07:12 | Not Started | -201.7 | No | 21.3 | Green |  |  |  | 0
IRIS 03 B.01 | Buildings | Schematic | Schematic Design (MEP) |  | KAD |  | 2026-07-09 04:48 | Not Started |  | No | 25.2 | Green |  |  |  | 0
IRIS 03 B.01 | Buildings | Schematic | HAP Review |  |  |  | 2026-07-26 16:48 | Not Started |  | No | 42.7 | Green |  |  |  | 0
IRIS 03 B.01 | Buildings | Schematic | Cost Verification | Nour / Noha |  | 2027-01-30 | 2026-07-26 04:48 | Not Started | -187.8 | No | 42.2 | Green |  |  |  | 0
IRIS 03 B.01 | Buildings |  |  |  |  | 2027-05-24 | 2026-11-11 02:24 |  | -193.9 |  | 150.1 | Green |  |  |  | 0
IRIS 03 B.01 | Buildings | DD, IFT & IFC | 50% Detailed Design | Ashraf / Sara | KAD | 2027-03-01 | 2026-08-30 16:48 | Not Started | -182.3 | No | 77.7 | Green |  |  |  | 0
IRIS 03 B.01 | Buildings | DD, IFT & IFC | HAP Review | Ashraf / Sara |  | 2027-03-09 | 2026-09-06 16:48 | Not Started | -183.3 | No | 84.7 | Green |  |  |  | 0
IRIS 03 B.01 | Buildings | DD, IFT & IFC | 100% Detailed Design (Podium Str. IFT Package) | Ashraf / Sara | KAD | 2027-04-07 | 2026-10-04 16:48 | Not Started | -184.3 | No | 112.7 | Green |  |  |  | 0
IRIS 03 B.01 | Buildings | DD, IFT & IFC | HAP Review | Ashraf / Sara |  | 2027-04-15 | 2026-10-11 16:48 | Not Started | -185.3 | No | 119.7 | Green |  |  |  | 0
IRIS 03 B.01 | Buildings | DD, IFT & IFC | Cost Verification | Nour / Noha |  | 2027-04-22 | 2026-10-19 16:48 | Not Started | -184.3 | No | 127.7 | Green |  |  |  | 0
IRIS 03 B.01 | Buildings | DD, IFT & IFC | Permit Package | Ashraf / Sara | KAD | 2027-03-24 | 2026-10-28 12:00 | Not Started | -146.5 | No | 136.5 | Green |  |  |  | 0
IRIS 03 B.01 | Buildings | DD, IFT & IFC | IFT Package | Ashraf / Sara | KAD | 2027-05-15 | 2026-11-04 02:24 | Not Started | -191.9 | No | 143.1 | Green |  |  |  | 0
IRIS 03 B.01 | Buildings | DD, IFT & IFC | HAP Review + Final IFT Package | Ashraf / Sara |  | 2027-05-24 | 2026-11-11 02:24 | Not Started | -193.9 | No | 150.1 | Green |  |  |  | 0
IRIS 03 B.01 | Buildings |  |  |  |  | 2027-01-23 | 2026-07-26 07:12 |  | -180.7 |  | 42.3 | Green |  |  |  | 0
IRIS 03 B.01 | Buildings | Schematic | Schematic Design (Arch + Str + MEP) | Ashraf / Sara | KAD | 2027-01-07 | 2026-07-09 12:00 | Inprogress | -181.5 | No | 25.5 | Green |  |  |  | 0
IRIS 03 B.01 | Buildings | Schematic | HAP Review | Ashraf / Sara |  | 2027-01-16 | 2026-07-26 07:12 | Not Started | -173.7 | No | 42.3 | Green |  |  |  | 0
IRIS 03 B.02 | Buildings | Schematic | Cost Verification | Nour / Noha | Survtec | 2027-01-23 | 2026-07-26 07:12 | Not Started | -180.7 | No | 42.3 | Green |  | IRIS 03 B.02¦Buildings |  | 0
IRIS 03 B.02 | Buildings |  |  |  |  | 2027-05-24 | 2026-11-24 16:48 |  | -180.3 |  | 163.7 | Green |  |  |  | 0
IRIS 03 B.02 | Buildings | DD, IFT & IFC | 50% Detailed Design | Ashraf / Sara | KAD | 2027-03-01 | 2026-09-14 16:48 | Not Started | -167.3 | No | 92.7 | Green |  |  |  | 0
IRIS 03 B.02 | Buildings | DD, IFT & IFC | HAP Review | Ashraf / Sara |  | 2027-03-09 | 2026-09-22 09:36 | Not Started | -167.6 | No | 100.4 | Green |  |  |  | 0
IRIS 03 B.02 | Buildings | DD, IFT & IFC | 100% Detailed Design (Podium Str. IFT Package) | Ashraf / Sara | KAD | 2027-04-07 | 2026-10-20 16:48 | Not Started | -168.3 | No | 128.7 | Green |  |  |  | 0
IRIS 03 B.02 | Buildings | DD, IFT & IFC | HAP Review | Ashraf / Sara |  | 2027-04-15 | 2026-10-27 16:48 | Not Started | -169.3 | No | 135.7 | Green |  |  |  | 0
IRIS 03 B.02 | Buildings | DD, IFT & IFC | Cost Verification | Nour / Noha |  | 2027-04-22 | 2026-11-03 16:48 | Not Started | -169.3 | No | 142.7 | Green |  |  |  | 0
IRIS 03 B.02 | Buildings | DD, IFT & IFC | Permit Package | Ashraf / Sara | KAD | 2027-03-24 | 2026-11-12 19:12 | Not Started | -131.2 | No | 151.8 | Green |  |  |  | 0
IRIS 03 B.02 | Buildings | DD, IFT & IFC | IFT Package | Ashraf / Sara | KAD | 2027-05-15 | 2026-11-17 16:48 | Not Started | -178.3 | No | 156.7 | Green |  |  |  | 0
IRIS 03 B.02 | Buildings | DD, IFT & IFC | HAP Review + Final IFT Package | Ashraf / Sara |  | 2027-05-24 | 2026-11-24 16:48 | Not Started | -180.3 | No | 163.7 | Green |  |  |  | 0
IRIS 03 | Buildings |  |  |  |  | 2026-10-01 07:12 | 2026-08-30 |  | -32.3 |  | 77 | Green |  |  |  | 0
IRIS 03 | Buildings | IRIS 03 - Structure Packages | 100% Detailed Design | Ashraf / Sara | KAD | 2026-08-02 07:12 | 2026-07-01 | Not Started | -32.3 | Yes | 17 | Amber |  |  | 16 | 1 | 16
IRIS 03 | Buildings | IRIS 03 - Structure Packages | 100% Str Detailed Design Peer Review | Ashraf / Sara |  | 2026-08-09 07:12 | 2026-07-08 | Not Started | -32.3 | No | 24 | Green |  |  |  | 0
IRIS 03 | Buildings | IRIS 03 - Structure Packages | HAP Review | Ashraf / Sara | HAP | 2026-08-09 07:12 | 2026-07-08 | Not Started | -32.3 | No | 24 | Green |  |  |  | 0
IRIS 03 | Buildings | IRIS 03 - Structure Packages | Tender Package for 2 Buildings + Basement Inprogress Package | Ashraf / Sara | KAD | 2026-09-06 07:12 | 2026-08-05 | Not Started | -32.3 | No | 52 | Green |  |  |  | 0
IRIS 03 | Buildings | IRIS 03 - Structure Packages | Tender Package Peer Review | Ashraf / Sara |  | 2026-09-13 07:12 | 2026-08-12 | Not Started | -32.3 | No | 59 | Green |  |  |  | 0
IRIS 03 | Buildings | IRIS 03 - Structure Packages | HAP Review | Ashraf / Sara | HAP | 2026-09-17 07:12 | 2026-08-16 | Not Started | -32.3 | No | 63 | Green |  |  |  | 0
IRIS 03 | Buildings | IRIS 03 - Structure Packages | Final Tender Package for 2 Buildings + Basement Final Package | Ashraf / Sara | KAD | 2026-10-01 07:12 | 2026-08-30 | Not Started | -32.3 | No | 77 | Green |  |  |  | 0
IRIS 03 | Masterplan |  |  |  |  | 2025-12-28 | 2026-03-09 |  | 71 |  | -97 | Red |  | IRIS 03¦Masterplan |  | 0
IRIS 03 | Masterplan | IRIS 03 - Masterplan | 100% Detailed Design | Ashraf / Sara | YBA | 2025-10-29 |  | Not Started |  |  |  | Amber |  |  |  | 0
IRIS 03 | Masterplan | IRIS 03 - Masterplan | HAP Review | Ashraf / Sara |  | 2025-11-13 |  | Not Started |  |  |  | Amber |  |  |  | 0
IRIS 03 | Masterplan | IRIS 03 - Masterplan | Ministerial Decree | Ashraf / Sara | YBA | 2025-10-29 |  | Not Started |  |  |  | Amber |  |  |  | 0
IRIS 03 | Masterplan | IRIS 03 - Masterplan | IFT Package | Ashraf / Sara | YBA | 2025-12-13 | 2026-03-02 | Completed | 79 | - | 0 | Red |  |  |  | 0
IRIS 03 | Masterplan | IRIS 03 - Masterplan | HAP Review + Final IFT Package | Ashraf / Sara |  | 2025-12-28 | 2026-03-09 | Completed | 71 | - | 0 | Red |  |  |  | 0
IRIS 03 | Infrastructure |  |  |  |  | 2027-07-08 | 2027-01-06 16:48 |  | -182.3 |  | 206.7 | Green |  | IRIS 03¦Infrastructure |  | 0
IRIS 03 | Infrastructure | IRIS 03 Infra | IFT Revised Package for IRIS 03 | Ashraf / Sara | Shaker | 2027-03-30 | 2026-09-28 16:48 | Not Started | -182.3 | No | 106.7 | Green |  |  |  | 0
IRIS 03 | Infrastructure | IRIS 03 Infra | HAP Review + IFT Final Package | Ashraf / Sara |  | 2027-04-14 | 2026-10-13 16:48 | Not Started | -182.3 | No | 121.7 | Green |  |  |  | 0
IRIS 03 | Infrastructure | IRIS 03 Infra | Tender Process |  |  | 2027-07-08 | 2027-01-06 16:48 | Not Started | -182.3 | No | 206.7 | Green |  |  |  | 0
IRIS 03 | Landscape |  |  |  |  | 2027-10-20 | 2026-11-17 |  | -337 |  | 156 | Green |  | IRIS 03¦Landscape |  | 0
IRIS 03 | Landscape | Landscape - IRIS 03 | Concept Design - IRIS 03 | Hoda / Dina | Cracknell | 2025-10-13 | 2025-10-13 | Completed | 0 | - | -244 | Red |  |  |  | 0
IRIS 03 | Landscape | Landscape - IRIS 03 | HAP Review | Hoda / Dina |  | 2025-10-28 | 2025-10-28 | Completed | 0 | - | -229 | Red |  |  |  | 0
IRIS 03 | Landscape | Landscape - IRIS 03 | 50% Schematic Design - Iris 03 | Hoda / Dina | Cracknell | 2027-02-20 | 2026-06-01 | Completed | -264 | - | -13 | Red |  |  |  | 0
IRIS 03 | Landscape | Landscape - IRIS 03 | HAP Review | Hoda / Dina |  | 2027-03-07 | 2026-06-25 | Inprogress | -255 | Yes | 11 | Amber |  |  | 17 | 1 | 17
IRIS 03 | Landscape | Landscape - IRIS 03 | Cost Verification | Nour / Hoda | Survtec | 2027-03-14 | 2026-06-24 | Not Started | -263 | Yes | 10 | Amber |  |  | 18 | 1 | 18
IRIS 03 | Landscape | Landscape - IRIS 03 | 100% Schematic Design - Iris 03 | Hoda / Dina | Cracknell | 2027-04-05 | 2026-07-21 | Not Started | -258 | No | 37 | Green |  |  |  | 0
IRIS 03 | Landscape | Landscape - IRIS 03 | HAP Review | Hoda / Dina |  | 2027-04-21 | 2026-08-06 | Not Started | -258 | No | 53 | Green |  |  |  | 0
IRIS 03 | Landscape | Landscape - IRIS 03 | Landscape Schematic Review & validation | Hoda / Dina | Sites | 2027-05-05 | 2026-08-04 | Not Started | -274 | No | 51 | Green |  |  |  | 0
|  | Landscape - IRIS 03 | HAP Review | Hoda / Dina |  | 2027-05-19 | 2026-08-04 | Not Started | -288 | No | 51 | Green |  | ¦ |  | 0
IRIS 03 | Landscape | Landscape - IRIS 03 | Cost Plan | Nour / Hoda | Survtec | 2027-05-19 | 2026-08-18 | Not Started | -274 | No | 65 | Green |  |  |  | 0
|  | Landscape - IRIS 03 | 50% Design Development | Hoda / Dina | Sites | 2027-06-30 | 2026-08-04 | Not Started | -330 | No | 51 | Green |  | ¦ |  | 0
|  | Landscape - IRIS 03 | HAP Review | Hoda / Dina |  | 2027-07-14 | 2026-08-04 | Not Started | -344 | No | 51 | Green |  | ¦ |  | 0
IRIS 03 | Landscape | Landscape - IRIS 03 | 100% Design Development | Hoda / Dina | Sites | 2027-08-25 | 2026-09-08 | Not Started | -351 | No | 86 | Green |  |  |  | 0
IRIS 03 | Landscape | Landscape - IRIS 03 | HAP Review | Hoda / Dina |  | 2027-09-08 | 2026-09-22 | Not Started | -351 | No | 100 | Green |  |  |  | 0
IRIS 03 | Landscape | Landscape - IRIS 03 | Cost Plan | Nour / Hoda | Survtec | 2027-09-15 | 2026-09-29 | Not Started | -351 | No | 107 | Green |  |  |  | 0
IRIS 03 | Landscape | Landscape - IRIS 03 | Landscape IFT | Hoda / Dina | Sites | 2027-10-06 | 2026-11-03 | Not Started | -337 | No | 142 | Green |  |  |  | 0
IRIS 03 | Landscape | Landscape - IRIS 03 | HAP Review | Hoda / Dina |  | 2027-10-20 | 2026-11-17 | Not Started | -337 | No | 156 | Green |  |  |  | 0
IRIS 03 | Authorities |  |  |  |  | 2027-06-16 | 2027-01-27 |  | -140 |  | 227 | Green |  | IRIS 03¦Authorities |  | 0
IRIS 03 | Authorities | Authorities - IRIS 03 | Ministerial decree | Afifi |  | 2026-02-18 | 2026-11-04 | Not Started | 259 | No | 143 | Green |  |  |  | 0
IRIS 03 | Authorities | Authorities - IRIS 03 | Egyptian Institution for Construction Civil Liability Insurance | Afifi |  | 2027-05-05 | 2026-12-16 | Not Started | -140 | No | 185 | Green |  |  |  | 0
IRIS 03 | Authorities | Authorities - IRIS 03 | Permits | Afifi |  | 2027-06-16 | 2027-01-27 | Not Started | -140 | No | 227 | Green |  |  |  | 0
IRIS 03 | Plot Fences | [5 empty] | 2026-07-16 |  |  |  | 32 | Green |  | IRIS 03¦Plot Fences |  | 0
IRIS 03 | Plot Fences | Plot Fences - IRIS 03 | Tender Package | Adham |  |  | 2026-07-09 | Not Started |  | No | 25 | Green |  |  |  | 0
IRIS 03 | Plot Fences | Plot Fences - IRIS 03 | HAP Review |  |  |  | 2026-07-16 | Not Started |  | No | 32 | Green |  |  |  | 0
IRIS 03 | Parcel Fence | [5 empty] | 2025-10-08 |  |  |  | -249 | Red |  | IRIS 03¦Parcel Fence |  | 0
IRIS 03 | Parcel Fence | Parcel Fence - IRIS 03 | HAP For IFT Package |  |  |  | 2025-10-08 | Completed |  | - | -249 | Red |  |  |  | 0
Parcel 07 | Infrastructure |  |  |  |  | 2025-02-02 | 2025-02-02 |  | 0 |  | -497 | Red |  | Parcel 07¦Infrastructure |  | 0
Parcel 07 | Infrastructure | Infra - Shaker (Parcel 07 & Parcel 14) | Data to be send by HAP |  |  | 2024-11-07 | 2024-11-07 | Not Started | 0 | Yes | -584 | Red |  |  | 19 | 1 | 19
Parcel 07 | Infrastructure | Infra - Shaker (Parcel 07 & Parcel 14) | Infra IFC Submission |  |  | 2024-12-05 | 2024-12-05 | Completed | 0 | - | -556 | Red |  |  |  | 0
Parcel 07 | Infrastructure | Infra - Shaker (Parcel 07 & Parcel 14) | HAP Review + Final IFC Submission |  |  | 2025-02-02 | 2025-02-02 | Completed | 0 | - | -497 | Red |  |  |  | 0
Parcel 07 | Fit-out |  |  |  |  | 2025-11-30 | 2026-05-12 |  | 163 |  | -33 | Red |  | Parcel 07¦Fit-out |  | 0
Parcel 07 | Fit-out | RMC - MEP Packages & ID - KH Studio | Revised Submission for Patch 01 Buildings IFT |  |  | 2025-06-18 | 2025-06-18 | Completed | 0 | - | -361 | Red |  |  |  | 0
Parcel 07 | Fit-out | RMC - MEP Packages & ID - KH Studio | HAP Review |  |  | 2025-06-19 | 2025-06-19 | Completed | 0 | - | -360 | Red |  |  |  | 0
Parcel 07 | Fit-out | RMC - MEP Packages & ID - KH Studio | Revised Submission for Basement & Incl. ID 15-Jun-25 |  |  | 2025-06-25 | 2025-06-25 | Completed | 0 | - | -354 | Red |  |  |  | 0
Parcel 07 | Fit-out | RMC - MEP Packages & ID - KH Studio | HAP Review |  |  | 2025-06-26 | 2025-06-26 | Completed | 0 | - | -353 | Red |  |  |  | 0
Parcel 07 | Fit-out | RMC - MEP Packages & ID - KH Studio | Revised Submission for Patch 02 Buildings IFT (B01,03,04) |  |  | 2025-11-15 | 2025-11-13 | Completed | -2 | - | -213 | Red |  |  |  | 0
Parcel 07 | Fit-out | RMC - MEP Packages & ID - KH Studio | HAP Review |  |  | 2025-11-30 | 2025-11-30 | Completed | 0 | - | -196 | Red |  |  |  | 0
Parcel 07 | Fit-out | RMC - MEP Packages & ID - KH Studio | Revised Submission for Patch 03 Buildings IFT (A12,A13) |  |  | 2025-11-01 | 2025-11-13 | Completed | 12 | - | -213 | Red |  |  |  | 0
Parcel 07 | Fit-out | RMC - MEP Packages & ID - KH Studio | HAP Review |  |  | 2025-11-16 | 2025-11-25 | Completed | 9 | - | -201 | Red |  |  |  | 0
Parcel 07 | Tenant manual |  |  |  |  | 2026-05-14 | 2026-06-29 |  | 46 |  | 15 | Amber |  | Parcel 07¦Tenant manual |  | 0
Parcel 07 | Tenant manual | Tenant manual - Parcel 07 | Shops Tenant Manual (Sample) | Ashraf / Sara | RMC | 2026-04-30 | 2026-06-01 | Completed | 32 | - | -13 | Red |  |  |  | 0
Parcel 07 | Tenant manual | Tenant manual - Parcel 07 | HAP Review | Ashraf / Sara |  | 2026-05-07 | 2026-06-29 | Inprogress | 53 | Yes | 15 | Amber |  |  | 20 | 1 | 20
Parcel 07 | Tenant manual | Tenant manual - Parcel 07 | Office Tenant Manual (Sample) | Ashraf / Sara | RMC | 2026-05-07 | 2026-06-01 | Completed | 25 | - | -13 | Red |  |  |  | 0
Parcel 07 | Tenant manual | Tenant manual - Parcel 07 | HAP Review | Ashraf / Sara |  | 2026-05-14 | 2026-06-29 | Inprogress | 46 | Yes | 15 | Amber |  |  | 21 | 1 | 21
Parcel 07 | Authorities | [5 empty] | 2026-10-11 |  |  |  | 119 | Green |  | Parcel 07¦Authorities |  | 0
Parcel 07 | Authorities | Authorities - Parcel 07 | Ministerial decree | Afifi |  |  | 2026-07-15 | Inprogress |  | No | 31 | Green |  |  |  | 0
Parcel 07 | Authorities | Authorities - Parcel 07 | Egyptian Institution for Construction Civil Liability Insurance | Afifi |  |  | 2026-08-26 | Not Started |  | No | 73 | Green |  |  |  | 0
Parcel 07 | Authorities | Authorities - Parcel 07 | Permits | Afifi |  |  | 2026-10-11 | Not Started |  | No | 119 | Green |  |  |  | 0
Parcel 07 | Landscape |  |  |  |  | 2026-02-02 | 2026-02-02 |  | 0 |  | -132 | Red |  | Parcel 07¦Landscape |  | 0
Parcel 07 | Landscape | Landscape | 100% Tender Package |  |  | 2026-02-01 | 2026-02-01 | Completed | 0 | - | -133 | Red |  |  |  | 0
Parcel 07 | Landscape | Landscape | HAP Review |  |  | 2026-02-02 | 2026-02-02 | Completed | 0 | - | -132 | Red |  |  |  | 0
Parcel 07 | LEED Certificate |  |  |  |  | 2026-10-01 | 2026-10-06 |  | 5 |  | 114 | Green |  | Parcel 07¦LEED Certificate |  | 0
Parcel 07 | LEED Certificate | LEED Certificate Process | LEED Online Documentation Design phase) | Ashraf / Sara | ES | 2026-06-24 | 2026-06-14 | Completed | -10 | - | 0 | Amber |  |  |  | 0
Parcel 07 | LEED Certificate | LEED Certificate Process | Preliminary Design review Fees | Ashraf / Sara | HAP | 2026-06-25 | 2026-06-30 | Inprogress | 5 | Yes | 16 | Amber |  |  | 22 | 1 | 22
Parcel 07 | LEED Certificate | LEED Certificate Process | Preliminary Design review | Ashraf / Sara | USGBC | 2026-07-30 | 2026-08-04 | Not Started | 5 | No | 51 | Green |  |  |  | 0
Parcel 07 | LEED Certificate | LEED Certificate Process | LEED Consultant response | Ashraf / Sara | ES | 2026-08-27 | 2026-09-01 | Not Started | 5 | No | 79 | Green |  |  |  | 0
Parcel 07 | LEED Certificate | LEED Certificate Process | Final design review | Ashraf / Sara | USGBC | 2026-10-01 | 2026-10-06 | Not Started | 5 | No | 114 | Green |  |  |  | 0
Parcel 07 | LEED Certificate | LEED Certificate Process | Construction phase | Ashraf / Sara | HAP |  |  | Not Started |  |  |  | Amber |  |  |  | 0
Hotel |  | LEED Certificate Process | Launch Date |  |  | 2026-09-09 | 2027-01-05 | Not Started | 118 | No | 205 | Green |  | Hotel¦ |  | 0
Hotel | Buildings | LEED Certificate Process | Concept & Schematic Design Stage |  |  | 2026-11-17 | 2027-01-06 | Not Started | 50 | No | 206 | Green |  | Hotel¦Buildings |  | 0
Hotel | Buildings | LEED Certificate Process | Comencment Date |  |  | 2025-11-30 | 2025-11-30 | Completed | 0 | Yes | -196 | Red |  |  | 23 | 1 | 23
Hotel | Buildings | LEED Certificate Process | Project Build up |  |  | 2026-02-01 | 2026-02-01 | Completed | 0 | Yes | -133 | Red |  |  | 24 | 1 | 24
Hotel | Buildings | LEED Certificate Process | HAP Review |  |  | 2026-02-09 | 2026-02-09 | Completed | 0 | Yes | -125 | Red |  |  | 25 | 1 | 25
Hotel | Buildings | LEED Certificate Process | Offices 50% Concept Design – Architecture |  |  | 2026-03-30 | 2026-03-30 | Completed | 0 | Yes | -76 | Red |  |  | 26 | 1 | 26
Hotel | Buildings | LEED Certificate Process | HOTEL 50% Concept Design – Architecture |  |  | 2026-03-30 | 2026-03-30 | Completed | 0 | Yes | -76 | Red |  |  | 27 | 1 | 27
Hotel | Buildings | LEED Certificate Process | HAP Review |  |  | 2026-04-07 | 2026-04-27 | Completed | 20 | Yes | -48 | Red |  |  | 28 | 1 | 28
Hotel | Buildings | LEED Certificate Process | Project Build-up (Hotel & Offices) |  |  |  | 2026-05-18 | Completed |  | Yes | -27 | Red |  |  | 29 | 1 | 29
Hotel | Buildings | LEED Certificate Process | HAP Review |  |  |  | 2026-05-25 | Completed |  | Yes | -20 | Red |  |  | 30 | 1 | 30
Hotel | Buildings | LEED Certificate Process | Adha Vacation |  |  | 2026-06-08 | 2026-05-31 | Completed | -8 | Yes | -14 | Red |  |  | 31 | 1 | 31
Hotel | Buildings | LEED Certificate Process | 50% Masterplan and Architecture Concept (Hotel and Office Buildings |  |  |  | 2026-06-29 | Inprogress |  | Yes | 15 | Amber |  |  | 32 | 1 | 32
Hotel | Buildings | LEED Certificate Process | HAP Review |  |  |  | 2026-07-07 | Not Started |  | No | 23 | Green |  |  |  | 0
Hotel | Buildings | LEED Certificate Process | Project Budget Review and Vaildation 1 |  |  | 2026-04-15 | 2026-07-07 | Not Started | 83 | No | 23 | Green |  |  |  | 0
Hotel | Buildings | LEED Certificate Process | Offices 100% Concept Design – Architecture & Masterplan |  |  | 2026-05-20 | 2026-08-12 | Not Started | 84 | No | 59 | Green |  |  |  | 0
Hotel | Buildings | LEED Certificate Process | HOTEL 100% Concept Design – Architecture & Masterplan |  |  | 2026-05-20 | 2026-08-12 | Not Started | 84 | No | 59 | Green |  |  |  | 0
Hotel | Buildings | LEED Certificate Process | HAP Review |  |  | 2026-05-31 | 2026-08-20 | Not Started | 81 | No | 67 | Green |  |  |  | 0
Hotel | Buildings | LEED Certificate Process | Project Budget Review and Vaildation 2 |  |  | 2026-06-16 | 2026-08-20 | Not Started | 65 | Yes | 67 | Green |  |  | 33 | 1 | 33
Hotel | Buildings | LEED Certificate Process | HOTEL 100% Concept Design – Interior Design |  |  | 2026-06-17 | 2026-10-15 | Not Started | 120 | Yes | 123 | Green |  |  | 34 | 1 | 34
Hotel | Buildings | LEED Certificate Process | Offices 100% Concept Design – Interior Design |  |  |  | 2026-10-15 | Not Started |  | Yes | 123 | Green |  |  | 35 | 1 | 35
Hotel | Buildings | LEED Certificate Process | HAP Review |  |  | 2026-06-28 | 2026-10-22 | Not Started | 116 | Yes | 130 | Green |  |  | 36 | 1 | 36
Hotel | Buildings | LEED Certificate Process | Project Budget Review and Vaildation 3 |  |  | 2026-07-27 | 2026-11-12 | Not Started | 108 | Yes | 151 | Green |  |  | 37 | 1 | 37
Hotel | Buildings | LEED Certificate Process | Marketing Material - Development |  |  | 2026-08-09 | 2026-12-03 | Not Started | 116 | Yes | 172 | Green |  |  | 38 | 1 | 38
Hotel | Buildings | LEED Certificate Process | Marketing Material - Marketing |  |  | 2026-08-24 | 2026-12-20 | Not Started | 118 | Yes | 189 | Green |  |  | 39 | 1 | 39
Hotel | Buildings | LEED Certificate Process | Budget & Cashflow |  |  | 2026-09-01 | 2026-12-28 | Not Started | 118 | Yes | 197 | Green |  |  | 40 | 1 | 40
Hotel | Buildings | LEED Certificate Process | Run BM & Pricing |  |  | 2026-09-09 | 2027-01-05 | Not Started | 118 | Yes | 205 | Green |  |  | 41 | 1 | 41
Hotel | Buildings | LEED Certificate Process | Sales Induction |  |  | 2026-09-16 | 2027-01-06 | Not Started | 112 | Yes | 206 | Green |  |  | 42 | 1 | 42
Hotel | Buildings | LEED Certificate Process | 100% Schematic Design (Hotel and Office Buildings) |  |  | 2026-10-26 | 2026-12-09 | Not Started | 44 | Yes | 178 | Green |  |  | 43 | 1 | 43
Hotel | Buildings | LEED Certificate Process | Operator Review |  |  | 2026-11-10 | 2026-12-23 | Not Started | 43 | Yes | 192 | Green |  |  | 44 | 1 | 44
Hotel | Buildings | LEED Certificate Process | HAP Review |  |  | 2026-11-10 | 2026-12-23 | Not Started | 43 | Yes | 192 | Green |  |  | 45 | 1 | 45
Hotel | Buildings | LEED Certificate Process | Conslidated Comments |  |  | 2026-11-17 | 2026-12-30 | Not Started | 43 | Yes | 199 | Green |  |  | 46 | 1 | 46
Hotel | Buildings | LEED Certificate Process | Cost Verification |  |  | 2026-11-24 | 2027-01-06 | Not Started | 43 | Yes | 206 | Green |  |  | 47 | 1 | 47
Hotel | Buildings | LEED Certificate Process | 100% Interior Schematic Design (Hotel and Office Buildings) |  |  |  | 2027-02-04 | Not Started |  | Yes | 235 | Green |  |  | 48 | 1 | 48
Hotel | Buildings | LEED Certificate Process | Operator Review |  |  |  | 2027-02-18 | Not Started |  | Yes | 249 | Green |  |  | 49 | 1 | 49
Hotel | Buildings | LEED Certificate Process | HAP Review |  |  |  | 2027-02-18 | Not Started |  | Yes | 249 | Green |  |  | 50 | 1 | 50
Hotel | Buildings | LEED Certificate Process | Conslidated Comments |  |  |  | 2027-02-25 | Not Started |  | Yes | 256 | Green |  |  | 51 | 1 | 51
Hotel | Buildings | LEED Certificate Process | Cost Verification |  |  |  | 2027-03-04 | Not Started |  | Yes | 263 | Green |  |  | 52 | 1 | 52
Hotel | Buildings | LEED Certificate Process | Mockup Package |  |  | 2026-12-15 | 2027-01-27 | Not Started | 43 | Yes | 227 | Green |  |  | 53 | 1 | 53
Hotel | Buildings | LEED Certificate Process | HAP Review |  |  | 2026-12-29 | 2027-02-10 | Not Started | 43 | Yes | 241 | Green |  |  | 54 | 1 | 54
Hotel | Buildings | LEED Certificate Process | Local Design Tender |  |  | 2026-06-17 | 2026-07-29 | Not Started | 42 | Yes | 45 | Green |  |  | 55 | 1 | 55
Hotel | Buildings | LEED Certificate Process | Tender to Assign Consultant |  |  | 2026-06-17 | 2026-07-29 | Not Started | 42 | Yes | 45 | Green |  |  | 56 | 1 | 56
Hotel | Buildings | LEED Certificate Process | Buildings Including ID |  |  | 2027-06-15 | 2027-08-04 | Not Started | 50 | Yes | 416 | Green |  |  | 57 | 1 | 57
Hotel | Buildings | LEED Certificate Process | Commencement date |  |  | 2026-06-17 | 2026-07-29 | Not Started | 42 | Yes | 45 | Green |  |  | 58 | 1 | 58
Hotel | Buildings | LEED Certificate Process | Peer Review (Concept Validation) |  |  | 2026-07-12 | 2026-09-02 | Not Started | 52 | Yes | 80 | Green |  |  | 59 | 1 | 59
Hotel | Buildings | LEED Certificate Process | HAP Review |  |  |  | 2026-09-09 | Not Started |  | Yes | 87 | Green |  |  | 60 | 1 | 60
Hotel | Buildings | LEED Certificate Process | Schematic Validation |  |  | 2026-06-03 | 2026-12-30 | Not Started | 210 | Yes | 199 | Green |  |  | 61 | 1 | 61
Hotel | Buildings | LEED Certificate Process | HAP Review |  |  | 2026-06-17 | 2027-01-13 | Not Started | 210 | Yes | 213 | Green |  |  | 62 | 1 | 62
Hotel | Buildings | LEED Certificate Process | Detailed Design 50% & Specialist Consultant (Kitchen, Sauna& ETC..) |  |  | 2027-01-12 | 2027-03-03 | Not Started | 50 | Yes | 262 | Green |  |  | 63 | 1 | 63
Hotel | Buildings | LEED Certificate Process | Operator Review |  |  | 2027-01-26 | 2027-03-17 | Not Started | 50 | Yes | 276 | Green |  |  | 64 | 1 | 64
Hotel | Buildings | LEED Certificate Process | HAP Review |  |  | 2027-01-26 | 2027-03-17 | Not Started | 50 | Yes | 276 | Green |  |  | 65 | 1 | 65
Hotel | Buildings | LEED Certificate Process | Conslidated Comments |  |  | 2027-02-02 | 2027-03-24 | Not Started | 50 | Yes | 283 | Green |  |  | 66 | 1 | 66
Hotel | Buildings | LEED Certificate Process | Detailed Design 100% & Specialist Consultant (Kitchen, Sauna& ETC..) |  |  | 2027-03-30 | 2027-05-19 | Not Started | 50 | Yes | 339 | Green |  |  | 67 | 1 | 67
Hotel | Buildings | LEED Certificate Process | Permits Drawings |  |  | 2027-04-27 | 2027-06-16 | Not Started | 50 | Yes | 367 | Green |  |  | 68 | 1 | 68
Hotel | Buildings | LEED Certificate Process | Operator Review |  |  | 2027-04-13 | 2027-06-02 | Not Started | 50 | Yes | 353 | Green |  |  | 69 | 1 | 69
Hotel | Buildings | LEED Certificate Process | HAP Review |  |  | 2027-04-13 | 2027-06-02 | Not Started | 50 | Yes | 353 | Green |  |  | 70 | 1 | 70
Hotel | Buildings | LEED Certificate Process | Conslidated Comments |  |  | 2027-04-20 | 2027-06-09 | Not Started | 50 | Yes | 360 | Green |  |  | 71 | 1 | 71
Hotel | Buildings | LEED Certificate Process | Enabling Package (Skeleton Package) |  |  | 2027-04-20 | 2027-06-09 | Not Started | 50 | Yes | 360 | Green |  |  | 72 | 1 | 72
Hotel | Buildings | LEED Certificate Process | HAP Review |  |  | 2027-04-20 | 2027-06-09 | Not Started | 50 | Yes | 360 | Green |  |  | 73 | 1 | 73
Hotel | Buildings | LEED Certificate Process | Cost Verification |  |  | 2027-04-27 | 2027-06-16 | Not Started | 50 | Yes | 367 | Green |  |  | 74 | 1 | 74
Hotel | Buildings | LEED Certificate Process | Tender Package |  |  | 2027-06-01 | 2027-07-21 | Not Started | 50 | Yes | 402 | Green |  |  | 75 | 1 | 75
Hotel | Buildings | LEED Certificate Process | HAP Review |  |  | 2027-06-15 | 2027-08-04 | Not Started | 50 | Yes | 416 | Green |  |  | 76 | 1 | 76
Hotel | Masterplan | LEED Certificate Process | Masterplan |  |  | 2026-07-26 | 2026-12-10 | Not Started | 137 | Yes | 179 | Green |  | Hotel¦Masterplan | 77 | 1 | 77
Hotel | Masterplan | LEED Certificate Process | VO With YBA |  |  | 2026-05-31 | 2026-08-20 | Not Started | 81 | Yes | 67 | Green |  |  | 78 | 1 | 78
Hotel | Masterplan | LEED Certificate Process | 100% Schematic Design (Grading Package) |  |  |  | 2026-09-17 | Not Started |  | Yes | 95 | Green |  |  | 79 | 1 | 79
Hotel | Masterplan | LEED Certificate Process | HAP Review |  |  |  | 2026-09-24 | Not Started |  | Yes | 102 | Green |  |  | 80 | 1 | 80
Hotel | Masterplan | LEED Certificate Process | Grading Package |  |  |  | 2026-10-08 | Not Started
Hotel | Masterplan | LEED Certificate Process | HAP Review |  |  |  | 2026-10-15 | Not Started
Hotel | Masterplan | LEED Certificate Process | 100% Detailed Design |  |  | 2026-07-19 | 2026-11-12 | Not Started
Hotel | Masterplan | LEED Certificate Process | Hap Review |  |  | 2026-07-26 | 2026-11-19 | Not Started
Hotel | Masterplan | LEED Certificate Process | Ministerial Decree |  |  | 2026-06-07 | 2026-12-03 | Not Started
Hotel | Masterplan | LEED Certificate Process | Hap Review |  |  | 2026-06-14 | 2026-12-10 | Not Started
Hotel | Landscape | LEED Certificate Process | Landscape |  |  | 2027-01-24 | 2027-05-20 | Not Started
Hotel | Landscape | LEED Certificate Process | VO With Sites |  |  | 2026-07-26 | 2026-11-19 | Not Started
Hotel | Landscape | LEED Certificate Process | 50% Schematic |  |  | 2026-08-23 | 2026-12-17 | Not Started
Hotel | Landscape | LEED Certificate Process | HAP Review |  |  | 2026-09-06 | 2026-12-31 | Not Started
Hotel | Landscape | LEED Certificate Process | 100% Schematic |  |  | 2026-10-04 | 2027-01-28 | Not Started
Hotel | Landscape | LEED Certificate Process | HAP Review |  |  | 2026-10-18 | 2027-02-11 | Not Started
Hotel | Landscape | LEED Certificate Process | 100% Detailed Design |  |  | 2026-11-29 | 2027-03-25 | Not Started
Hotel | Landscape | LEED Certificate Process | HAP Review |  |  | 2026-12-13 | 2027-04-08 | Not Started
Hotel | Landscape | LEED Certificate Process | Cost Verification |  |  | 2026-12-13 | 2027-04-08 | Not Started
Hotel | Landscape | LEED Certificate Process | Tender Package |  |  | 2027-01-10 | 2027-05-06 | Not Started
Hotel | Landscape | LEED Certificate Process | HAP Review |  |  | 2027-01-24 | 2027-05-20 | Not Started
|  | LEED Certificate Process | Mockup Tender Process |  |  | 2027-02-23 | 2027-04-07 | Not Started
|  | LEED Certificate Process | Tender Process |  |  | 2027-02-09 | 2027-03-24 | Not Started
|  | LEED Certificate Process | Contractor Awarding |  |  | 2027-02-23 | 2027-04-07 | Not Started
|  | LEED Certificate Process | Tender Process |  |  | 2027-10-05 | 2027-11-24 | Not Started
|  | LEED Certificate Process | Earth Work Contractor Awarding |  |  | 2027-05-18 | 2026-10-15 | Not Started
|  | LEED Certificate Process | Tender Process for Enabling package |  |  | 2027-07-13 | 2027-09-01 | Not Started
|  | LEED Certificate Process | Contractor Awarding |  |  | 2027-08-10 | 2027-09-29 | Not Started
|  | LEED Certificate Process | Tender Process |  |  | 2027-09-07 | 2027-10-27 | Not Started
|  | LEED Certificate Process | Contractor Awarding |  |  | 2027-10-05 | 2027-11-24 | Not Started
Hotel | Authorities | LEED Certificate Process | Authorities Issuance |  |  | 2027-04-27 | 2027-10-27 | Not Started
Hotel | Authorities | LEED Certificate Process | Ministerial decree NUCA |  |  | 2026-06-14 | 2027-03-04 | Not Started
Hotel | Authorities | LEED Certificate Process | Rough Grading and Earth Work |  |  | 2027-04-20 | 2027-07-07 | Not Started
Hotel | Authorities | LEED Certificate Process | Touristic Licenses |  |  | 2027-04-20 | 2027-08-04 | Not Started
Hotel | Authorities | LEED Certificate Process | Egyptian Institution for Construction Civil Liability Insurance & Civil Defense |  |  | 2027-04-27 | 2027-09-15 | Not Started
Hotel | Authorities | LEED Certificate Process | Mineral licenses-Excavation |  |  | 2027-04-27 | 2027-10-27 | Not Started
|  | LEED Certificate Process | Construction |  |  | 2029-10-02 | 2029-11-21 | Not Started
|  | LEED Certificate Process | Mockup Construction |  |  | 2027-08-24 | 2027-10-06 | Not Started
|  | LEED Certificate Process | Earth Work & Rough Grading |  |  | 2027-01-19 | 2027-04-01 | Not Started
|  | LEED Certificate Process | Engineering and Mobilization |  |  | 2027-09-07 | 2027-10-27 | Not Started
|  | LEED Certificate Process | Construction of Enabling Package (Skeleton & Podium Package) |  |  | 2028-10-31 | 2028-12-20 | Not Started
|  | LEED Certificate Process | Buildings Construction (Arch + MEP) |  |  | 2029-10-02 | 2029-11-21 | Not Started
|  | LEED Certificate Process | Roads |  |  | 2029-10-02 | 2029-11-21 | Not Started
|  | LEED Certificate Process | Landscape |  |  | 2029-10-02 | 2029-11-21 | Not Started
|  | LEED Certificate Process | Long Lead Items Procurement |  |  | 2029-06-12 | 2029-08-01 | Not Started
|  | LEED Certificate Process | Hotel Opertional Licenses |  |  | 2030-06-11 | 2030-07-31 | Not Started
|  | LEED Certificate Process | Touristic Licenses |  |  | 2030-01-22 | 2030-03-13 | Not Started
|  | LEED Certificate Process | Compliance with Civil Defense Requirements |  |  | 2030-03-19 | 2030-05-08 | Not Started
|  | LEED Certificate Process | Security Authorities |  |  | 2030-06-11 | 2030-07-31 | Not Started
|  | LEED Certificate Process | Hotel Soft Openeing |  |  | 2030-07-09 | 2030-08-28 | Not Started
|  | LEED Certificate Process | Soft Openeing |  |  | 2030-07-09 | 2030-08-28 | Not Started
Parcel 15 | Masterplan |  |  |  |  | 2024-11-12 | 2024-11-12
Parcel 15 | Masterplan | Masterplan - Detailed Design | Revised Package |  |  | 2024-11-06 | 2024-11-06 | Completed
Parcel 15 | Masterplan | Masterplan - Detailed Design | HAP Review |  |  | 2024-11-12 | 2024-11-12 | Completed
Parcel 15 | Infrastructure |  |  |  |  | 2025-02-13 | 2025-02-13
Parcel 15 | Infrastructure | Infrastructure | Revised Package |  |  | 2025-01-09 | 2025-01-09 | Completed
Parcel 15 | Infrastructure | Infrastructure | HAP Review |  |  | 2025-02-13 | 2025-02-13 | Completed
Parcel 15 | Landscape |  |  |  |  | 2025-06-10 | 2025-06-10
Parcel 15 | Landscape | Landscape | Schematic Submission |  |  | 2024-11-27 | 2024-11-27 | Completed
Parcel 15 | Landscape | Landscape | HAP Review |  |  | 2024-12-12 | 2024-12-12 | Completed
Parcel 15 | Landscape | Landscape | DD Submission |  |  | 2025-01-13 | 2025-01-13 | Completed
Parcel 15 | Landscape | Landscape | HAP Review |  |  | 2025-01-15 | 2025-01-15 | Completed
Parcel 15 | Landscape | Landscape | IFT Submission |  |  | 2025-05-13 | 2025-05-13 | Completed
Parcel 15 | Landscape | Landscape | HAP Review |  |  | 2025-05-20 | 2025-05-20 | Completed
|  | Landscape | IFC Submission |  |  | 2025-06-04 | 2025-06-04 | Completed
|  | Landscape | HAP Review |  |  | 2025-06-10 | 2025-06-10 | Completed
Buffer Zone | Landscape |  |  |  |  | 2025-07-24 | 2025-07-23
Buffer Zone | Landscape | Landscape - SITES | Data to be send by HAP |  |  | 2025-02-13 | 2025-02-13 | Completed
Buffer Zone | Landscape | Landscape - SITES | Baseplan |  |  | 2025-06-04 | 2025-06-04 | Completed
Buffer Zone | Landscape | Landscape - SITES | HAP Review |  |  | 2025-06-12 | 2025-06-12 | Completed
Buffer Zone | Landscape | Landscape - SITES | IFT Submission |  |  | 2025-07-17 | 2025-07-17 | Completed
Buffer Zone | Landscape | Landscape - SITES | HAP Review |  |  | 2025-07-24 | 2025-07-23 | Completed
Boulevard | Landscape |  |  |  |  | 2025-11-29 | 2026-07-01
Boulevard | Landscape | Landscape - SITES | IFT Submission |  | Sites | 2025-11-15 | 2025-11-08 | Completed
Boulevard | Landscape | Landscape - SITES | HAP Review |  |  | 2025-11-29 | 2025-11-24 | Completed
Boulevard | Landscape | Landscape - SITES | 100% IFT Phase.01 |  | Sites |  | 2026-05-19 | Completed
Boulevard | Landscape | Landscape - SITES | HAP Review |  |  |  | 2026-05-21 | Completed
Boulevard | Landscape | Landscape - SITES | 100% IFT Phase.02 | Hoda / Ayman | Sites |  | 2026-06-24 | Inprogress
Boulevard | Landscape | Landscape - SITES | HAP Review | Hoda / Ayman |  |  | 2026-07-01 | Not Started
Main Valley | Landscape |  |  |  |  | 2025-11-26 | 2025-12-22
Main Valley | Landscape | Landscape - SITES | Detailed Design |  |  | 2025-10-15 | 2025-11-01 | Not Started
Main Valley | Landscape | Landscape - SITES | HAP Review |  |  | 2025-10-29 | 2025-11-13 | Completed
Main Valley | Landscape | Landscape - SITES | IFT Submission |  |  | 2025-11-12 | 2025-12-22 | Completed
Main Valley | Landscape | Landscape - SITES | HAP Review |  |  | 2025-11-26 | 2025-12-22 | Completed
Parcel 11 | Landscape | [5 empty] | 2026-07-02
Parcel 11 | Landscape | Landscape | 50% Tender Package | Hoda / Dina | Sites |  | 2025-06-23 | Not Started
Parcel 11 | Landscape | Landscape | HAP Review | Hoda / Dina |  |  | 2026-02-05 | Not Started
Parcel 11 | Landscape | Landscape | 100 % Tender Package | Hoda / Dina | Sites |  | 2026-06-03 | Completed
Parcel 11 | Landscape | Landscape | HAP Review | Hoda / Dina |  |  | 2026-07-02 | Inprogress
Parcel 12 | Landscape | [5 empty] | 2026-07-02
Parcel 12 | Landscape | Landscape (Signage) | 100% Tender Package | Hoda / Dina | Sites |  | 2026-06-25 | Inprogress
Parcel 12 | Landscape | Landscape (Signage) | HAP Review | Hoda / Dina |  |  | 2026-07-02 | Not Started
Parcel 12 | Landscape |  |  |  |  | 2026-07-29 | 2026-08-12
Parcel 12 | Landscape | Landscape | 50% Tender Package | Hoda / Roshdy | Sites |  | 2024-09-12 | Not Started
Parcel 12 | Landscape | Landscape | HAP Review | Hoda / Roshdy |  |  | 2026-07-01 | Not Started
Parcel 12 | Landscape | Landscape | 100 % Tender Package | Hoda / Roshdy | Sites | 2026-07-29 | 2026-07-29 | Not Started
Parcel 12 | Landscape | Landscape | HAP Review | Hoda / Roshdy |  |  | 2026-08-12 | Not Started
Parcel 14 | Landscape |  |  |  |  | 2026-02-12 | 2026-05-05
Parcel 14 | Landscape | Landscape | 100% Tender Package |  | RMC | 2026-02-12 | 2026-02-12 | Completed
Parcel 14 | Landscape | Landscape | HAP Review |  |  |  | 2026-05-05 | Completed
Formulas:
Overdue? = IF([Parent]="","",IF([Actual / Forecast Finish]="","",IF([Status]="completed","-",IF([Actual / Forecast Finish]>TODAY(),"No","Yes"))))
Overdue? = IF([Actual / Forecast Finish]="","",IF([Actual / Forecast Finish]>TODAY(),"No","Yes"))

## SLNX
SLNX | [5 empty] | 2026-05-14 | 2026-08-16 | 94
Phase | Trade | Parent | Task | Task Owner | Consultant | Baseline Finish | Actual / Forecast Finish | Status | Slippage (days) | Overdue? | Days to Finish/Delay | RAG | Notes | CurKey | OvdRank | ShowFlag | DesignRank
Landscape (Phase 04) | Landscape |  |  |  |  | 2026-01-13 | 2026-05-24 |  | 131 |  | -21 | Red |  | #REF! |  | 0
Landscape (Phase 04) | Landscape | Landscape (Phase 04) | Tender Package |  | ECG | 2025-11-29 | 2026-01-15 | Completed | 47 | - | 0 | Red |  |  |  | 0
Landscape (Phase 04) | Landscape | Landscape (Phase 04) | HAP Review |  |  | 2025-12-14 | 2026-04-26 | Completed | 133 | - | 0 | Red |  |  |  | 0
Landscape (Phase 04) | Landscape | Landscape (Phase 04) | BOQ Preparation |  |  | 2026-01-05 | 2026-05-17 | Not Started | 132 | Yes | -28 | Red |  |  | 1 | 1 | 1
Landscape (Phase 04) | Landscape | Landscape (Phase 04) | IFC Package |  |  | 2026-01-13 | 2026-05-24 | Not Started | 131 | Yes | -21 | Red |  |  | 2 | 1 | 2
Landscape (Phase 04) | Landscape | Landscape (Phase 04) | Tender Process |  |  | 2026-04-08 | 2026-08-16 | Not Started | 130 | No | 63 | Green |  |  |  | 0
FM-Building | Buildings |  |  |  |  | 2025-12-30 | 2026-02-18 |  | 50 |  | -116 | Red |  | FM-Building¦Buildings |  | 0
FM-Building | Buildings | FM-Building | Schematic Design - KA Design |  |  | 2025-12-09 | 2025-12-09 | Completed | 0 | - | 0 | Red |  |  |  | 0
FM-Building | Buildings | FM-Building | Enabling Package |  |  | 2025-12-16 | 2025-12-25 | Completed | 9 | - | 0 | Red |  |  |  | 0
FM-Building | Buildings | FM-Building | IFC Package |  |  | 2025-12-30 | 2026-02-18 | Completed | 50 | - | 0 | Red |  |  |  | 0
General | General |  |  |  |  | 2025-11-03 | 2026-01-06 |  | 64 |  | -159 | Red |  | General¦General |  | 0
General | General | General | Development Brief |  |  | 2025-09-28 | 2025-09-28 | Completed | 0 | - | 0 | Red |  |  |  | 0
General | General | General | Brief Approval |  |  | 2025-10-05 | 2025-10-05 | Completed | 0 | - | 0 | Red |  |  |  | 0
General | General | General | RFP |  |  | 2025-10-12 | 2025-10-12 | Completed | 0 | - | 0 | Red |  |  |  | 0
General | General | General | Tender to assign Consultant |  |  | 2025-11-03 | 2026-01-06 | Completed | 64 | - | 0 | Red |  |  |  | 0
General | General | General | Kick off |  |  | 2025-11-03 | 2026-01-06 | Completed | 64 | - | 0 | Red |  |  |  | 0
Master Plan | Master Plan |  |  |  |  | 2026-04-04 | 2026-05-13 |  | 39 |  | -32 | Red |  | Master Plan¦Master Plan |  | 0
Master Plan | Master Plan | Master Plan | Pre-Concept |  | Design Zone | 2026-02-22 | 2026-02-22 | Completed | 0 | - | 0 | Red |  |  |  | 0
Master Plan | Master Plan | Master Plan | HAP Review |  |  | 2026-02-26 | 2026-02-26 | Completed | 0 | - | 0 | Red |  |  |  | 0
Master Plan | Master Plan | Master Plan | 50% Concept |  | Design Zone | 2026-03-12 | 2026-03-15 | Completed | 3 | - | 0 | Red |  |  |  | 0
Master Plan | Master Plan | Master Plan | HAP Review |  |  | 2026-03-19 | 2026-03-18 | Completed | -1 | - | 0 | Red |  |  |  | 0
Master Plan | Master Plan | Master Plan | 100% Concept |  | Design Zone | 2026-03-28 | 2026-05-06 | Inprogress | 39 | Yes | -39 | Red |  |  | 3 | 1 | 3
Master Plan | Master Plan | Master Plan | HAP Review |  |  | 2026-04-04 | 2026-05-13 | Not Started | 39 | Yes | -32 | Red |  |  | 4 | 1 | 4
Buildings | Buildings |  |  |  |  | 2026-04-02 | 2026-06-17 |  | 76 |  | 3 | Amber |  | Buildings¦Buildings |  | 0
Buildings | Buildings | Buildings | Pre-Concept |  |  | 2026-02-26 | 2026-03-15 | Completed | 17 | - | 0 | Red |  |  |  | 0
Buildings | Buildings | Buildings | HAP Review |  |  | 2026-03-05 | 2026-03-18 | Completed | 13 | - | 0 | Red |  |  |  | 0
Buildings | Buildings | Buildings | 50% Concept |  |  | 2026-03-12 | 2026-05-06 | Inprogress | 55 | Yes | -39 | Red |  |  | 5 | 1 | 5
Buildings | Buildings | Buildings | HAP Review |  |  | 2026-03-19 | 2026-05-13 | Not Started | 55 | Yes | -32 | Red |  |  | 6 | 1 | 6
Buildings | Buildings | Buildings | 100% Concept |  |  | 2026-03-26 | 2026-06-10 | Not Started | 76 | Yes | -4 | Red |  |  | 7 | 1 | 7
Buildings | Buildings | Buildings | HAP Review |  |  | 2026-04-02 | 2026-06-17 | Not Started | 76 | Yes | 3 | Amber |  |  | 8 | 1 | 8
Interior | Fit-out |  |  |  |  | 2026-05-14 | 2026-07-22 |  | 69 |  | 38 | Green |  | Interior¦Fit-out |  | 0
Interior | Fit-out | Interior | Pre-Concept |  | Design Zone (Optional) | 2026-04-02 | 2026-05-27 | Not Started | 55 | Yes | -18 | Red |  |  | 9 | 1 | 9
Interior | Fit-out | Interior | HAP Review |  |  | 2026-04-09 | 2026-06-03 | Not Started | 55 | Yes | -11 | Red |  |  | 10 | 1 | 10
Interior | Fit-out | Interior | 50% Concept + Furnished & Colored Plans +ID Shots |  | Design Zone (Optional) | 2026-04-23 | 2026-07-01 | Not Started | 69 | Yes | 17 | Amber |  |  | 11 | 1 | 11
Interior | Fit-out | Interior | HAP Review |  |  | 2026-04-30 | 2026-07-08 | Not Started | 69 | No | 24 | Green |  |  |  | 0
Interior | Fit-out | Interior | 100% Concept |  |  | 2026-05-07 | 2026-07-15 | Not Started | 69 | No | 31 | Green |  |  |  | 0
Interior | Fit-out | Interior | HAP Review |  | Design Zone (Optional) | 2026-05-14 | 2026-07-22 | Not Started | 69 | No | 38 | Green |  |  |  | 0
Landscape | Landscape |  |  |  |  | 2026-04-02 | 2026-08-02 |  | 122 |  | 49 | Green |  | Landscape¦Landscape |  | 0
Landscape | Landscape | Landscape | Pre-Concept |  | Design Zone | 2026-03-05 | 2026-05-03 | Inprogress | 59 | Yes | -42 | Red |  |  | 12 | 1 | 12
Landscape | Landscape | Landscape | HAP Review |  |  | 2026-03-12 | 2026-05-10 | Not Started | 59 | Yes | -35 | Red |  |  | 13 | 1 | 13
Landscape | Landscape | Landscape | 50% Concept Design |  | Design Zone | 2026-03-12 | 2026-05-31 | Not Started | 80 | Yes | -14 | Red |  |  | 14 | 1 | 14
Landscape | Landscape | Landscape | HAP Review |  |  | 2026-03-19 | 2026-06-07 | Not Started | 80 | Yes | -7 | Red |  |  | 15 | 1 | 15
Landscape | Landscape | Landscape | 100% Concept Design |  | Design Zone | 2026-03-26 | 2026-07-19 | Not Started | 115 | No | 35 | Green |  |  |  | 0
Landscape | Landscape | Landscape | HAP Review |  |  | 2026-04-02 | 2026-08-02 | Not Started | 122 | No | 49 | Green |  |  |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
Formulas:
Overdue? = IF([Parent]="","",IF([Actual / Forecast Finish]="","",IF([Status]="completed","-",IF([Actual / Forecast Finish]>TODAY(),"No","Yes"))))
Overdue? = IF([Actual / Forecast Finish]="","",IF([Actual / Forecast Finish]>TODAY(),"No","Yes"))

## Lotus
Lotus | [5 empty] | 2028-05-28 | 2028-07-02 | 35
Phase | Trade | Parent | Task | Task Owner | Consultant | Baseline Finish | Actual / Forecast Finish | Status | Slippage (days) | Overdue? | Days to Finish/Delay | RAG | Notes | CurKey | OvdRank | ShowFlag | DesignRank
Phase 1 | Buildings |  |  |  |  | 2027-01-31 | 2027-03-07 |  | 35 |  | 266 | Green |  | #REF! |  | 0
Phase 1 | Buildings | Buildings (Phase.01) | Single Source Concept Consultant - Buildings (Phase.01) | Mostafa Abdel Aziz | Khaled Mokhtar /Dev | 2026-05-17 | 2026-06-14 | Completed | 28 | - | 0 | Amber |  |  |  | 0
Phase 1 | Buildings | Buildings (Phase.01) | Kick-off - Buildings (Phase.01) | Mostafa Abdel Aziz | Khaled Mokhtar/HAP | 2026-05-17 | 2026-06-14 | Completed | 28 | - | 0 | Amber |  |  |  | 0
Phase 1 | Buildings | Buildings (Phase.01) | 50% Concept Design (Hafez) | Mostafa Abdel Aziz | Khaled Mokhtar /Dev | 2026-06-07 | 2026-06-28 | Inprogress | 21 | Yes | 14 | Amber |  |  | 1 | 1 | 1
Phase 1 | Buildings | Buildings (Phase.01) | HAP Review - 50% CD | Mostafa Abdel Aziz | Khaled Mokhtar/HAP | 2026-06-21 | 2026-07-12 | Not Started | 21 | No | 28 | Green |  |  |  | 0
Phase 1 | Buildings | Buildings (Phase.01) | 100% Concept Design (Hafez) | Mostafa Abdel Aziz | Khaled Mokhtar /Dev | 2026-05-31 | 2026-07-26 | Not Started | 56 | No | 42 | Green |  |  |  | 0
Phase 1 | Buildings | Buildings (Phase.01) | HAP Review - 100% CD | Mostafa Abdel Aziz | Khaled Mokhtar/HAP | 2026-06-14 | 2026-08-09 | Not Started | 56 | No | 56 | Green |  |  |  | 0
Phase 1 | Buildings | Buildings (Phase.01) | 50% Concept Design (Mimar) | Mostafa Abdel Aziz | Khaled Mokhtar /Dev | 2026-06-07 | 2026-07-12 | Not Started | 35 | No | 28 | Green |  |  |  | 0
Phase 1 | Buildings | Buildings (Phase.01) | HAP Review - 50% CD | Mostafa Abdel Aziz | Khaled Mokhtar/HAP | 2026-06-21 | 2026-07-26 | Not Started | 35 | No | 42 | Green |  |  |  | 0
Phase 1 | Buildings | Buildings (Phase.01) | 100% Concept Design (Mimar) | Mostafa Abdel Aziz | Khaled Mokhtar /Dev | 2026-08-02 | 2026-08-09 | Not Started | 7 | No | 56 | Green |  |  |  | 0
Phase 1 | Buildings | Buildings (Phase.01) | HAP Review - 100% CD | Mostafa Abdel Aziz | Khaled Mokhtar/HAP | 2026-08-16 | 2026-08-23 | Not Started | 7 | No | 70 | Green |  |  |  | 0
Phase 1 | Buildings | Buildings (Phase.01) | Single Source Consultant Contract - Buildings (Phase.01) | Qadry / Ashraf | ECG / Design | 2026-05-31 | 2026-09-06 | Not Started | 98 | No | 84 | Green |  |  |  | 0
Phase 1 | Buildings | Buildings (Phase.01) | Kick-off - Buildings (Phase.01) | Qadry / Ashraf | ECG / HAP | 2026-05-31 | 2026-09-06 | Not Started | 98 | No | 84 | Green |  |  |  | 0
Phase 1 | Buildings | Buildings (Phase.01) | Concept Validation | Qadry / Ashraf | ECG | 2026-07-12 | 2026-09-27 | Not Started | 77 | No | 105 | Green |  |  |  | 0
Phase 1 | Buildings | Buildings (Phase.01) | HAP Review - CV | Qadry / Ashraf | ECG / HAP | 2026-07-19 | 2026-10-04 | Not Started | 77 | No | 112 | Green |  |  |  | 0
Phase 1 | Buildings | Buildings (Phase.01) | 100% Schematic Design | Qadry / Ashraf | ECG | 2026-09-20 | 2026-10-25 | Not Started | 35 | No | 133 | Green |  |  |  | 0
Phase 1 | Buildings | Buildings (Phase.01) | HAP Review - 100% SD | Qadry / Ashraf | ECG / HAP | 2026-10-04 | 2026-11-08 | Not Started | 35 | No | 147 | Green |  |  |  | 0
Phase 1 | Buildings | Buildings (Phase.01) | Cost Plan - 100% SD | Nour / Ali | Survtec | 2026-10-11 | 2026-11-15 | Not Started | 35 | No | 154 | Green |  |  |  | 0
Phase 1 | Buildings | Buildings (Phase.01) | Business Plan Update (Phase.01) | Mostafa Abdel Aziz |  | 2026-10-18 | 2026-11-22 | Not Started | 35 | No | 161 | Green |  |  |  | 0
Phase 1 | Buildings | Buildings (Phase.01) | 50% Detailed Design | Qadry / Ashraf | ECG | 2026-11-01 | 2026-12-06 | Not Started | 35 | No | 175 | Green |  |  |  | 0
Phase 1 | Buildings | Buildings (Phase.01) | HAP Review - 50% DD | Qadry / Ashraf | ECG / HAP | 2026-11-15 | 2026-12-20 | Not Started | 35 | No | 189 | Green |  |  |  | 0
Phase 1 | Buildings | Buildings (Phase.01) | Permits Drawings | Qadry / Ashraf | ECG | 2026-11-29 | 2027-01-03 | Not Started | 35 | No | 203 | Green |  |  |  | 0
Phase 1 | Buildings | Buildings (Phase.01) | HAP Review - PD | Qadry / Ashraf | ECG / HAP | 2026-12-06 | 2027-01-10 | Not Started | 35 | No | 210 | Green |  |  |  | 0
Phase 1 | Buildings | Buildings (Phase.01) | 100% Detailed Design | Qadry / Ashraf | ECG | 2026-12-13 | 2027-01-17 | Not Started | 35 | No | 217 | Green |  |  |  | 0
Phase 1 | Buildings | Buildings (Phase.01) | HAP Review - 100% DD | Qadry / Ashraf | ECG / HAP | 2026-12-27 | 2027-01-31 | Not Started | 35 | No | 231 | Green |  |  |  | 0
Phase 1 | Buildings | Buildings (Phase.01) | Cost Plan - 100% DD | Nour / Ali | Survtec | 2027-01-03 | 2027-02-07 | Not Started | 35 | No | 238 | Green |  |  |  | 0
Phase 1 | Buildings | Buildings (Phase.01) | Tender Package | Qadry / Ashraf | ECG | 2027-01-17 | 2027-02-21 | Not Started | 35 | No | 252 | Green |  |  |  | 0
Phase 1 | Buildings | Buildings (Phase.01) | HAP Review - TD | Qadry / Ashraf | ECG / HAP | 2027-01-31 | 2027-03-07 | Not Started | 35 | No | 266 | Green |  |  |  | 0
lotus | Payment |  |  |  |  | 2026-10-06 | 2026-11-10 |  | 35 |  | 149 | Green |  | lotus¦Payment |  | 0
lotus | Payment | Land Payment Plan | Settlement of 2025,2026 instalment (100% 2025,2.5%2026) |  |  | 2026-10-06 | 2026-11-10 | Not Started | 35 | No | 149 | Green |  |  |  | 0
Authorities (Phase.01) | Authorities |  |  |  |  | 2027-04-25 | 2027-05-30 |  | 35 |  | 350 | Green |  | Authorities (Phase.01)¦Authorities |  | 0
Authorities (Phase.01) | Authorities | Authorities Issuance (Phase.01) | Egyptian Institution for Construction Civil Liability Insurance & Civil Defense | Afif |  | 2027-01-17 | 2027-02-21 | Not Started | 35 | No | 252 | Green |  |  |  | 0
Authorities (Phase.01) | Authorities | Authorities Issuance (Phase.01) | Construction licenses-Permits | Afif |  | 2027-02-28 | 2027-04-04 | Not Started | 35 | No | 294 | Green |  |  |  | 0
Authorities (Phase.01) | Authorities | Authorities Issuance (Phase.01) | Mineral licenses-Excavation | Afif |  | 2027-04-25 | 2027-05-30 | Not Started | 35 | No | 350 | Green |  |  |  | 0
Phase 2 | Buildings |  |  |  |  | 2027-10-10 | 2027-11-14 |  | 35 |  | 518 | Green |  | Phase 2¦Buildings |  | 0
Phase 2 | Buildings | Buildings (Phase.02) | 50% Concept Design | Mostafa Abdel Aziz | Khaled Mokhtar /Dev | 2026-07-12 | 2026-08-16 | Not Started | 35 | No | 63 | Green |  |  |  | 0
Phase 2 | Buildings | Buildings (Phase.02) | HAP Review - 50% CD | Mostafa Abdel Aziz | Khaled Mokhtar/HAP | 2026-07-26 | 2026-08-30 | Not Started | 35 | No | 77 | Green |  |  |  | 0
Phase 2 | Buildings | Buildings (Phase.02) | Concept Validation | Qadry / Ashraf | ECG | 2026-08-16 | 2026-09-20 | Not Started | 35 | No | 98 | Green |  |  |  | 0
Phase 2 | Buildings | Buildings (Phase.02) | HAP Review - CV | Qadry / Ashraf | ECG / HAP | 2026-08-23 | 2026-09-27 | Not Started | 35 | No | 105 | Green |  |  |  | 0
Phase 2 | Buildings | Buildings (Phase.02) | 100% Concept Design | Mostafa Abdel Aziz | Khaled Mokhtar /Dev | 2026-09-06 | 2026-10-11 | Not Started | 35 | No | 119 | Green |  |  |  | 0
Phase 2 | Buildings | Buildings (Phase.02) | HAP Review - 100% CD | Mostafa Abdel Aziz | Khaled Mokhtar/HAP | 2026-09-20 | 2026-10-25 | Not Started | 35 | No | 133 | Green |  |  |  | 0
Phase 2 | Buildings | Buildings (Phase.02) | 100% Schematic Design | Qadry / Ashraf | ECG | 2027-03-14 | 2027-04-18 | Not Started | 35 | No | 308 | Green |  |  |  | 0
Phase 2 | Buildings | Buildings (Phase.02) | HAP Review - 100% SD | Qadry / Ashraf | ECG / HAP | 2027-03-28 | 2027-05-02 | Not Started | 35 | No | 322 | Green |  |  |  | 0
Phase 2 | Buildings | Buildings (Phase.02) | Cost Plan - 100% SD | Nour / Ali | Survtec | 2027-04-04 | 2027-05-09 | Not Started | 35 | No | 329 | Green |  |  |  | 0
Phase 2 | Buildings | Buildings (Phase.02) | Business Plan Update (Phase.02) |  |  | 2027-04-11 | 2027-05-16 | Not Started | 35 | No | 336 | Green |  |  |  | 0
Phase 2 | Buildings | Buildings (Phase.02) | 50% Detailed Design | Qadry / Ashraf | ECG | 2027-05-23 | 2027-06-27 | Not Started | 35 | No | 378 | Green |  |  |  | 0
Phase 2 | Buildings | Buildings (Phase.02) | HAP Review - 50% DD | Qadry / Ashraf | ECG / HAP | 2027-06-06 | 2027-07-11 | Not Started | 35 | No | 392 | Green |  |  |  | 0
Phase 2 | Buildings | Buildings (Phase.02) | Permit Drawings | Qadry / Ashraf | ECG | 2027-07-04 | 2027-08-08 | Not Started | 35 | No | 420 | Green |  |  |  | 0
Phase 2 | Buildings | Buildings (Phase.02) | HAP Review - PD | Qadry / Ashraf | ECG / HAP | 2027-07-18 | 2027-08-22 | Not Started | 35 | No | 434 | Green |  |  |  | 0
Phase 2 | Buildings | Buildings (Phase.02) | 100% Detailed Design | Qadry / Ashraf | ECG | 2027-08-01 | 2027-09-05 | Not Started | 35 | No | 448 | Green |  |  |  | 0
Phase 2 | Buildings | Buildings (Phase.02) | HAP Review - 100% DD | Qadry / Ashraf | ECG / HAP | 2027-08-15 | 2027-09-19 | Not Started | 35 | No | 462 | Green |  |  |  | 0
Phase 2 | Buildings | Buildings (Phase.02) | Cost Plan - 100% DD | Nour / Ali | Survtec | 2027-08-22 | 2027-09-26 | Not Started | 35 | No | 469 | Green |  |  |  | 0
Phase 2 | Buildings | Buildings (Phase.02) | Tender Package | Qadry / Ashraf | ECG | 2027-09-26 | 2027-10-31 | Not Started | 35 | No | 504 | Green |  |  |  | 0
Phase 2 | Buildings | Buildings (Phase.02) | HAP Review - TD | Qadry / Ashraf | ECG / HAP | 2027-10-10 | 2027-11-14 | Not Started | 35 | No | 518 | Green |  |  |  | 0
Authorities (Phase.02) | Authorities |  |  |  |  | 2027-12-05 | 2028-01-09 |  | 35 |  | 574 | Green |  | Authorities (Phase.02)¦Authorities |  | 0
Authorities (Phase.02) | Authorities | Authorities Issuance (Phase.02) | Ministerial decree NUCA | Afifi |  | 2027-03-28 | 2027-05-02 | Not Started | 35 | No | 322 | Green |  |  |  | 0
Authorities (Phase.02) | Authorities | Authorities Issuance (Phase.02) | Egyptian Institution for Construction Civil Liability Insurance & Civil Defense | Afifi |  | 2027-08-29 | 2027-10-03 | Not Started | 35 | No | 476 | Green |  |  |  | 0
Authorities (Phase.02) | Authorities | Authorities Issuance (Phase.02) | Construction licenses-Permits | Afifi |  | 2027-10-10 | 2027-11-14 | Not Started | 35 | No | 518 | Green |  |  |  | 0
Authorities (Phase.02) | Authorities | Authorities Issuance (Phase.02) | Mineral licenses-Excavation | Afifi |  | 2027-12-05 | 2028-01-09 | Not Started | 35 | No | 574 | Green |  |  |  | 0
Phase 3 | Buildings |  |  |  |  | 2028-03-05 | 2028-04-09 |  | 35 |  | 665 | Green |  | Phase 3¦Buildings |  | 0
Phase 3 | Buildings | Buildings (Phase.03) | 50% Concept Design | Mostafa Abdel Aziz | Khaled Mokhtar /Dev | 2026-10-11 | 2026-11-15 | Not Started | 35 | No | 154 | Green |  |  |  | 0
Phase 3 | Buildings | Buildings (Phase.03) | HAP Review - 50% CD | Mostafa Abdel Aziz | Khaled Mokhtar/HAP | 2026-10-25 | 2026-11-29 | Not Started | 35 | No | 168 | Green |  |  |  | 0
Phase 3 | Buildings | Buildings (Phase.03) | Concept Validation | Qadry / Ashraf | ECG | 2026-11-15 | 2026-12-20 | Not Started | 35 | No | 189 | Green |  |  |  | 0
Phase 3 | Buildings | Buildings (Phase.03) | HAP Review - CV | Qadry / Ashraf | ECG / HAP | 2026-11-22 | 2026-12-27 | Not Started | 35 | No | 196 | Green |  |  |  | 0
Phase 3 | Buildings | Buildings (Phase.03) | 100% Concept Design | Mostafa Abdel Aziz | Khaled Mokhtar /Dev | 2026-12-06 | 2027-01-10 | Not Started | 35 | No | 210 | Green |  |  |  | 0
Phase 3 | Buildings | Buildings (Phase.03) | HAP Review - 100% CD | Mostafa Abdel Aziz | Khaled Mokhtar/HAP | 2026-12-20 | 2027-01-24 | Not Started | 35 | No | 224 | Green |  |  |  | 0
Phase 3 | Buildings | Buildings (Phase.03) | 100% Schematic Design | Qadry / Ashraf | ECG | 2027-10-24 | 2027-11-28 | Not Started | 35 | No | 532 | Green |  |  |  | 0
Phase 3 | Buildings | Buildings (Phase.03) | HAP Review - 100% SD | Qadry / Ashraf | ECG / HAP | 2027-11-07 | 2027-12-12 | Not Started | 35 | No | 546 | Green |  |  |  | 0
Phase 3 | Buildings | Buildings (Phase.03) | Cost Plan - 100% SD | Nour / Ali | Survtec | 2027-11-14 | 2027-12-19 | Not Started | 35 | No | 553 | Green |  |  |  | 0
Phase 3 | Buildings | Buildings (Phase.03) | Business Plan Update (Phase.03) |  |  | 2027-11-21 | 2027-12-26 | Not Started | 35 | No | 560 | Green |  |  |  | 0
Phase 3 | Buildings | Buildings (Phase.03) | 50% Detailed Design | Qadry / Ashraf | ECG | 2027-12-05 | 2028-01-09 | Not Started | 35 | No | 574 | Green |  |  |  | 0
Phase 3 | Buildings | Buildings (Phase.03) | HAP Review - 50% DD | Qadry / Ashraf | ECG / HAP | 2027-12-19 | 2028-01-23 | Not Started | 35 | No | 588 | Green |  |  |  | 0
Phase 3 | Buildings | Buildings (Phase.03) | Permit Drawings | Qadry / Ashraf | ECG | 2028-01-02 | 2028-02-06 | Not Started | 35 | No | 602 | Green |  |  |  | 0
Phase 3 | Buildings | Buildings (Phase.03) | HAP Review - PD | Qadry / Ashraf | ECG / HAP | 2028-01-09 | 2028-02-13 | Not Started | 35 | No | 609 | Green |  |  |  | 0
Phase 3 | Buildings | Buildings (Phase.03) | 100% Detailed Design | Qadry / Ashraf | ECG | 2028-01-16 | 2028-02-20 | Not Started | 35 | No | 616 | Green |  |  |  | 0
Phase 3 | Buildings | Buildings (Phase.03) | HAP Review - 100% DD | Qadry / Ashraf | ECG / HAP | 2028-01-30 | 2028-03-05 | Not Started | 35 | No | 630 | Green |  |  |  | 0
Phase 3 | Buildings | Buildings (Phase.03) | Cost Plan - 100% DD | Nour / Ali | Survtec | 2028-02-06 | 2028-03-12 | Not Started | 35 | No | 637 | Green |  |  |  | 0
Phase 3 | Buildings | Buildings (Phase.03) | Tender Package | Qadry / Ashraf | ECG | 2028-02-20 | 2028-03-26 | Not Started | 35 | No | 651 | Green |  |  |  | 0
Phase 3 | Buildings | Buildings (Phase.03) | HAP Review - TD | Qadry / Ashraf | ECG / HAP | 2028-03-05 | 2028-04-09 | Not Started | 35 | No | 665 | Green |  |  |  | 0
Phase 3 | Buildings | Buildings (Phase.03) | Authorities Issuance (Phase.03) |  |  | 2028-05-28 | 2028-07-02 | Not Started | 35 | No | 749 | Green |  |  |  | 0
Phase 3 | Buildings | Buildings (Phase.03) | Ministerial decree-NUCA |  |  | 2027-03-28 | 2027-05-02 | Not Started | 35 | No | 322 | Green |  |  |  | 0
Phase 3 | Buildings | Buildings (Phase.03) | Egyptian Institution for Construction Civil Liability Insurance & Civil Defense |  |  | 2028-02-20 | 2028-03-26 | Not Started | 35 | No | 651 | Green |  |  |  | 0
Phase 3 | Buildings | Buildings (Phase.03) | Construction licenses-Permits |  |  | 2028-04-02 | 2028-05-07 | Not Started | 35 | No | 693 | Green |  |  |  | 0
Phase 3 | Buildings | Buildings (Phase.03) | Mineral licenses-Excavation |  |  | 2028-05-28 | 2028-07-02 | Not Started | 35 | No | 749 | Green |  |  |  | 0
Podium | Buildings |  |  |  |  | 2027-01-31 | 2027-03-07 |  | 35 |  | 266 | Green |  | Podium¦Buildings |  | 0
Podium | Buildings | Podium (All Phases) | Kick-off - Podium (All Phases) | Qadry / Ashraf |  | 2026-05-31 | 2026-09-06 | Not Started | 98 | No | 84 | Green |  |  |  | 0
Podium | Buildings | Podium (All Phases) | Concept Validation | Qadry / Ashraf |  | 2026-06-14 | 2026-09-20 | Not Started | 98 | No | 98 | Green |  |  |  | 0
Podium | Buildings | Podium (All Phases) | HAP Review - CV | Qadry / Ashraf |  | 2026-06-28 | 2026-10-04 | Not Started | 98 | No | 112 | Green |  |  |  | 0
Podium | Buildings | Podium (All Phases) | 100% Schematic Design (Including MEP & Infra Works) | Qadry / Ashraf |  | 2026-09-20 | 2026-10-25 | Not Started | 35 | No | 133 | Green |  |  |  | 0
Podium | Buildings | Podium (All Phases) | HAP Review - 100% SD | Qadry / Ashraf |  | 2026-10-04 | 2026-11-08 | Not Started | 35 | No | 147 | Green |  |  |  | 0
Podium | Buildings | Podium (All Phases) | Cost Plan - 100% SD | Nour / Ali | Survtec | 2026-10-04 | 2026-11-08 | Not Started | 35 | No | 147 | Green |  |  |  | 0
Podium | Buildings | Podium (All Phases) | 50% Detailed Design (Including MEP & Infra Works) | Qadry / Ashraf |  | 2026-11-01 | 2026-12-06 | Not Started | 35 | No | 175 | Green |  |  |  | 0
Podium | Buildings | Podium (All Phases) | HAP Review - 50% CD | Qadry / Ashraf |  | 2026-11-15 | 2026-12-20 | Not Started | 35 | No | 189 | Green |  |  |  | 0
Podium | Buildings | Podium (All Phases) | Permit Drawings | Qadry / Ashraf |  | 2026-11-29 | 2027-01-03 | Not Started | 35 | No | 203 | Green |  |  |  | 0
Podium | Buildings | Podium (All Phases) | HAP Review - PD | Qadry / Ashraf |  | 2026-12-06 | 2027-01-10 | Not Started | 35 | No | 210 | Green |  |  |  | 0
Podium | Buildings | Podium (All Phases) | 100% Detailed Design (Including MEP & Infra Works) | Qadry / Ashraf |  | 2026-12-13 | 2027-01-17 | Not Started | 35 | No | 217 | Green |  |  |  | 0
Podium | Buildings | Podium (All Phases) | HAP Review - 100% DD | Qadry / Ashraf |  | 2026-12-27 | 2027-01-31 | Not Started | 35 | No | 231 | Green |  |  |  | 0
Podium | Buildings | Podium (All Phases) | Cost Plan - 100% DD | Nour / Ali | Survtec | 2027-01-03 | 2027-02-07 | Not Started | 35 | No | 238 | Green |  |  |  | 0
Podium | Buildings | Podium (All Phases) | Tender Package (Including MEP & Infra Works) | Qadry / Ashraf |  | 2027-01-17 | 2027-02-21 | Not Started | 35 | No | 252 | Green |  |  |  | 0
Podium | Buildings | Podium (All Phases) | HAP Review - TD | Qadry / Ashraf |  | 2027-01-31 | 2027-03-07 | Not Started | 35 | No | 266 | Green |  |  |  | 0
Authorities (Phase.03) | Authorities |  |  |  |  | 2027-04-25 | 2027-05-30 |  | 35 |  | 350 | Green |  | Authorities (Phase.03)¦Authorities |  | 0
Authorities (Phase.03) | Authorities | Authorities Issuance (Podium) | Egyptian Institution for Construction Civil Liability Insurance & Civil Defense |  |  | 2027-01-17 | 2027-02-21 | Not Started | 35 | No | 252 | Green |  |  |  | 0
Authorities (Phase.03) | Authorities | Authorities Issuance (Podium) | Construction licenses-Permits |  |  | 2027-02-28 | 2027-04-04 | Not Started | 35 | No | 294 | Green |  |  |  | 0
Authorities (Phase.03) | Authorities | Authorities Issuance (Podium) | Mineral licenses-Excavation |  |  | 2027-04-25 | 2027-05-30 | Not Started | 35 | No | 350 | Green |  |  |  | 0
Masterplan (All Phases) | Masterplan |  |  |  |  | 2026-11-08 | 2027-01-31 |  | 84 |  | 231 | Green |  | Masterplan (All Phases)¦Masterplan |  | 0
Masterplan (All Phases) | Masterplan | Masterplan (All Phases) | 50% Concept Design (Hafez) | Mostafa Abdel Aziz | Khaled Mokhtar /Dev | 2026-06-28 | 2026-06-28 | Inprogress | 0 | Yes | 14 | Amber |  |  | 2 | 1 | 2
Masterplan (All Phases) | Masterplan | Masterplan (All Phases) | HAP Review - 50% CD | Mostafa Abdel Aziz | Khaled Mokhtar/HAP | 2026-07-12 | 2026-07-12 | Not Started | 0 | No | 28 | Green |  |  |  | 0
Masterplan (All Phases) | Masterplan | Masterplan (All Phases) | 100% Concept Design (Hafez) | Mostafa Abdel Aziz | Khaled Mokhtar /Dev | 2026-07-26 | 2026-07-26 | Not Started | 0 | No | 42 | Green |  |  |  | 0
Masterplan (All Phases) | Masterplan | Masterplan (All Phases) | HAP Review - 100% CD | Mostafa Abdel Aziz | Khaled Mokhtar/HAP | 2026-08-09 | 2026-08-09 | Not Started | 0 | No | 56 | Green |  |  |  | 0
Masterplan (All Phases) | Masterplan | Masterplan (All Phases) | 50% Concept Design (Mimar) | Mostafa Abdel Aziz | Khaled Mokhtar /Dev | 2026-07-12 | 2026-07-12 | Not Started | 0 | No | 28 | Green |  |  |  | 0
Masterplan (All Phases) | Masterplan | Masterplan (All Phases) | HAP Review - 50% CD | Mostafa Abdel Aziz | Khaled Mokhtar/HAP | 2026-07-26 | 2026-07-26 | Not Started | 0 | No | 42 | Green |  |  |  | 0
Masterplan (All Phases) | Masterplan | Masterplan (All Phases) | 100% Concept Design (Mimar) | Mostafa Abdel Aziz | Khaled Mokhtar /Dev | 2026-08-09 | 2026-08-09 | Not Started | 0 | No | 56 | Green |  |  |  | 0
Masterplan (All Phases) | Masterplan | Masterplan (All Phases) | HAP Review - 100% CD | Mostafa Abdel Aziz | Khaled Mokhtar/HAP | 2026-08-23 | 2026-08-23 | Not Started | 0 | No | 70 | Green |  |  |  | 0
Masterplan (All Phases) | Masterplan | Masterplan (All Phases) | Concept Validation | Qadry / Ashraf |  | 2026-06-14 | 2026-09-06 | Not Started | 84 | No | 84 | Green |  |  |  | 0
Masterplan (All Phases) | Masterplan | Masterplan (All Phases) | HAP Review - CV | Qadry / Ashraf |  | 2026-06-21 | 2026-09-13 | Not Started | 84 | No | 91 | Green |  |  |  | 0
Masterplan (All Phases) | Masterplan | Masterplan (All Phases) | 100% Schematic Design | Qadry / Ashraf |  | 2026-07-12 | 2026-10-04 | Not Started | 84 | No | 112 | Green |  |  |  | 0
Masterplan (All Phases) | Masterplan | Masterplan (All Phases) | HAP Review - 100% SD | Qadry / Ashraf |  | 2026-07-26 | 2026-10-18 | Not Started | 84 | No | 126 | Green |  |  |  | 0
Masterplan (All Phases) | Masterplan | Masterplan (All Phases) | Updated Ministerial decree | Qadry / Ashraf |  | 2026-10-04 | 2026-11-08 | Not Started | 35 | No | 147 | Green |  |  |  | 0
Masterplan (All Phases) | Masterplan | Masterplan (All Phases) | HAP Review - Updated Ministerial decree | Qadry / Ashraf |  | 2026-10-11 | 2026-11-15 | Not Started | 35 | No | 154 | Green |  |  |  | 0
Masterplan (All Phases) | Masterplan | Masterplan (All Phases) | 50% Detailed Design | Qadry / Ashraf |  | 2026-08-16 | 2026-11-08 | Not Started | 84 | No | 147 | Green |  |  |  | 0
Masterplan (All Phases) | Masterplan | Masterplan (All Phases) | HAP Review - 50% DD | Qadry / Ashraf |  | 2026-08-30 | 2026-11-22 | Not Started | 84 | No | 161 | Green |  |  |  | 0
Masterplan (All Phases) | Masterplan | Masterplan (All Phases) | 100% Detailed Design | Qadry / Ashraf |  | 2026-09-20 | 2026-12-13 | Not Started | 84 | No | 182 | Green |  |  |  | 0
Masterplan (All Phases) | Masterplan | Masterplan (All Phases) | HAP Review - 100% DD | Qadry / Ashraf |  | 2026-10-04 | 2026-12-27 | Not Started | 84 | No | 196 | Green |  |  |  | 0
Masterplan (All Phases) | Masterplan | Masterplan (All Phases) | Tender Package | Qadry / Ashraf |  | 2026-10-25 | 2027-01-17 | Not Started | 84 | No | 217 | Green |  |  |  | 0
Masterplan (All Phases) | Masterplan | Masterplan (All Phases) | HAP Review - TD | Qadry / Ashraf |  | 2026-11-08 | 2027-01-31 | Not Started | 84 | No | 231 | Green |  |  |  | 0
Landscape (Phase.01) | Landscape |  |  |  |  | 2027-01-17 | 2027-04-20 |  | 93 |  | 310 | Green |  | Landscape (Phase.01)¦Landscape |  | 0
Landscape (Phase.01) | Landscape | Landscape (Phase.01) | RFP - Landscape (Phase.01) | Dina |  | 2026-05-10 | 2026-05-21 | Completed | 11 | - | 0 | Red |  |  |  | 0
Landscape (Phase.01) | Landscape | Landscape (Phase.01) | Single Source Concept Consultant - Landscape (Phase.01) | Dina |  | 2026-05-31 | 2026-07-05 | Inprogress | 35 | No | 21 | Amber |  |  |  | 0
Landscape (Phase.01) | Landscape | Landscape (Phase.01) | 50% Concept Design | Dina |  | 2026-06-28 | 2026-09-29 | Not Started | 93 | No | 107 | Green |  |  |  | 0
Landscape (Phase.01) | Landscape | Landscape (Phase.01) | HAP Review - 50% CD | Dina |  | 2026-07-05 | 2026-10-06 | Not Started | 93 | No | 114 | Green |  |  |  | 0
Landscape (Phase.01) | Landscape | Landscape (Phase.01) | 100% Concept Design | Dina |  | 2026-07-19 | 2026-10-20 | Not Started | 93 | No | 128 | Green |  |  |  | 0
Landscape (Phase.01) | Landscape | Landscape (Phase.01) | HAP Review - 100% CD | Dina |  | 2026-08-02 | 2026-11-03 | Not Started | 93 | No | 142 | Green |  |  |  | 0
Landscape (Phase.01) | Landscape | Landscape (Phase.01) | Cost Plan - 100% CD | Nour / Ali | Survtec | 2026-08-09 | 2026-11-10 | Not Started | 93 | No | 149 | Green |  |  |  | 0
Landscape (Phase.01) | Landscape | Landscape (Phase.01) | 50% Schematic Design | Dina |  | 2026-08-16 | 2026-11-17 | Not Started | 93 | No | 156 | Green |  |  |  | 0
Landscape (Phase.01) | Landscape | Landscape (Phase.01) | HAP Review - 50% SD | Dina |  | 2026-08-30 | 2026-12-01 | Not Started | 93 | No | 170 | Green |  |  |  | 0
Landscape (Phase.01) | Landscape | Landscape (Phase.01) | 100% Schematic Design | Dina |  | 2026-09-27 | 2026-12-29 | Not Started | 93 | No | 198 | Green |  |  |  | 0
Landscape (Phase.01) | Landscape | Landscape (Phase.01) | HAP Review - 100% SD | Dina |  | 2026-10-11 | 2027-01-12 | Not Started | 93 | No | 212 | Green |  |  |  | 0
Landscape (Phase.01) | Landscape | Landscape (Phase.01) | Cost Plan - 100% SD | Nour / Ali | Survtec | 2026-10-18 | 2027-01-19 | Not Started | 93 | No | 219 | Green |  |  |  | 0
Landscape (Phase.01) | Landscape | Landscape (Phase.01) | 50% Detailed Design | Dina |  | 2026-11-01 | 2027-02-02 | Not Started | 93 | No | 233 | Green |  |  |  | 0
Landscape (Phase.01) | Landscape | Landscape (Phase.01) | HAP Review - 50% DD | Dina |  | 2026-11-15 | 2027-02-16 | Not Started | 93 | No | 247 | Green |  |  |  | 0
Landscape (Phase.01) | Landscape | Landscape (Phase.01) | 100% Detailed Design | Dina |  | 2026-11-29 | 2027-03-02 | Not Started | 93 | No | 261 | Green |  |  |  | 0
Landscape (Phase.01) | Landscape | Landscape (Phase.01) | HAP Review - 100% DD | Dina |  | 2026-12-13 | 2027-03-16 | Not Started | 93 | No | 275 | Green |  |  |  | 0
Landscape (Phase.01) | Landscape | Landscape (Phase.01) | Cost Plan - 100% DD | Nour / Ali | Survtec | 2026-12-20 | 2027-03-23 | Not Started | 93 | No | 282 | Green |  |  |  | 0
Landscape (Phase.01) | Landscape | Landscape (Phase.01) | Tender Package | Dina |  | 2027-01-03 | 2027-04-06 | Not Started | 93 | No | 296 | Green |  |  |  | 0
Landscape (Phase.01) | Landscape | Landscape (Phase.01) | HAP Review - TD | Dina |  | 2027-01-17 | 2027-04-20 | Not Started | 93 | No | 310 | Green |  |  |  | 0
Landscape (Phase.02) | Landscape |  |  |  |  | 2027-03-14 | 2027-06-15 |  | 93 |  | 366 | Green |  | Landscape (Phase.02)¦Landscape |  | 0
Landscape (Phase.02) | Landscape | Landscape (Phase.02) | 100% Concept Design | Dina |  | 2026-09-13 | 2026-12-15 | Not Started | 93 | No | 184 | Green |  |  |  | 0
Landscape (Phase.02) | Landscape | Landscape (Phase.02) | HAP Review - 100% CD | Dina |  | 2026-09-27 | 2026-12-29 | Not Started | 93 | No | 198 | Green |  |  |  | 0
Landscape (Phase.02) | Landscape | Landscape (Phase.02) | Cost Plan - 100% CD | Nour / Ali | Survtec | 2026-10-04 | 2027-01-05 | Not Started | 93 | No | 205 | Green |  |  |  | 0
Landscape (Phase.02) | Landscape | Landscape (Phase.02) | 50% Schematic Design | Dina |  | 2026-10-11 | 2027-01-12 | Not Started | 93 | No | 212 | Green |  |  |  | 0
Landscape (Phase.02) | Landscape | Landscape (Phase.02) | HAP Review - 50% SD | Dina |  | 2026-10-25 | 2027-01-26 | Not Started | 93 | No | 226 | Green |  |  |  | 0
Landscape (Phase.02) | Landscape | Landscape (Phase.02) | 100% Schematic Design | Dina |  | 2026-11-22 | 2027-02-23 | Not Started | 93 | No | 254 | Green |  |  |  | 0
Landscape (Phase.02) | Landscape | Landscape (Phase.02) | HAP Review - 100% SD | Dina |  | 2026-12-06 | 2027-03-09 | Not Started | 93 | No | 268 | Green |  |  |  | 0
Landscape (Phase.02) | Landscape | Landscape (Phase.02) | Cost Plan - 100% SD | Nour / Ali | Survtec | 2026-12-13 | 2027-03-16 | Not Started | 93 | No | 275 | Green |  |  |  | 0
Landscape (Phase.02) | Landscape | Landscape (Phase.02) | 50% Detailed Design | Dina |  | 2026-12-27 | 2027-03-30 | Not Started | 93 | No | 289 | Green |  |  |  | 0
Landscape (Phase.02) | Landscape | Landscape (Phase.02) | HAP Review - 50% DD | Dina |  | 2027-01-10 | 2027-04-13 | Not Started | 93 | No | 303 | Green |  |  |  | 0
Landscape (Phase.02) | Landscape | Landscape (Phase.02) | 100% Detailed Design | Dina |  | 2027-01-24 | 2027-04-27 | Not Started | 93 | No | 317 | Green |  |  |  | 0
Landscape (Phase.02) | Landscape | Landscape (Phase.02) | HAP Review - 100% DD | Dina |  | 2027-02-07 | 2027-05-11 | Not Started | 93 | No | 331 | Green |  |  |  | 0
Landscape (Phase.02) | Landscape | Landscape (Phase.02) | Cost Plan - 100% DD | Nour / Ali | Survtec | 2027-02-14 | 2027-05-18 | Not Started | 93 | No | 338 | Green |  |  |  | 0
Landscape (Phase.02) | Landscape | Landscape (Phase.02) | Tender Package | Dina |  | 2027-02-28 | 2027-06-01 | Not Started | 93 | No | 352 | Green |  |  |  | 0
Landscape (Phase.02) | Landscape | Landscape (Phase.02) | HAP Review - TD | Dina |  | 2027-03-14 | 2027-06-15 | Not Started | 93 | No | 366 | Green |  |  |  | 0
Landscape (Phase.03) | Landscape |  |  |  |  | 2027-05-09 | 2027-08-10 |  | 93 |  | 422 | Green |  | Landscape (Phase.03)¦Landscape |  | 0
Landscape (Phase.03) | Landscape | Landscape (Phase.03) | 100% Concept Design | Dina |  | 2026-11-08 | 2027-02-09 | Not Started | 93 | No | 240 | Green |  |  |  | 0
Landscape (Phase.03) | Landscape | Landscape (Phase.03) | HAP Review - 100% CD | Dina |  | 2026-11-22 | 2027-02-23 | Not Started | 93 | No | 254 | Green |  |  |  | 0
Landscape (Phase.03) | Landscape | Landscape (Phase.03) | Cost Plan - 100% CD | Nour / Ali | Survtec | 2026-11-29 | 2027-03-02 | Not Started | 93 | No | 261 | Green |  |  |  | 0
Landscape (Phase.03) | Landscape | Landscape (Phase.03) | 50% Schematic Design | Dina |  | 2026-12-06 | 2027-03-09 | Not Started | 93 | No | 268 | Green |  |  |  | 0
Landscape (Phase.03) | Landscape | Landscape (Phase.03) | HAP Review - 50% SD | Dina |  | 2026-12-20 | 2027-03-23 | Not Started | 93 | No | 282 | Green |  |  |  | 0
Landscape (Phase.03) | Landscape | Landscape (Phase.03) | 100% Schematic Design | Dina |  | 2027-01-17 | 2027-04-20 | Not Started | 93 | No | 310 | Green |  |  |  | 0
Landscape (Phase.03) | Landscape | Landscape (Phase.03) | HAP Review - 100% SD | Dina |  | 2027-01-31 | 2027-05-04 | Not Started | 93 | No | 324 | Green |  |  |  | 0
Landscape (Phase.03) | Landscape | Landscape (Phase.03) | Cost Plan - 100% SD | Nour / Ali | Survtec | 2027-02-07 | 2027-05-11 | Not Started | 93 | No | 331 | Green |  |  |  | 0
Landscape (Phase.03) | Landscape | Landscape (Phase.03) | 50% Detailed Design | Dina |  | 2027-02-21 | 2027-05-25 | Not Started | 93 | No | 345 | Green |  |  |  | 0
Landscape (Phase.03) | Landscape | Landscape (Phase.03) | HAP Review - 50% DD | Dina |  | 2027-03-07 | 2027-06-08 | Not Started | 93 | No | 359 | Green |  |  |  | 0
Landscape (Phase.03) | Landscape | Landscape (Phase.03) | 100% Detailed Design |  |  | 2027-03-21 | 2027-06-22 |  | 93 | No | 373 | Green |  |  |  | 0
Landscape (Phase.03) | Landscape | Landscape (Phase.03) | HAP Review - 100% DD |  |  | 2027-04-04 | 2027-07-06 |  | 93 | No | 387 | Green |  |  |  | 0
Landscape (Phase.03) | Landscape | Landscape (Phase.03) | Cost Plan - 100% DD |  |  | 2027-04-11 | 2027-07-13 |  | 93 | No | 394 | Green |  |  |  | 0
Landscape (Phase.03) | Landscape | Landscape (Phase.03) | Tender Package |  |  | 2027-04-25 | 2027-07-27 |  | 93 | No | 408 | Green |  |  |  | 0
Landscape (Phase.03) | Landscape | Landscape (Phase.03) | HAP Review - TD |  |  | 2027-05-09 | 2027-08-10 |  | 93 | No | 422 | Green |  |  |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
Formulas:
Overdue? = IF([Parent]="","",IF([Actual / Forecast Finish]="","",IF([Status]="completed","-",IF([Actual / Forecast Finish]>TODAY(),"No","Yes"))))
Overdue? = IF([Actual / Forecast Finish]="","",IF([Actual / Forecast Finish]>TODAY(),"No","Yes"))

## Keys 52
Keys 52 | [5 empty] | 2026-02-01 | 2026-07-02 | 151
Phase | Trade | Parent | Task | Task Owner | Consultant | Baseline Finish | Actual / Forecast Finish | Status | Slippage (days) | Overdue? | Days to Finish/Delay | RAG | Notes | CurKey | OvdRank | ShowFlag | DesignRank
Keys 52 | Buldings |  |  |  |  | 2025-09-21 | 2026-07-02 |  | 284 |  | 18 | Amber |  | #REF! |  | 0
Keys 52 | Buldings | BLDGs,External | 100% Schematic Design |  | GDG | 2024-10-13 | 2024-10-13 | Completed | 0 | - | 0 | Red |  |  |  | 0
Keys 52 | Buldings | BLDGs,External | HAP Review - 100% SD |  |  | 2024-10-27 | 2024-10-27 | Completed | 0 | - | 0 | Red |  |  |  | 0
Keys 52 | Buldings | BLDGs,External | Cost Plan - 100% SD | Nour / Ali |  | 2024-11-10 | 2024-11-10 | Completed | 0 | - | 0 | Red |  |  |  | 0
Keys 52 | Buldings | BLDGs,External | 50% Detailed Design |  | GDG | 2025-01-19 | 2025-01-19 | Completed | 0 | - | 0 | Red |  |  |  | 0
Keys 52 | Buldings | BLDGs,External | HAP Review - 50% DD |  |  | 2025-04-13 | 2025-04-13 | Completed | 0 | - | 0 | Red |  |  |  | 0
Keys 52 | Buldings | BLDGs,External | 100% Detailed Design |  | GDG | 2025-06-22 | 2025-06-22 | Completed | 0 | - | 0 | Red |  |  |  | 0
Keys 52 | Buldings | BLDGs,External | HAP Review - 100% DD |  |  | 2025-07-06 | 2025-07-06 | Completed | 0 | - | 0 | Red |  |  |  | 0
Keys 52 | Buldings | BLDGs,External | Cost Plan - 100% DD | Nour / Ali |  | 2025-07-06 | 2025-07-06 | Completed | 0 | - | 0 | Red |  |  |  | 0
Keys 52 | Buldings | BLDGs,External | Permit Drawings & Documents (IFP, IFDL, IFCD) |  | GDG | 2025-08-24 | 2025-08-24 | Completed | 0 | - | 0 | Red |  |  |  | 0
BLDGs A | Buldings |  |  |  |  | 2025-09-07 | 2025-12-31 |  | 115 |  | -165 | Red |  | BLDGs A¦Buldings |  | 0
BLDGs A | Buldings | BLDGs A | Tender Package |  | GDG | 2025-08-31 | 2025-12-28 | Completed | 119 | - | 0 | Red |  |  |  | 0
BLDGs A | Buldings | BLDGs A | HAP Review - TD |  |  | 2025-09-07 | 2025-12-31 | Completed | 115 | - | 0 | Red |  |  |  | 0
BLDGs B | Buldings |  |  |  |  | 2025-09-07 | 2026-02-03 |  | 149 |  | -131 | Red |  | BLDGs B¦Buldings |  | 0
BLDGs B | Buldings | BLDGs B | Tender Package |  | GDG | 2025-08-31 | 2026-01-28 | Completed | 150 | - | 0 | Red |  |  |  | 0
BLDGs B | Buldings | BLDGs B | HAP Review - TD |  |  | 2025-09-07 | 2026-02-03 | Completed | 149 | - | 0 | Red |  |  |  | 0
BLDGs C | Buldings |  |  |  |  | 2025-09-07 | 2025-12-23 |  | 107 |  | -173 | Red |  | BLDGs C¦Buldings |  | 0
BLDGs C | Buldings | BLDGs C | Tender Package |  | GDG | 2025-08-31 | 2025-12-11 | Completed | 102 | - | 0 | Red |  |  |  | 0
BLDGs C | Buldings | BLDGs C | HAP Review - TD |  |  | 2025-09-07 | 2025-12-23 | Completed | 107 | - | 0 | Red |  |  |  | 0
mockup | Fit-out | [5 empty] | 2026-07-02 |  |  |  | 18 | Amber |  | mockup ¦Fit-out |  | 0
mockup | Fit-out | mockup ( Interior) | Concept Design | design team | Khalifa Studio |  | 2026-06-25 | Inprogress |  | Yes | 11 | Amber |  |  | 1 | 1 | 1
mockup | Fit-out | mockup ( Interior) | HAP Review - 100% CD | design team | Khalifa Studio |  | 2026-07-02 | Not Started |  | No | 18 | Amber |  |  |  | 0
Authorities - Keys 52 | [5 empty] | 2025-09-21 | 2025-11-30 |  | 70 |  | -196 | Red |  | Authorities - Keys 52¦ |  | 0
Authorities - Keys 52 | Authorities | Permits Issuance | Construction licenses |  |  | 2025-09-21 | 2025-11-30 | Completed | 70 | - | 0 | Red |  | Authorities - Keys 52¦Authorities |  | 0
Landscape & Infra - Keys 52 | Landscape |  |  |  |  | 2025-11-10 | 2026-06-17 |  | 219 |  | 3 | Amber |  | Landscape & Infra - Keys 52¦Landscape |  | 0
Landscape & Infra - Keys 52 | Landscape | External Works Landscape & Infra | 100% Detailed Design |  | GDG | 2025-09-15 | 2025-09-15 | Completed | 0 | - | 0 | Red |  |  |  | 0
Landscape & Infra - Keys 52 | Landscape | External Works Landscape & Infra | HAP Review - 100% DD |  |  | 2025-09-29 | 2025-09-29 | Completed | 0 | - | 0 | Red |  |  |  | 0
Landscape & Infra - Keys 52 | Landscape | External Works Landscape & Infra | Tender Package |  | GDG | 2025-10-13 | 2026-02-23 | Completed | 133 | - | 0 | Red |  |  |  | 0
Landscape & Infra - Keys 52 | Landscape | External Works Landscape & Infra | HAP Review - TD |  |  | 2025-10-27 | 2026-02-26 | Completed | 122 | - | 0 | Red |  |  |  | 0
Landscape & Infra - Keys 52 | Landscape | External Works Landscape & Infra | Revised IFT (Regarding the infra modifications) |  | GDG |  | 2026-06-09 | Completed |  | - | 0 | Red |  |  |  | 0
Landscape & Infra - Keys 52 | Landscape | External Works Landscape & Infra | HAP Review - TD |  |  |  | 2026-06-10 | Completed |  | - | 0 | Red |  |  |  | 0
Landscape & Infra - Keys 52 | Landscape | External Works Landscape & Infra | Revised IFT (Regarding the Landscape modifications) |  | GDG |  | 2026-06-14 | Completed |  | - | 0 | Amber |  |  |  | 0
Landscape & Infra - Keys 52 | Landscape | External Works Landscape & Infra | HAP Review - TD |  |  |  | 2026-06-17 | Completed |  | - | 0 | Amber |  |  |  | 0
Fences & Gates - Keys 52 | Fences & Gates |  |  |  |  | 2026-02-01 | 2026-03-12 |  | 39 |  | -94 | Red |  | Fences & Gates - Keys 52¦Fences & Gates |  | 0
Fences & Gates - Keys 52 | Fences & Gates | Fences & Gates | IFT |  | GDG | 2026-01-11 | 2026-02-23 | Completed | 43 | - | 0 | Red |  |  |  | 0
Fences & Gates - Keys 52 | Fences & Gates | Fences & Gates | HAP Review |  |  | 2026-01-18 | 2026-02-26 | Completed | 39 | - | 0 | Red |  |  |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
Formulas:
Overdue? = IF([Parent]="","",IF([Actual / Forecast Finish]="","",IF([Status]="completed","-",IF([Actual / Forecast Finish]>TODAY(),"No","Yes"))))
Overdue? = IF([Actual / Forecast Finish]="","",IF([Actual / Forecast Finish]>TODAY(),"No","Yes"))

## Encore
DRJ | [5 empty] | 2027-02-25 | 2027-03-01 | 4
Phase | Trade | Parent | Task | Task Owner | Consultant | Baseline Finish | Actual / Forecast Finish | Status | Slippage (days) | Overdue? | Days to Finish/Delay | RAG | Notes | CurKey | OvdRank | ShowFlag | DesignRank
Genral | Genral | Overall Disciplines | RFP - Overall Disciplines |  |  | 2025-10-07 | 2025-10-07 | Completed | 0 | - | 0 | Red |  | #REF! |  | 0
Genral | Genral | Overall Disciplines | Tender to assign consultant - Overall Disciplines |  |  | 2025-10-28 | 2025-10-28 | Completed | 0 | - | 0 | Red |  |  |  | 0
Genral | Genral | Overall Disciplines | BODR |  |  | 2025-11-02 | 2025-11-02 | Completed | 0 | - | 0 | Red |  |  |  | 0
Genral | Genral | Overall Disciplines | HAP Review - BODR |  |  | 2025-11-04 | 2025-11-04 | Completed | 0 | - | 0 | Red |  |  |  | 0
Two types (B1&B2) | Buildings |  |  |  |  | 2026-04-05 | 2026-06-22 |  | 78 |  | 8 | Amber |  | Two types (B1&B2)¦Buildings |  | 0
Two types (B1&B2) | Buildings | Two types (B1&B2) | Structure IFC PKG |  | GDG | 2025-10-23 | 2025-10-23 | Completed | 0 | - | 0 | Red |  |  |  | 0
Two types (B1&B2) | Buildings | Two types (B1&B2) | 100% Detailed Design (Finishes) |  | GDG | 2025-12-02 | 2025-12-07 | Completed | 5 | - | 0 | Red |  |  |  | 0
Two types (B1&B2) | Buildings | Two types (B1&B2) | HAP Review - 100% DD |  |  | 2025-12-17 | 2025-12-22 | Completed | 5 | - | 0 | Red |  |  |  | 0
Two types (B1&B2) | Buildings | Two types (B1&B2) | Cost Plan - 100% DD | Nour / Ali | Survtec | 2025-12-17 | 2026-06-22 | Inprogress | 187 | Yes | 8 | Amber |  |  | 1 | 1 | 1
Two types (B1&B2) | Buildings | Two types (B1&B2) | Tender Package (Full Fit-Out PKGS) |  | GDG | 2026-01-01 | 2026-02-08 | Completed | 38 | - | 0 | Red |  |  |  | 0
Two types (B1&B2) | Buildings | Two types (B1&B2) | HAP Review - TD |  |  | 2026-01-11 | 2026-02-12 | Completed | 32 | - | 0 | Red |  |  |  | 0
One type (B3) | Buildings |  |  |  |  | 2026-04-06 | 2026-06-22 |  | 77 |  | 8 | Amber |  | One type (B3)¦Buildings |  | 0
One type (B3) | Buildings | One type (B3) | 100% Detailed Design |  | GDG | 2025-12-02 | 2025-12-07 | Completed | 5 | - | 0 | Red |  |  |  | 0
One type (B3) | Buildings | One type (B3) | Structure IFT PKG |  | GDG | 2025-12-02 | 2025-12-31 | Completed | 29 | - | 0 | Red |  |  |  | 0
One type (B3) | Buildings | One type (B3) | HAP Review - 100% DD |  |  | 2025-12-17 | 2025-12-31 | Completed | 14 | - | 0 | Red |  |  |  | 0
One type (B3) | Buildings | One type (B3) | Cost Plan - 100% DD | Nour / Ali | Survtec | 2025-12-17 | 2026-06-22 | Inprogress | 187 | Yes | 8 | Amber |  |  | 2 | 1 | 2
One type (B3) | Buildings | One type (B3) | Structure IFC PKG |  | GDG | 2025-12-17 | 2025-12-31 | Completed | 14 | - | 0 | Red |  |  |  | 0
One type (B3) | Buildings | One type (B3) | Tender Package ( Full Fit-Out PKG) |  | GDG | 2026-01-01 | 2026-02-08 | Completed | 38 | - | 0 | Red |  |  |  | 0
One type (B3) | Buildings | One type (B3) | HAP Review - TD |  |  | 2026-01-11 | 2026-02-12 | Completed | 32 | - | 0 | Red |  |  |  | 0
Authorities | Authorities |  |  |  |  | 2025-10-22 | 2025-10-22 |  | 0 |  | -235 | Red |  | Authorities¦Authorities |  | 0
Authorities | Authorities | Authorities | TDA Permits |  |  | 2025-10-22 | 2025-10-22 | Completed | 0 | - | 0 | Red |  |  |  | 0
Crystal Lagoon | Crystal Lagoon |  |  |  |  | 2027-02-25 | 2027-03-01 |  | 4 |  | 260 | Green |  | Crystal Lagoon¦Crystal Lagoon |  | 0
Crystal Lagoon | Crystal Lagoon | Crystal Lagoon | Zero Geometry | Tark |  | 2025-10-22 | 2026-02-11 | Completed | 112 | - | 0 | Red |  |  |  | 0
Crystal Lagoon | Crystal Lagoon | Crystal Lagoon | HAP Review - Zero Geometry | Tark |  | 2025-11-13 | 2026-02-11 | Completed | 90 | - | 0 | Red |  |  |  | 0
Crystal Lagoon | Crystal Lagoon | Crystal Lagoon | Design Criteria Package - Crystal Lagoon | Tark |  | 2025-12-11 | 2026-05-04 | Completed | 144 | - | 0 | Red |  |  |  | 0
Crystal Lagoon | Crystal Lagoon | Crystal Lagoon | RFP - Crystal Lagoon | Tark |  | 2026-05-19 | 2026-05-19 | Completed | 0 | - | 0 | Red |  |  |  | 0
Crystal Lagoon | Crystal Lagoon | Crystal Lagoon | Tender to assign consultant - Crystal Lagoon | Tark |  | 2026-06-25 | 2026-06-29 | Inprogress | 4 | Yes | 15 | Amber |  |  | 3 | 1 | 3
Crystal Lagoon | Crystal Lagoon | Crystal Lagoon | Full Package Design | Tark |  | 2026-06-25 | 2026-09-07 | Not Started | 74 | No | 85 | Green |  |  |  | 0
Crystal Lagoon | Crystal Lagoon | Crystal Lagoon | HAP + Crystal Lagoon Review | Tark |  | 2026-07-23 | 2026-10-05 | Not Started | 74 | No | 113 | Green |  |  |  | 0
Crystal Lagoon | Crystal Lagoon | Crystal Lagoon | 50% Detailed Design | Tark |  | 2026-07-16 | 2026-07-20 | Not Started | 4 | No | 36 | Green |  |  |  | 0
Crystal Lagoon | Crystal Lagoon | Crystal Lagoon | HAP Review - 50% DD + Crystal Lagoon Review | Tark |  | 2026-08-13 | 2026-08-17 | Not Started | 4 | No | 64 | Green |  |  |  | 0
Crystal Lagoon | Crystal Lagoon | Crystal Lagoon | 100% Detailed Design | Tark |  | 2026-09-03 | 2026-09-07 | Not Started | 4 | No | 85 | Green |  |  |  | 0
Crystal Lagoon | Crystal Lagoon | Crystal Lagoon | HAP Review - 100% DD + Crystal Lagoon Review | Tark |  | 2026-10-01 | 2026-10-05 | Not Started | 4 | No | 113 | Green |  |  |  | 0
Crystal Lagoon | Crystal Lagoon | Crystal Lagoon | Tender Package | Tark |  | 2026-10-22 | 2026-10-26 | Not Started | 4 | No | 134 | Green |  |  |  | 0
Crystal Lagoon | Crystal Lagoon | Crystal Lagoon | HAP Review - TD + Crystal Lagoon Review | Tark |  | 2026-11-05 | 2026-11-09 | Not Started | 4 | No | 148 | Green |  |  |  | 0
Crystal Lagoon | Crystal Lagoon | Crystal Lagoon | Tender Action | Tark |  | 2027-02-25 | 2027-03-01 | Not Started | 4 | No | 260 | Green |  |  |  | 0
Crystal Lagoon | Crystal Lagoon | Crystal Lagoon | IFC | Tark |  | 2027-02-25 | 2027-03-01 | Not Started | 4 | No | 260 | Green |  |  |  | 0
Master Plan | Master Plan |  |  |  |  | 2026-01-11 | 2026-02-12 |  | 32 |  | -122 | Red |  | Master Plan¦Master Plan |  | 0
Master Plan | Master Plan | Master Plan | 100% Detailed Design |  | GDG | 2025-12-02 | 2025-12-10 | Completed | 8 | - | 0 | Red |  |  |  | 0
Master Plan | Master Plan | Master Plan | HAP Review - 100% DD |  |  | 2025-12-17 | 2025-12-16 | Completed | -1 | - | 0 | Red |  |  |  | 0
Master Plan | Master Plan | Master Plan | Tender Package |  | GDG | 2026-01-01 | 2026-02-08 | Completed | 38 | - | 0 | Red |  |  |  | 0
Master Plan | Master Plan | Master Plan | HAP Review - TD |  |  | 2026-01-11 | 2026-02-12 | Completed | 32 | - | 0 | Red |  |  |  | 0
Landscape DD, IFT & IFC | Landscape |  |  |  |  | 2026-01-11 | 2026-07-05 |  | 175 |  | 21 | Amber |  | Landscape DD, IFT & IFC¦Landscape |  | 0
Landscape DD, IFT & IFC | Landscape | Landscape DD, IFT & IFC | 100% Detailed Design |  | GDG | 2025-12-02 | 2026-02-19 | Completed | 79 | - | 0 | Red |  |  |  | 0
Landscape DD, IFT & IFC | Landscape | Landscape DD, IFT & IFC | HAP Review - 100% DD |  |  | 2025-12-17 | 2026-03-04 | Completed | 77 | - | 0 | Red |  |  |  | 0
Landscape DD, IFT & IFC | Landscape | Landscape DD, IFT & IFC | Cost Plan - 100% DD | Nour / Ali | Survtec | 2025-12-17 | 2026-05-25 | Completed | 159 | - | 0 | Red |  |  |  | 0
Landscape DD, IFT & IFC | Landscape | Landscape DD, IFT & IFC | Tender Package |  | GDG | 2026-01-01 | 2026-06-22 | Completed | 172 | - | 0 | Amber |  |  |  | 0
Landscape DD, IFT & IFC | Landscape | Landscape DD, IFT & IFC | HAP Review - TD | Dina |  | 2026-01-11 | 2026-07-05 | Inprogress | 175 | No | 21 | Amber |  |  |  | 0
Landscape DD, IFT & IFC | Landscape | Landscape DD, IFT & IFC | IFC Package |  | GDG | 2026-01-25 | 2026-07-19 | Not Started | 175 | No | 35 | Green |  |  |  | 0
Landscape DD, IFT & IFC | Landscape | Landscape DD, IFT & IFC | Tender Process |  |  | 2026-04-05 | 2026-09-27 | Not Started | 175 | No | 105 | Green |  |  |  | 0
Infrastructure | Infrastructure |  |  |  |  | 2026-01-11 | 2026-04-05 |  | 84 |  | -70 | Red |  | Infrastructure¦Infrastructure |  | 0
Infrastructure | Infrastructure | Infrastructure | 100% Detailed Design |  | GDG | 2025-12-02 | 2025-12-04 | Completed | 2 | - | 0 | Red |  |  |  | 0
Infrastructure | Infrastructure | Infrastructure | HAP Review - 100% DD |  |  | 2025-12-17 | 2025-12-19 | Completed | 2 | - | 0 | Red |  |  |  | 0
Infrastructure | Infrastructure | Infrastructure | Tender Package |  | GDG | 2026-01-01 | 2026-02-08 | Completed | 38 | - | 0 | Red |  |  |  | 0
Infrastructure | Infrastructure | Infrastructure | HAP Review - TD |  |  | 2026-01-11 | 2026-02-12 | Completed | 32 | - | 0 | Red |  |  |  | 0
Infrastructure | Infrastructure | Infrastructure | IFT ( Modifications regarding Kiosks) |  |  |  | 2026-03-30 | Completed |  | - | 0 | Red |  |  |  | 0
Infrastructure | Infrastructure | Infrastructure | HAP Review - TD |  |  |  | 2026-04-05 | Completed |  | - | 0 | Red |  |  |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
[12 empty] | Amber |  | ¦ |  | 0
Formulas:
Overdue? = IF([Parent]="","",IF([Actual / Forecast Finish]="","",IF([Status]="completed","-",IF([Actual / Forecast Finish]>TODAY(),"No","Yes"))))
Overdue? = IF([Actual / Forecast Finish]="","",IF([Actual / Forecast Finish]>TODAY(),"No","Yes"))

## Refresh
Projects TRACKER Refresh
Hassan Allam Properties
All